## Slide 1
Sub-Activity 5.4.1.1: Populate the Beneficiary and Technology Tracking Tool (BTTT) Tanzania, Malawi, and Zambia with information about AR technologies applied, and farmers/households engaged in validating the technologies. Daniel Magalla
6. Deliverables | Means of verification | Delivery date | Achievement Status Sept 2021
6.1 Updated, harmonized, and documented BTTT for Malawi | Activity report submitted to Chief Scientist, progress report submitted to Chief Scientist and updated BTTT in AR Websites | January - February 2021 | Completed, (numbers consolidated online) https://www.dropbox.com/s/s6qbng743dbudh0/Updated_Direct%20Beneficiaries%20in%20%20Malawifn.xlsx?dl=0
6.2 Updated, harmonized, and documented BTTT version for Zambia | Activity report submitted to Chief Scientist, progress report submitted to Chief Scientist and updated BTTT in AR Websites | March - April 2021 | Partially Completed, (numbers consolidated online), inclusion of 1,223 names of direct beneficiaries in BTTT to be completed in October
6.3 Updated, harmonized, and documented BTTT for Tanzania | Activity report submitted to Chief Scientist, progress report submitted to Chief Scientist and updated BTTT in AR Websites | April – June 2021 | Completed http://africa-rising-wiki.net/images/7/79/DMangalla_MeetingUpdate_2021.docx
Proposed action for 2021/2022: Work with Munya to populate list of 1,223 direct benefciaries and their corresponding technologies in Zambia by October 2021 |  |  | 

## Slide 2
Sub-Activity 5.4.1.2: Populate the technology scaling tool with detailed information on scaling data for Tanzania, Malawi, and Zambia
6. Deliverables | Means of verification | Delivery date | Achievements March 2021 | Achievement Status Sept 2021
6.1 Complete package of AR workbook with details on number of scaling beneficiaries, technologies scaled, responsible researcher, name of development partner, scaling approach | Activity report submitted to Chief Scientist, progress report submitted to Chief Scientist and updated workbook in AR Websites | January - August 2021 | Completed http://africa-rising-wiki.net/images/7/79/DMangalla_MeetingUpdate_2021.docx https://www.dropbox.com/s/k6cy52pm2vwwmwp/AR%20Research%20partners%20and%20Beneficiaries%20Tracking.xlsx?dl=0 | Completed with additional numbers from Malawi, Set of technologies scaled provided in scaling data sheet attached. http://africa-rising-wiki.net/images/7/79/DMangalla_MeetingUpdate_2021.docx https://www.dropbox.com/s/k6cy52pm2vwwmwp/AR%20Research%20partners%20and%20Beneficiaries%20Tracking.xlsx?dl=0
Proposed action for 2021/2022: Collect more scaling data from Lead Foundation in Dodoma, and new project sites in Singinda and Monduli DC. |  |  |  | 

## Slide 3: Trends of Cumulative Direct & Scaling Beneficiaries 2015/2016 - 2020/2021: AR -ESA-Impact Targets Status

## Slide 4
Sub-Activity 5.4.1.3: Design simple research rack up database and populate it with research rack up data for Tanzania, Malawi, and Zambia)
6. Deliverables | Means of verification | Delivery date | Achievement Status Sept 2021
6.1 Simple Kobol Toolbox database with all the information about research rack up data (research output title, description, output type, phases of the output in R&D, type of technology, technology recipient type and name if scaled, crop/breed type, research partners and type, country/region technology evaluated and released, Feed the Future Innovation Exchange Information (FTFIE) for all 58 technologies developed and data entered | Database developed data entered, analyzed and report shared in AR website | January - Sept 2021 | Partially Completed: Research rack up KobolToolBox database designed and tested , gathering of data from researchers started, XX researcherssubmitted and data entry done. Link to koboltoolbox data entry https://ee.kobotoolbox.org/x/v8wczRCs
6.2 Research rack up data (research output title, description, output type, phases of the output in R&D, type of technology, technology recipient type and name if scaled, crop/breed type, research partners and type, country/region technology evaluated and released, Feed the Future Innovation Exchange Information (FTFIE) for all 58 technologies submitted to USAID web-based research rack up data for 2021 | Data submission to USAID research rack up online data platform done and activity report submitted to Chief Scientist | October - December 2021 | To be completed on December 4th 2021
Proposed action for 2021/2022: Finalize research rack up data entry by Oct 15th then proceed with Data submission on to USAID research rack up database by 4th December |  |  | 

## Slide 5
Sub-Activity 5.4.1.4: Conduct data quality assessment (DQA) to verify number of direct beneficiaries reported against those verified in source data for the selected sites
6. Deliverables | Means of verification | Delivery date | Achievements March 2021 | Achievement Status Sept 2021
6.1 Project Data quality assessment report for ESA region (Tanzania, Malawi, and Zambia) | Report shared with chief scientist and published in AR website | February - March 2021 for Tanzania | Completed for Tanzania http://africa-rising-wiki.net/images/b/bb/DMangalla_DataQuality_2021.docx | Completed for Tanzania http://africa-rising-wiki.net/images/b/bb/DMangalla_DataQuality_2021.docx Activity was not done in Malawi & Zambia due to travel restrictions courtesy of COVID-19
Proposed action for 2021/2022: Conduct data quality assessment(DQA) in Malawi & Zambia |  |  |  | 

## Slide 6
Sub-Activity 5.4.1.5: Provide additional capacity building and work with ESA research partners to ensure timely (and complete) submission of FTF indicators data, research rack up data, country narratives, IM performance narratives for Fiscal Year 2021, compliance with the AR Data Management Plan (Dataverse data uploading and sharing)
6. Deliverables | Means of verification | Delivery date | Achievement Status Sept 2021
6.1 Training materials to address gaps asociated with FTF &Dataverse submssion, IM performance narratives, Research rack up prepared and capacity built to researchers | Report shared to chief scientist and uploaded in AR website | April - June 2021 | Partially Completed Capacity built to few researchers in Tanzania, PPT shared to them as a guide and consideration during preparation of FTF, Dataverse, IM performance Narratives
6.2 Workbook with data summary on 2021 achievements on the five FtF indicators and for each ESA country, dis aggregated by individual research theme/group who submitted indicator target and additional data as necessary, list of IM performance and country narratives, research rack up data | Activity report, progress report and FtF data, narratives uploaded in DIS system | September – November 2021 | in progress, to be completed in Novermber;
6.3 Workbook with a list of research themes/groups by country, PIs, and their email contact, associated to datasets collected and to be collected etc. since 2013 (according to the proposals) | Activity report, progress report and data submitted in Dataverse | July - October 2021 | In progress, Partially Completed; 4 number of researchers submitted their Datasets & meta data for review up to now
Proposed action for 2021/2022: Work with researchers to ensure all dataverse, FTF data, IM performance narratives are prepared and uploaded to dataverse, USAID DIS system by 4th November 2021 |  |  | 

## Slide 7
Sub-Activity 5.4.1.6: Contribute to the development and implementation of learning efforts, documentation and sharing of best practice
6. Deliverables | Means of verification | Delivery date | Achievement status March 2021 | Achievement Status Sept 2021
6.1 Policy briefs, reports and other related knowledge products and scientific publications | confirmation from journal o acceptance of articles, CG space | February - September 2021 | Contributed compilation of scaling data to the work by chief scientists | Partially completed 1. Contributed on the compilation of scaling data to the work by chief scientists 2. Study by Francis Muthoni not implemented this year 3. Documentation of success story to continue in October in collaboration with Comunication team/Swai
Proposed action for 2021/2022: 1. Collect more scaling beneficiary numbers from Lead Foundation (Dodoma, Singida, Monduli) and IOP (Karatu) for contributing on the work being done by chief scientists 2. Work with communication team & Swai to document success story in Kongwa |  |  |  | 

## Slide 8
Dataverse/Research rack up FtF data: key items
FtF data: 4 out of 10 researchers submitted FTF data in 2020 without providing narratives for 10% difference nor filling IM performance narrative sessions, kindly take not of key issues as in the guide i sent recently and do correctly for 2021 submission(no one submitted 2021 FTF data by 8 August 2021, complete submission by October 1st to allow time for review)
Dataverse: 44 datasets+metadata, received and uploaded from more than 11 scientists in 2020,(only 4 datasets received from Gichohi, Martha, Julius, & Jumbo for 2021 - pending reviews before upload; Ensure complete submission by October 5th )
Research Rack up data: data for 16 technologies received so far from Swai, N’Danikou,Job,& Christian: Ensure you submit by 1st October in accordance with achievements you claim in FTF Indicator no. E.G.2-7. more than 50 techs to be submitted this year if achievements remains like last year.
IM performance narrative: Along with FTF , submit IM performance narratives to enable completion of country level & project level performance narratives