## Slide 1
Deliverables | Status (March 2021) | Status (August 2021)
SI field trials established for each site | Done during Jan 2021. List of field trials, host farmer names available | Crops harvested, data being processed
Baby trials established by at least 3000 farmers experimenting with SI technologies | Data being analysed as part of the panel survey | Manuscript on data from panel suvey being developed (Philip Grabowski, Sieg Snapp, Regis Chikowo: SI drivers and impacts from the plot-level to the landscape-level
Benefits of SI technologies evaluated across sites | Chiwimbo Gwenambira-Mwika, Sieglinde S Snapp, Regis Chikowo, Broadening farmer options through legume rotational and intercrop diversity in maize based cropping systems of central Malawi. Field Crops Research (Accepted with revisions) | Paper fully published (Chiwimbo Gwenambira-Mwika, Sieglinde S Snapp, Regis Chikowo. 2021. Broadening farmer options through legume rotational and intercrop diversity in maize-based cropping systems of central Malawi. Field Crops Research https://doi.org/10.1016/j.fcr.2021.108225
At least one field day per EPA conducted | COVID has persisted, no field days permitted throughout Malawi | completely suspended for the rest of the year
At least two farmer exchange visits conducted | COVID has persisted, no exchange visits are permitted | completely suspended for the rest of the year
Sub-activity 1.1.1.2 Investigations on the medium to long term impacts of SI technologies (improved soil fertility management, improved germplasm, crop combinations, nutrient and water management) on crop productivity on multi-locational field sites and baby trials.

## Slide 2
Deliverables | Status (March 2021) | Status (August 2021)
Africa RISING attends at least one DAECC-led district workshop for SI technologies dissemination | Prohibitions on meetings remained in place | Prohibitions on meetings remained in place
Data uploaded on to DataVerse | To be completed by August 2021 | Data available and submitted for uploading on dataverse
FtF indicators data submitted to M&E/IFPRI for upload | To be completed by August 2021 | FTF data has been provided
List new deliverables planned after above submission | Six key field sites maintained; link with one CGIAR LTEs 2. Manuscript developed | 
Proposed action for 2021/2022: Select six key field sites that will be transformed to Long Term Experiments (LTEs), as part of an Africa RISING Legay; integration with One CGIAR initatives on long term experiments Continue with data synthesis, and take measurements by depth for accumulated decade C sequestration (2012 to 2022) |  | 
Sub-activity 1.1.1.2 Continued..

## Slide 3
Deliverables | Status (March 2021) | Status (August 2021)
Mother trials for water limited yields established | Trials for 2021 established as planned | Benchmark yields from trials being integrated in analysis
Revised protocol finalized | Protocol updated and approved as part of 2021 workplans | All three modules implemented. Data available and being processed
Detailed farm profiles documented (Data sets by farm typologies; estimates of yield gaps; farm-scale SI scaling compiled.) | Data collected from Module 1; electronic survey instrument created using surveystack and used to implement both Modules 1 and 2 | Modules 2 and 3 successfully implemented. Data files submitted for dataverse upload
Activities by implementing students monitored | Students have begun synthesizing Module 1 data | Graduate students collected data; now synthesis ongoing
Estimates of yield gaps; farm scale SI scaling (formerly Data sets by farm typologies; estimates of yield gaps; farm-scale SI scaling compiled) | Yield cuts data collection for yield estimations currently underway for mother trial host farms, baby farmers, and local controls | Whole farm yield measurements were completed. Datafiles available; data being processed; Data also submitted for dataverse upload.
Data uploaded on to dataverse | To be done at a later date(August/September 2021) | Data files submitted for dataverse uploading
Sub-activity 5.1.1.4. Case studies: Application of SI technologies use among farmers interacting with Africa RISING at different intensities

## Slide 4
Deliverables | Status (March 2021) | Status (August 2021)
FtF indicators data submitted to M&E/IFPRI for upload | NA | NA
Survey instrument verified (Module 3) | Survey instrument was verified in November/December 2020 https://bit.ly/2OoLlBH New sites were selected for the survey; instruments shared with partners | Module 3 implemented and all data collected, Analysis partially completed and results are put into a report (Consultancy Report from Munyaradzi Mutenje)
Econometric model set up | This is still under development | Data was all collected and analysis is in progress
Model Results after validation | No results are yet available, which will be finalized after the 3rd wave | Data was all collected and analysis is in progress
Data generated and uploaded into Dataverse | No results are yet available. It will be finalized in July/August 2021 | Data is still being analysed – upload expected by End of September 2021
 |  | Drivers of Sustainable Intensification technology uptake; Implication on adaptive capacity, food security and scaling Submission in October to:Technology forecasting and social change Student thesis of Module 3 (no link yet)
Sub-activity 5.1.1.4. Continued (CIMMYT)

## Slide 5
Deliverables |  | 
List new deliverables planned after above submission | In depth study of a subset of intensified and stagnant farms Mansciprt submitted by April 2022 | 
Proposed action for 2021/2022: Continue with data synthesis, link modules 1,2 and 3. Follow up with a subset of intensified farms and contact in-depth analysis of their circunmstances. Also a subset of stagnant farms toi be revisited. |  | 
Sub-activity 5.1.1.4. Continued (CIMMYT)

## Slide 6
Deliverables | Status (March 2021) | Status (August 2021)
Updated panel survey instrument | Instrument for legumes survey available and being used for implementation grain legumes yield cuts | Instrument available and was used at harvest to track grain legumes production for 120 farms.
Panel survey implemented | Panel legumes survey implementation being completed by end of April 2021 | Grain legumes survey implemented. Datra submitted for dataverse;Data analysis has began
Meta-analysis data collated | Some data fully analysed, papers published, some in progress (Bill and Jayne, 2020; Bill et al. 2020 | Innocensia Festo John, Sieglinde Snapp, Alison Nord, Vimbayi Chimonyo, Chiwimbo Gwenambira, Regis Chikowo 2021. Marginal more than mesic sites benefit from groundnut diversification of maize: increased yield, protein, stability, and profits. Agriculture, Ecosystems and Environment 320:107585 (https://doi.org/10.1016/j.agee.2021.107585) Burke B and Jayne T. 2021. Disparate access to quality land and fertilizers explain Malawi’s gender yield gap. Food Policy. 100: 102002. https://doi.org/10.1016/j.foodpol.2020.102002
Soil analysis | Soil bulk density determined, data available, other data pending | All data available. Bulk density being used for soil C stocks computations
List new deliverables planned after above submission | Data integration in meta-analysis manuscripts | 
Sub-activity 5.1.1.5: Panel survey, soils processing and meta-analysis studies for maize-grain legumes sequences and implications for sustainability

## Slide 7
Deliverables | Status (March 2021) | Status (August 2021)
At least one nutrient x water management trial established per EPA | Three repeat field trials successfully established in Ntubwi, Nsanama and Nyambi as planned during Jan 2021 | Accomplished earlier in the year
Field days held with partners | Field days are currently suspended | Field days are currently suspended
Soil water and nutrients use interactions determined | Experiments just harvested. Data to be included in next report | Data compilation completed. The three field sites that had persisted uin Machinga have now been completed
At least 10,000 farmers practicing tied ridges across projects site; technology dissemination affected by District Ext. Coordination Committees | Targeting 15,000 this season. | Onfarm work curtailed by COVID related restrictions. Monitoring activities handicapped over the year.
Manuscript | Not much progress on this during this period. We concentrated on other outputs | Data synthesis on-going
Data uploaded on to DataVerse |  | Data provided for uploading as required
FtF indicators data submitted to M&E/IFPRI for upload |  | 
Proposed action for 2021/2022: continue with data synthesis, and publications |  | 
Sub-activity 2.2.1.2: Investigations on nutrient and water management for climate resilience along a climate gradient in southern Malawi

## Slide 8
Deliverables | Status (March 2021) | Status (August 2021)
At least one field trial established in Linthipe and Ntubwi | This work was completed during 2019 | NA
Site description details (soils, seasonal rainfall) | NA | NA
Density x variety x seed generation assessed | This work was completed during 2019; MSc thesis has been defended | 
At least 5000 farmers in Dedza and Machinga adopting double-row cropping of groundnut | The Panel survey showed some adoption of the technology | 
MSc thesis | Kalumba defended thesis | Thesis since completed
Scaling. Information from trials to be discussed with Malawi Agricultural Technology Assessment Committee | DAECC partners have adopted double-row groundnut as an intensification pathway | 
Sub-activity 1.1.1.3. Determining the productivity of groundnut as a function of seed generation x variety x density interactions in two contrasting agro-ecologies, and rotational benefits to maize

## Slide 9
Deliverables | Status (March 2021) | Status (August 2021)
Goat feeding trials established |  | 
Weight gain assessments done fortnightly | NA – experiments never completed well | Discontinued
Breeding goats available to communities | NA – experiments never completed well | Discontinued
MSc thesis (old student) Research proposals (new student) | NA – experiments never completed well | Discontinued
Proposed action for 2021/2022: None |  | 
Sub-activity 1.1.1.4. Exploring productivity of goats under controlled breeding and feeding regimes among young breeding female goats in crop-livestock system in Malawi (2018)