IMPROVING PRODUCTIVITY OF LOCAL CHICKENS THROUGH BETTER NUTRITION MANAGEMENT IN MIXED CROP-LIVESTOCK FARMING SYSTEMS, BABATI, TANZANIA.

PROTOCAL FOR FIELD ACTIVITIES

ACTIVITY 1: Crosscutting activity on training and field days (With forage and crop residue team) on

“Training on Feed Ration Preparation (Total Mixed Ration and Crop Residues Based Ration) based on locally available Livestock Feed Resources fed to Dairy cattle and Poultry for the Smallholding

Crop-livestock Farmers in Babati”

The training and study visit will be carried out in Babati district. Six villages adopted in the Africa RISING projectwill be involved in the study. The Six villages are; Long village which is located in the humid highland zone, Seloto village which is located in the sub humid highlands, Sabilo village which is located in the semi-arid uplands, Hallu which is located in semi humid-arid midlands, Matufa and Shaurimoyo which are both located in semi-arid lowlands.

Table 1: The agro ecological zones of Babati district

| No. | Agro-ecological zone | Altitude (m a.s.l) | Rainfall (mm/year) |
| --- | --- | --- | --- |
| 1 | Humid highlands | 2,150 – 2,450 | 1,200 |
| 2 | Sub humid highlands | 1,850 – 2,150 | 1,100 – 1,200 |
| 3 | Semi humid uplands | 1,500 – 1,850 | 900 – 1,100 |
| 4 | Semi humid arid midlands | 1,200 – 1,500 | 750 – 900 |
| 5 | Semi-arid lowlands | 950 – 1,200 | 500 - 750 |

Source: Babati district profile (2002).

VILLAGE AND FARMERS SELECTION FOR TRAINING

Farmers to be selected toparticipate in the training will be those who already adopted by the Africa RISING project and showed active participation in different on-farm activities in their host farms during the research period. Also, these farmers should be ready to train other farmers in their villages.

CRITERIA FOR SELECTING FARMERS

Farmers to participate in the training will be selected after discussion with the extension officers on the following basic criteria’s;

- A farmer should be the residence of the selected Africa RISING project intervention,

- Farmers should have a well-constructed store, cattle shed, feed troughs and feed crop residues

- Keeping one of the major livestock which are normally fed on the crop residues

TRAINING SCHEDULE

Training will be conducted in three sites Seloto, Matufa and Hallu. One day training will be conducted per site as follows:-

- Farmers from Long, Sabilo and Seloto/Beremi and Haysam will be trained at Seloto village

- Farmers from Hallu and Gallapo will conduct the training at Gallapo

- Farmers from Shaurimoyo and Matufa will be trained at Matufa village

Proposed time to start the training with farmers will be 8:30 AM.

Tentatively, the expected time table will be as indicated in a table below;

| Date | Place | Activity | Time |
| --- | --- | --- | --- |
| Day 1 | Babati | Meet with Research Team agree on mode of conducting the training and organise training material | 09:00 – 14:00 hrs. |
| Day 2 | Seloto | Training and preparation for field day | 08:30 – 12:00 hrs. |
| Day 3 | Matufa | Training | 08:30 – 12:00 hrs. |
| Day 4 | Gallapo | Training | 08:30 –12:00 hrs. |
| Day 5 | Seloto | Preparation of Displaying materials for Farmers field day | 08:30 – 16: 00 hrs. |
| Day 6 | Seloto | Farmers field day | 08:30 – 15:00 hrs. |

REPORTING SCHEDULE

Reporting of the activities will be reported after completion of training and study visit/farmers field day

ACTIVITY 2: Evaluating the effect homemade rations on growing chickens in Babati district

The study on existing management practices and their impact on growth performance and mortality rate for the local chickens were done through the pilot experiment, searching out the current status in local chickens’ production, management and the core problems which hinders of productivity chickens in rural areas.

The results from the pilot study gave the starting point in feeding intervention which is the main objective of this study. The study expect to asses a total of 1,800 grown chicks to three different villages (Matufa, Galapo and Seloto/Bermi) each village with 600 growing chicks. However, the purchase and distribution of the chicks is done in three different clusters due to availability of the grown chicks. We have managed to reach the first two clusters , Matufa village and Galapo village. This activity then will target to reach the third and last village, (Seloto/Bermi Village).

Sub-activities

- purchase of experimental chicks

- distributions of experimental chicks

- Field data collection

# 2.2. Methodology

# 2.2.1.  Study site

The chicks will be distributed at Seloto/Bermi village while data collection on growth rate, disease incidences, survivability and cost of the feeding intervention will be done at Galapo Matufa and Seloto/Bermi villages.

# 2.2.2. Experimental chickens

One month old experimental chickens (300 local and 300 crossbred chickens) will be acquired at a one of the chick producer (Kwaraa farm) at Babati. The chickens will be tagged for easy identification. Moreover, vaccination against new castle and fowl pox diseases will be done prior distribution to different treatments at farm level.  The chickens will be allocated to three different feeding systems, replicated to 5 different farmers, each replicate with 20 chickens as illustrated in fig1.

2.2.3. Experimental design

The current trials will be set  in Seloto villages where by 10 farms will be engaged. Each farmer will be supplied with 20 chicks as outlined in fig 1 below.

### Fig.1: Experimental layout per village

| Genetic group | Feeding systems |  | Number of chickens |  |
| --- | --- | --- | --- | --- |
|  |  | Vegetable based ration | 5 farmers x 20 birds=100 chickens |  |
| Local chickens) | Non-vegetable based ration |  | 5 farmers x 20 birds=100 chickens |  |
|  | Scavenging |  | 5 farmers x 20 birds=100 chickens |  |
|  | Vegetable based ration |  | 5 farmers x 20 birds=100 chickens |  |
| Crossbred chickens | Non-vegetable based ration |  | 5 farmers x 20 birds=100 chickens |  |
|  | Scavenging |  | 5 farmers x 20 birds=100 chickens |  |

2.2.4. Data collection

Farmers will be sensitized on participatory data collection. One trainee is involved in data collection in collaboration with farmers within the village. The data collection sheets in appendix 1, 2, 3 and 4 will be used as the guide in data collection. The data to be collected will include growth, mortality, disease incidences and costs of the intervention.

2.3. Expected outputs

Conduct farmers training

Data collection in place

Data analysis in place

APPENDECES DATA COLLECTION SHEETS Appendix 1; GROWTH RECORDS. Farmer's name……………………………………………….VILLAGE………………………………………...Coordinates……………….…….… ……………….………Phone……………………………... Date of measurement. Chicken’s ID; Sex; Genetic group; Feeding system; Initial weight; wt at 8wk; Wt at 10wk; Wt at 12wk; Wt at 14wk; Wt at 16wk; Wt at 20wk; Remarks. Where ‘w’=weight, ‘wk’=week.

Appendix 2; DISEASE INCIDENCE RECORDS. Farmer’s name………………………………………… Village……………………………… Coordinate………………………… ………………………… Phone……………………………….. Number of chickens at the start of experiment 1; indigenous chickens………………………….., Crossbred chickens……………………………….. Disease incidence date; Feeding system in use; Genetic group; Total number of chickens per management system/genetic group; Number of chickens died of the disease; Disease type/Symptoms.

APPENDIX 3; MORTALITY RECORDS. Farmer's name……………………………………………… Village………………………………………...Coordinates…………………………….Phone……………………….. Number of chickens at the start of experiment 1; indigenous chickens……………………. Crossbred chickens……………………... Death date; Chicken ID; Sex; Genetic group; Management system; CAUSES/SYMPTOMS/REMARKS.

Appendix 4; COST RECORDS Farmer's name……………………………………………….VILLAGE………………………………………...Coordinates……………….…….… ……………….………Phone…………………………….. Feeding system……………………………………………..Genetic group………………………………….. Initial cost; Number of birds; Costs incurred; Remarks. At 6 weeks. At6- 8 weeks. At 8-10 weeks. At 10-12 weeks. At 12-14 weeks. At 14-16 weeks. At16-20 weeks.