LOGICAL FRAMEWORK

| Project Title: | Sustainable intensification of key farming systems in the Sudano Savannah of West Africa |  | Date: | 12 January, 2012 AMEEDD |
| --- | --- | --- | --- | --- |

|  |  | Narrative Summary | Objectively Verifiable Indicators | Means of Verification | Responsible institution | Important Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
| Development Hypothesis | If Purpose, then Goal | Goal: |  |  |  |  |
|  |  | Project Purpose: |  |  |  |  |
|  | If Outputs, then Purpose |  |  |  |  |  |
| Manageable Interest |  | Outputs: Disaggregate? And define scope? [The project’s tangible results] Should these be disaggregated? - Integrated crop and livestock production systems developed, evaluated, and (put in as another output? Also economics?) effectively delivered to end users. | #s of technologies #s of farmers/hacteres |  |  | - Continued commitment of all partners - Peace and security in the region - Stable rainfall - Continuous commitment by donors - Timely release of project funds - Stability of staff in partner institutions - Stable currency exchange rates |
|  | If Inputs, then Outputs |  |  |  |  |  |
|  |  | - Innovative harvest and post-harvest technologies and practices identified, evaluated and promoted (add another for delivery?). |  |  |  |  |
|  |  | Inputs (ACTIVITIES): 1.1. Diagnostic survey to identify bio-physical constraints, opportunities and entry points | - Complete database on constraints and opportunities available for use for planning interventions | Survey report | IITA, AfricaRice, ICRISAT, CSIR-SARI, IER, |  |
|  |  | 1.2. Evaluate and promote integrated soil fertility options | - Level of improvement of soil fertility | Soil monitoring reports | CSIR-SARI, IER, ICRAF, IITA, AfricaRice, SANREM-CRSP |  |
|  |  | - Evaluate and promote integrated parasitic weeds management options | Reduced parasitic weeds infestation and increased crop yields | Weed monitoring survey reports and publications | IITA, AfricaRice, ICRISAT, IER, CSIR-SARI |  |
|  |  | - Evaluate and promote integrated pest management for insect pests, weeds and diseases | Reduced pesticide use, pest damage, increased biodiversity, and increased crop yields | Survey reports and publications | CSIR-SARI, IER, IPM-CRSP, IITA, AfricaRice, AVRDC, ICRISAT |  |
|  |  | 1.5. Evaluate and promote options for adaptation to drought | Reduced crop loss due to drought | Crop yield reports and publications | IITA, AfricaRice, ICRISAT, IER, CSIR-SARI |  |
|  |  | 1.6. Evaluate and promote options for adaptation to flooding and submergence in lowland rice | - Reduced crop loss due to flooding and submergence | - Crop yield reports Publications | AfricaRice, CSIR-SARI |  |
|  |  | 1.7. Introduce, evaluate and promote water-efficient crop varieties | - Number of varieties introduced and released in Ghana and Mali | - Varietal release report for each country | IITA, AfricaRice, ICRISAT, CSIR-SARI, IER, AVRDC |  |
|  |  | 1.8. Introduce and evaluate crop management practices (planting dates, spacing, density, etc.) to optimize crop productivity | - Number of practices promoted and adopted - Level of increase in crop yields | - Farmers’ testimonies - Reports - Publications | IITA, AfricaRice, ICRISAT, SANREM-CRSP, IER, CSIR-SARI |  |
|  |  | 1.9. Develop and promote feeding strategies for small ruminants | - Number of feeding strategies promoted and adopted - Weight gain by small ruminants | - Farmers’ testimonies - Reports - Publications | ILRI, ICRAF, CSIR-SARI, CSIR-ARI, IER |  |
|  |  | 1.10. Introduce and assess the productivity performance and profitability of cross-bred small ruminant breeds | - Number of cross-bred small ruminants introduced - Quantity of milk and meat produced - Level of income | - Farmers’ testimonies - Reports - Publications | ILRI, CSIR-ARI, IER |  |
|  |  | 1.11. Introduce, evaluate and promote high value fruits and vegetables to improve system productivity | - Number of vegetables and fruits introduced - Yield levels - Income | - Farmers’ testimonies - Reports - Publications | AVRDC, CSIR-SARI, ICRAF, HORT-CRSP, IER, IPM-CRSP |  |
|  |  | 1.12. Undertake value chain analysis to identify market opportunities for smallholder farmers | - Utility and value chain perspectives on challenges and opportunities are identified and evaluated at key sites - Complete database of stakeholders’ perspectives on innovations and adoption of innovations collected | - Analysis reports - Publications | CSIR-SARI, IER, AfricaRice, |  |
|  |  | 1.13. Organize community-based seed production systems and link to seed companies (is this appropriate for this project?) | - Number of farmers producing own seeds - Quality of seeds produced and sold - Number of seed companies linked to seed producing farmers | - Survey report - Publications | CSIR-SARI, ICRISAT, IITA, AfricaRice, ICRAF, AVRDC, IER |  |
|  |  | 2.1. Introduce, evaluate, adapt, demonstrate and promote improved crop storage practices (is this appropriate for this project?) | - Number of crop storage facilities established - Level of storage losses | - Survey reports - Publications | HORT-CRSP, CSIR-SARI, IER, IITA |  |
|  |  | 2.2.. Introduce, evaluate, adapt, demonstrate and promote appropriate low-cost harvest and post-harvest technologies and practices | - Number of technologies introduced - Number of farmers using the introduced technologies | - Farmers’ testimonies - Reports - Publications | IMPLEMENT Factory-MOFA, AfricaRice, HORT-CRSP, CSIR-SARI, IER |  |
|  |  | 2.3. Introduce, evaluate, demonstrate and promote harvesting techniques to reduce aflatoxin | - Number of techniques introduced - Number of farmers using the techniques - Level of aflatoxin | - Farmers’ testimonies - Reports - Publications | IITA, ICRISAT, PEANUT-CRSP, CSIR-SARI, IER |  |
|  |  | 2.4. Introduce, evaluate and promote technologies for adding value and diversifying products | - Number of new products - Level of income | - Reports - Publications | AfricaRice, IITA, IER, CSIR-SARI |  |