## Slide 1
Sub-activity 1.1.1.8: Explore, document, and assess the sustainable intensification pathways of 3 farming system case studies in Tanzania to inform scaling potential. Lieven Claessens
Deliverables | Status (March 2021) | Status (August 2021)
Inventory of existing data for the three farms | The exercise is complete. | 
Interviews and surveys with farmers conducted and data gaps filled | 3rd farmer interview still not conducted due to COVID-19. It is considered that the data generated in the survey by Mutungi and Manda is sufficient to inform the case study analysis. | Data from HH survey were sufficient to perform the analysis with the 3 farms originally proposed.
Farming systems analyzed with SIAF and FarmDESIGN | MSc thesis titled “Scenarios for assessing and improving performance of smallholder farms in Tanzania affected by economic and climatic disturbances” is finalised. | MSc thesis titled “Farm performance evaluation Holistic impact assessment of project promoted sustainable intensification innovations at farm-level in Tanzania.” By Eveline Massop (WUR). Under review.
Sustainable intensification pathways assessed and documented | Outputs are contained in thesis mentioned above. | Outputs are contained in thesis mentioned above. Under review.
Data uploaded on to DataVerse | Recorded interviews have been transcribed. Household survey data was processed and is being analysed. | 
FtF indicators data submitted to M&E/IFPRI for upload | NA | NA

## Slide 2
Sub-activity 1.1.1.9: Assessing the impacts of Africa RISING technologies on the performance and resilience of multi-location and differentially exposed farming systems case studies in Malawi. Lieven Claessens
Deliverables | Status (September 2020) | Status (March 2021) | Status (August 2021)
Data from 2020 surveys processed and exchanged among team | New activity. | Completed. | 
Missing data (mainly on yields) collected | New activity. | Data collection is ongoing. | Missing data shared/modelled?
Farming systems analysed with FarmDESIGN | New activity. | Exploratory analysis is ongoing with available data. | Analysis completed
Adoption and impact of SI technologies for differentially exposed farming systems assessed and documented | New activity. | Exploratory analysis is ongoing with available data. | MSc Thesis submitted and under review

## Slide 3
Sub-activity 1.3.1.4: Ex ante impact assessment with Trade-off Analysis Model for Multidimensional Impact Assessment (TOA-MD) for regional relevance of Africa RISING technologies. . Lieven Claessens
Deliverables | Status (March 2021) | Status (August 2021)
Inventory of existing bio-physical data from Africa RISING experiments. | NA | 
TOA-MD model set up for Tanzania | NA | 
Ex-ante impact assessment implemented and analyzed | Analysis completed and documented as a Chapter in the PhD thesis of Shrabashi Ray. Draft journal article is pending final verification of some data and will be submitted before the next report. | Missing/erroneous data were received, analysis redone. Article will be submitted Sept21.
Data uploaded on to DataVerse | NA | 
FtF indicators data submitted to M&E/IFPRI for upload | NA |