## Slide 1
Sub-activity: 5.3.1.2: Role of gender from farm-to-fork and grain markets of legumes and dryland cereals in Kiteto and Kongwa
Deliverables | Status march 2021 | Status September 2020
Women empowerment as a result of access to yield-enhancing innovations and groups’ dynamics. | -Data analyses had no progress made because of administrative issues relating to student’s illness | -Gender data analyzed and manuscript in preparation
Publication | -Data analyses had no progress made because of administrative issues relating to student’s illness | -Gender data analyzed and manuscript in preparation
Capacity building-Msc student | - Data analyses had no progress made because of administrative issues relating to student’s illness | -Student studies halted and data now being handled fully by ICRISAT in collaboration with SUA staff
Nutrition indices associated with participating persons assembled to inform the benefits of rolling out the technologies at community level | -This will be completed in August 2021 | -Data analyzed and write up in preparation
Partnerships with development partners such as the World Food Programme established for scaling out of research knowledge | -This activity will be completed as projected | -This activity has not progressed as planned but will be the focus in 2021/2022
Proposed action for 2021/2022: (Should add value to this sub-activity) -Development of synthesis paper to inform future programming on how to link gender, Agriculture and nutrition for food and nutrition security -Develop knowledge products (e.g. extension bulletins, brochures, guide papers -Co-Researchers: Gundula, |  |