Agro-ecological intensification in Malawi through action research with smallholder farmers

Africa RISING- ESA Project Proposal 2014/16

December 2014

# RESEARCH TEAM COMPOSITION

Principal Investigators

Prof Sieglinde Snapp and Dr Regis Chikowo - Michigan State University, Department of Plant, Soil and Microbial Sciences, East Lansing, MI

| Name | Gender | Institution | Job title | Disciplinary expertise | Highest qualification | Project role/ responsibility | % time commitment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dr Fanny Chigwa | F | LUANAR | Lecturer | Animal Science | PhD | Livestock intensification | 15 |
| Dr Agness Mwangwela | F | LUANAR | Lecturer | Nutrition and Food Science | PhD | Nutrition and local level food processing | 15 |
| Dr Wezi Mhango | F | LUANAR | Lecturer | Agronomy | PhD | Agronomy/ action research | 10 |
| Dr Desta Lulseged Dr Roland Chirwa | M M | CIAT | Research Scientists | Soils and bean studies | PhD PhD | Beans integration (and soils) | 10 10 |
| Dr I Nyoka A. Mulwafu | M M | ICRAF | Research Scientists | Agroforestry/ livestock feeds | PhD MSc | Livestock intensification | 15 100 |
| Mrs A. Msukwa Mr O. Kumwenda | F M | DAES | DADO Ntcheu DADO Dedza | Extension | MSc MSc | Project R4D district platform hubs | 10 10 |
| Dr A. Arega | M | IITA | IITA Country rep | Economist | PhD | Malawi project hosting and supervision | 5 |
| Dr. Bekele Kotu | M | IITA | Agri. Economist | Agri. Economist | PhD | Economic analysis | 10 |

Table of Contents

RESEARCH TEAM COMPOSITION	2

SUMMARY	4

JUSTIFICATION (Research to impact trajectory)	5

METHODOLGY	6

Alignment to ESA project Logframe	6

Implementation plans and strategies	7

Project sites	8

Participatory action research and adaptive experimentation	9

Project thematic areas	9

Description of activities within themes	15

Expected outcomes - short, long term	19

Literature references	19

Global project activity schedule	21

USAID Indicator targets	23

Consolidated budget 2014/2015	25

Budgets notes: LUANAR Agronomy	26

Budgets notes: LUANAR Livestock Department	27

Budgets notes: LUANAR Nutrition Department	28

Budgets notes: CIAT	29

Budgets notes: ICRAF	30

Budgets notes: MSU	31

# SUMMARY

Over the past three years, Africa RISING Malawi has implemented action research in four farming communities (Extension Planning Areas, EPAs) in Dedza and Ntcheu districts. Various activities implemented by the consortium have identified plausible approaches that can help alleviate poverty across the communities through improved productivity of both crop and livestock components to enhance food security and nutrition outcomes. To date, key entry points have been sustainable intensification (SI) for productivity gains through refining crop sequences and spatial arrangements in maize-legume diversified systems, and improved fodder for intensified dairy production and goat meat production. This proposal outlines work-plans primarily for the period October 2014 to September 2015, but also includes our trajectory to September 2016. The proposal is organized into four thematic areas, which broadly address i) integrated maize-legume production systems, ii) livestock intensification, iii) nutrition and food processing, and iv) Research for Development (R4D) platforms and Networking. During Years 4 and 5, we will consolidate activities in the current action villages and more tightly integrate activities along thematic areas, as opposed to the work-packages approach, that has been used since project inception. Using participatory approaches, we propose to simultaneously disseminate mature technologies and implement research to consolidate technology components and packaging. To reach to thousands of farming households, we will strengthen the functioning of R4D platforms at district level, as well as those organized at action site level. We will deliver best-bet/best fit technologies for intensification across diverse farm typologies, and build capacity of farmers, graduate students and R4D stakeholders. The team will continue to invest in nutrition outcomes that we hypothesize to be centrally driven by gains in knowledge on local-level processing of grain legumes, when productivity constraints are already addressed at the field level. We envisage that farm-scale production strategies employed by different farm/farmer typologies will be further distilled through scenario analyses using farming systems simulation modeling approaches.

# JUSTIFICATION (Research to impact trajectory)

Over the past 3 years, the Africa RISING Malawi team has carried out both biophysical and socio-economic research in four action research sites, directly engaging over 1200 farming households. Some technologies have been newly introduced or refined and evaluated with farmers in a participatory action research mode. These included

- The doubled-up legume technology in which two legumes that have different growth habits are intercropped resulting in increased soil fertility and grain benefits

- Sequential cropping systems based on inoculated soyabean or groundnut and cowpea that enhance maize productivity under reduced fertilizer application

- Climbing and bush been varieties in association with fertilizer and manure application

- Local level grain legume processing and value addition technologies

- Fodder trees have been established to enhance availability of quality fodder for dairy cows

Of the technologies, we attach a lot of confidence on the first two that we deem to be ready for scaling up, while parallel research to refine these technologies will still continue to respond to emerging challenges noted during the first two years.  For example, the doubled-up legume technology will need to be further refined for specific agro-ecologies as insights from the past 2 years’ field work suggest that there are cases in which intra-specific competition is strong, calling for adjustments in companion plant populations or altered spatial crop arrangements.

Climbing beans have recently been evaluated in our action sites and require further investigations. For example, one of the varieties was shown to respond to manure application in an intercropping system with maize while such management produced an opposite effect on the other.  The next two require further research work to gain more insights on how the bean-based technologies perform across agro-ecologies and how local-level processing of grain legumes can be a pull factor to technology use. Clearly, work with fodder tree species does not readily produce results in the short term, and this is one area that we will continue to investigate during the 2014-2016 period.

Of the technologies that are ready to scale up and reaching 1000s of farmers, there remains a gap in how to efficiently involve relevant stakeholders to make this possible. To this end, the research team has begun working with various stakeholders and initiated Research for Development (R4D) platforms, operationalized at two levels:

- at the district level, capturing key government and NGO representation, and

- at the Extension Planning Area (EPA) level, principally involving community leaders, local extension and implementing farmers

While structurally already constructed, these platforms will need to be strengthened during the next 2 years, so as to be efficient conduits for agricultural transformation at different levels. We hope that anchoring the R4D platform on the existing government agricultural services structures together with development partners, will ensure that the platforms will persist beyond the Africa RISING project life.

The Africa RISING Malawi team is moving towards a more integrated approach to align with farm realities. It is generally agreed that the smallholder farms we are interacting with work as integrated but diverse units. Farm enterprises and management as dictated by the ‘farm typologies’ result in complex outcomes on soil, crop, and livestock productivity and environmental integrity. There is therefore need to appropriately package research products into forms easily usable by differently resource-endowed households. For example, the legume –maize sequence (rotations) may be the more efficient pathway for the well to do and market-oriented farmers, whereas the intercrops + doubled-up legumes technology will guarantee diversity of crops produced on small farms (< 0.5ha), resulting in positive nutrition outcomes. The next 2 years, therefore, provide an opportunity for refining and better targeting of the ‘best-bet’ technologies by farm typology, moving towards the desirable high systems functioning efficiency associated with the ‘best fit’ technology targeting scenario. We will continue to employ action-learning and systems approaches at scale across heterogeneous communities, a strategy that that has to date, proved effective, and replicable to other areas that generally have the same structure of farms.

# METHODOLGY

## Alignment to ESA project Logframe

In line with the ESA project logframe, the Africa RISING Malawi project aims to work with diverse farmers to sustainably intensify their agricultural enterprises, and enhance livelihoods, using entry points that have practical relevance to the local agro-ecologies. In Dedza and Ntcheu districts, our entry point hinges on harnessing the ecological benefits, nutritional and other direct economic benefits that accrue from intensified grain legume production on the farms that includes soyabean, groundnut, pigeonpea, cowpeas and bush/climbing beans. We hypothesize that this approach stimulates more closed nutrient cycling and systems productivity, resulting in farmers producing their staple maize more optimally when appropriate crop sequencing and soil nutrient management strategies are adhered to.

We recognize that historically, farm management recommendations in Malawi have generally not adequately aligned with agricultural risks, resource constraints and priorities of farmers (Snapp et al. 2003; Tenge et al. 2004). Moving into Years 4 and 5, this project will test a wider range of technological options across different farms, including targeted fertilizer application and legume-based technologies, and dairy production technologies, that are within the reach of resource poor farm families. We have identified a ‘local’ pigeonpea variety that we will use in action sites under improved management practices. This local variety is very popular with farmers as it is early maturing (May harvest) as opposed to improved varieties that mature well into the dry season, resulting in crop-livestock conflicts as the pigeonpea has to be protected, especially from goat damage. We will continue to evaluate in action groups with farmers different varieties of bush and climbing bean varieties to fortify protein and carbohydrates in local diets. Climbing beans generally have potential for higher yield compared to the bush beans, a trait that is advantageous for highly populated countries such as Malawi, to achieve increased food security levels and reduce poverty amongst farmers. Climbing beans also play a major role in crop rotation and intercropping systems, enhancing the productivity, not only to crops that are planted simultaneously, but also to those that follow in the rotation systems.

By the end of Year 5, we would have mobilized, sensitized and directly targeted at least 2000 farmers to experiment with different SI technologies, and expose at least 10 fold (20,000) more households to the technologies through community level activities such as field days and nutrition fares, with associated ripple effects expected to be enormous. We also anticipate realizing an increased participation by agricultural service providers, and other extension systems in learning platforms, which in turn is expected to stimulate increased demand for empirical knowledge. Already working with IFPRI, we have developed paired intervention-counterfactual research sites, which are being used to track the efficacy of our SI technologies delivery approaches. This approach is central to the Africa RISING research agenda. The baseline survey that was implemented by IFPRI in the intervention and counterfactual sites provides vital benchmarking statistics upon which evaluation of the project outcomes will be based when the end-line survey is finally implemented.

## Implementation plans and strategies

The project will continue to be guided by the hypothesis that when empirical knowledge on sustainable intensification (SI) is translated into action through participatory action research methods, households are better able to innovate, adapt and adopt technologies. The types of technologies will vary with typology of the households, yet an overall trajectory will prevail for sustainable intensification in crop yield, livestock products and incomes.

We will seek to

- Refine technologies for different agro-ecologies, and test new crop varieties, including the ‘local’ varieties under improvement nutrient management.

- Understand more below-ground biomass inputs for different cropping systems as an indicator of sustainable cropping. Preliminary investigations suggest below ground biomass inputs have a wide range, from as little as 0.2t/ha  to > 3t/ha

- Understand crop-weed interactions as influenced by cropping systems and crop sequences

- Understand the determinants of farmer participation in field-based learning platforms and subsequent influence on their use livestock production intensification technologies? (Adoption hypothesis, H2)

- Understand the food processing and utilization technology options that could be suitable for adoption by the targeted households to improve human nutrition and stimulate increased use SI options? (Innovation sequencing and SI pathways hypothesis, H4)

Specifically, the Malawi project will

- Consolidate R4D platforms in the two districts so as to influence stakeholder practices during 2014-2016. Action plans will be developed and implemented by April 2015

- Deploy technologies that enhance performance of farms, resulting in measurable evidence of increased productivity and proportion of farmers using improved technologies. This will be evaluated through the end line survey, for which survey instruments development and implementation will be done IFPRI

- Inventorize gains in crop productivity due to more efficient use of organic and mineral fertilizer resources by Sept 2016

- Inventorize gains in dairy milk production as a result of access to improved feed resources by Sept 2016

- Train and empower local extension more ably organize farmers for efficient inputs procurement (fertilizers and seed) and post harvest handling and marketing

## Project sites

During Years 4 and 5 (October 2014 through September 2016), we will maintain and consolidate activities within the projects sites in Dedza and Ntcheu, in line with the project research framework on intervention and counterfactual sites, to facilitate project impact evaluation. We have 2 intervention sites in Dedza district: Mposa and Golomoti Sections, located in Linthipe and Golomoti Extension Planning Areas (EPAs), respectively; and also 2 intervention sites in Ntcheu district: Kampanje and Mpamadzi Sections, located in Kandeu and Nsipe EPAs, respectively. Detailed organograms for these sites can be found in the Africa RISING Malawi Year 2 proposal. Maize-based production systems dominate for both Ntcheu and Dedza, which have unimodal rainfall and semi-arid to sub-humid tropical agro-ecological zones. The annual rainfall is 700-1100mm, with distribution occurring from November-April. The majority of farms in these districts are based on hand hoe preparation of land, ranging from 0.5 to 1ha, principally marked by production of crops on raised ridges.

## Participatory action research and adaptive experimentation

We propose to consolidate on our action ‘learning by doing’ research approach in the targeted intervention sites with emphasis on integration at the farm-scale level. Organization of interventions at the action site level remains similar to Year 3 (see Africa RISING Malawi Year 3 proposal). Participatory research and modeling will be systematically linked to enhance farmer decision-making, and evaluate performance of ‘best bet’ SI options for a range of agro-ecologies and farm typologies. With 2000 farmers anticipated to be directly participating in Africa RISING by 2016, the 'mother and baby’ adaptive trials will continue to take centre stage as platforms for knowledge dissemination. Mother trials are fully replicated experiments with several treatments, from which farmers are free to choose those options that more appropriately align with their circumstances to try on their own farms - we refer to these as the baby trials. The approach, therefore, presents a basket of options with no assumption of silver bullets, which have proven to be elusive. Mother trials are hosted by lead farmers while hundreds of other farmers experiment with different technologies in their own fields through baby trials. Using the intervention–counterfactual experimental design initiated in Year 2, we will progressively assess the level of knowledge gains among farmers in both intervention and counterfactual sites, with disaggregation of data by gender and other household characteristics.

## Project thematic areas

In contrast to the previous years, Africa RISING Malawi will be organized along four thematic areas (Table 1), as opposed to work-packages that we have used in the past. The project will be implemented with researchers from different institutions working collectively based on themes, with specific themes implementation leadership based on recognition of relevant institutional expertise.

| Table 1. Africa RISING Malawi themes–based research design for the period October 2014 through September 2016 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Themes | Technology | Scaling up (mature) | Consolidation | Further research | Key activities | Partners |
| - Intensified maize-legume systems | Pigeon/pea-groundnut doubled up | X | X | X | Dissemination (baby trials, participatory modeling, farmer field schools, documentation, DVDs, exchange visits, soil fauna investigations – graduate student training, etc) | MSU, LUANAR, DAES |
|  | Improved varieties of food legumes at high population, crop rotations/sequences | X | X |  | Experimentation and demonstrations (baby trials, exchange visits, etc) | MSU, LUANAR, DAES, CIAT |
|  | Bean studies - Climbing bean/maize/ integration - bush beans |  | X | X | Experimentation (mother and baby trials), documentation | CIAT, MSU |
|  |  |  | X | X | Experimentation (mother and baby trials), documentation | CIAT,MSU |
|  | Fertilization in legume –maize sequences (fertilizer, manure, rotations, intercrops) | X | X |  | Experimentation, weed investigations – effects of systems on weed pressure, | MSU |
| - Livestock intensification | Feed quality for livestock - dairy - goats |  | X | X | Fodder production and utilization -feeding regimes, manure quality and utilization, documentation | ICRAF, LUANAR, DAES |
|  |  |  | X | X | Graduate student research, forage production and utilization -feeding regimes, manure quality and utilization, documentation | LUANAR, DAES |
| - Nutrition and food processing | Value addition | X | X | X | Graduate student work, documentation of recipes, nutrition fares/open days | LUANAR, DAES, MSU, CIAT |
| - R4D platforms | Cross-cutting |  | X |  | Strengthening platforms, workshops, feedback sessions | ALL |

The four themes will broadly address:

- Integrated maize-legume production systems

- Livestock intensification

- Food processing and nutrition outcomes, and

- Research for Development (R4D) platforms and Networking

Theme 1: Integrated maize-legume production systems

This theme constitutes the bulk of our field crops experimentation and contributes to investigating components of the hypotheses H1 and H4:

What are the current biophysical and socio-economic constraints to increased quality, quantity and diversity of crop (cereals and grain legumes) and livestock products (meat and dairy), especially for women farmers? (Integration hypothesis, H1)

How effective are the different technological options under different biophysical and socioeconomic conditions in enhancing food security, nutrition and ecosystem stability? (Integration hypothesis, H1 & Innovation sequencing and SI pathways hypothesis, H4)

Co-evaluation of various technologies ( the doubled-up systems, crop rotations and soil fertility benefits, climbing and bush bean integration technologies that encompass manure utilization, fodder production for dairy feed, etc) will be done with farmers across all the four action sites through mother and baby trials. In line with the Year 3 approach, during Years 4-5, adaptive ‘baby trial' farmers will collectively participate during establishment of the ‘mother’ trials, and each of them would choose a few treatments from the ‘mother’ trials for experimentation in their own fields. We anticipate that the farmers we have engaged over the past two cropping seasons will have baby trials that at least double the area they used previously, using both new and retained legume seed. We will include some new farmers and these two groups will be monitored to evaluate the extent to which contact time with researchers influences the intensity of technology use.

Productivity of different legume types/legume varieties and maize under nutrient management options (fertilization with or without phosphorus, manure, compost, etc) will be evaluated across farms (fertility gradients), and subsequently investigate potential of the technologies to impact on household food security and income if implemented at scale.   During Years 4 and 5, we will invest resources in getting field data from baby trials that we hope will be useful in guiding farm level-level extrapolations and scenario analyses.

Theme 2: Livestock intensification

This theme is linked to the hypothesis:

What are the determinants of farmer participation in field-based learning platforms and subsequent influence on their use livestock production intensification technologies? (Adoption hypothesis, H2)

Malawi livestock statistics indicate a people-to-livestock ratio of 14:1 and 4:1 for cattle and goats, respectively (GoM, 2011). Goats are small in size and they can survive on tree leaves unlike cattle in periods of feed shortage. Goats can also be easily kept under free range, tethered or herded. Under crop-livestock integration, legume crop residues are conserved to strategically supplement goats prior to breeding, in late gestation and early lactation under free range or herding system for local goats in the short term. Goat manure is used in making better quality compost for crop production. Strategic goat supplementation in areas where farmers rear own local goats is a viable and adoptable technology because it offers an opportunity to improve the existing production system without necessarily bringing in other species that may not be compatible with current farming system or agro-ecological conditions.

While Malawi has a very low livestock density, we hypothesize that there exists a niche that can be exploited for enhanced productivity in this sector. To that end, we will test methodologies that can help those farmers that own livestock to be more productive. Complementary elements of the system allows for integrated cultivation of crop and livestock feeds, sequential harvesting and use of crops increasing efficiency of productive land and labor with multiple benefits. Livestock products could be the more direct economic products such as meat and milk, but could also be in the form of manure that can be used to reinforce soil fertility and hence productivity of field crops. Over the past year, ICRAF initiated fodder banks for dairy cows in Linthipe EPA mainly using Leucaena pallid. This work will be expanded to include one more Africa RISING action site during the period 2014-2016

The Animal Science Department at LUANAR is working with a graduate student who is investigating how to intensify production of local goat breeds.  During 2014-2016, we will enhance crop-livestock integration through offering practical and adaptable technologies that add value to the existing practices, including feed formulations based on available fodder and commercial feed concentrates. Considering the small landholdings that farmers have, goats are one of the livestock species that can thrive on limited land and fodder by surviving on tree leaves unlike bigger ruminants which require more feed.

Theme 3: Food processing and nutrition outcomes

Activities linked to this theme will test the hypothesis:

What are the food processing and utilization technology options that could be suitable for adoption by the targeted households to improve human nutrition and stimulate increased use SI options? (Innovation sequencing and SI pathways hypothesis, H4)

This component will be anchored by the department of nutrition at LUANAR. A graduate has already begun investigating nutrition outcomes in the intervention and counterfactual sites. At the action level, the Department of Agricultural Extension Services (DAES) has launched several nutrition campaigns over the past 2 years, and this will be consolidated though production and distribution of pamphlets with simple recipes to thousands of farmers.

Description of work (activities)

- Conduct a nutrition end-line study on food consumption patterns among diverse households. The appropriate questionnaire will have been developed by February 2015

- Collect food samples from households for quantification of nutritive value

- Map food calendars from harvest to the next across diverse households

- Provide training on processing and nutritional value of legumes and dairy products to households, including farmer friendly training and reference materials, capturing a wide range of recipes

- Train at least 200 farmers on appropriate practices on preservation of farm produce (preserve quality, local drying, minimize contamination and losses)

- Conduct community nutrition workshops and open days

Theme 4: Research for Development (R4D) platforms and Networking

Innovation systems play an important role in magnifying research results and providing a pathway for scaling up and impact realization. Promotion of innovation systems fosters effective partnerships for delivery of agricultural services and benefits to farmers. This approach normally hinges on creation and operationalization of innovation platforms (IPs) that identify and characterize prevailing agricultural challenges and jointly develop solutions to address these problems. Thus, this coalition of research and development actors has a shared vision and operational objective, but with each participating actor deriving their desired benefit in the process (win-win scenario). The R4D platforms for each of the two intervention districts will be consolidated around already identified stakeholders that include the District Agriculture Extension Office as the R4D platform convener/chairperson, NGOs operating in the districts (World Vision, Concern Universal, CADECOM), the District Commissioner/Office, extension staff from intervention sites, and lead farmers/innovators. Africa RISING Malawi R4D platforms are operationalized at two levels:

- at the district level, capturing key government and NGO representation, and

- at the Extension Planning Area (EPA) level, principally involving community leaders, local extension and implementing farmers

While structurally already constructed, these platforms will need to be strengthened during the next 2 years, so as to efficiently be conduits for agricultural transformation at different levels. Immediate contribution of the R4D platforms will include

- Enabling stakeholders to do things differently/innovatively  in the intervention districts  through fostering mutual focus without creating new institutional layers of bureaucracy

- Transforming researchers to learners/facilitators rather than remain as ‘experts’

- Use of limited resources (from Africa RISING, from government, from NGOs) more effectively

- Accelerating collective behavioral change, and

- Accelerating project impact realization at scale

## Description of activities within themes

Project coordination – Michigan State University

Specific objective: To coordinate project activities, establish inter-linkages and communication between partners, provide quality assurance of deliverables and report to IITA

Operational objectives: - To ensure achievement of the envisaged project outcomes and results and reporting to IITA within an optimal timeframe - To establish inter-linkages and facilitate information flows among themes, and communication with stakeholders at large - To ensure the integrity of the results emanating from the various work packages

Description of work (activities) - Align with reporting requirements - Ensure inter-linkages, project updates - Organize workshops

Expected results - Project team workshop reports at various stages during the life of the project - Half-yearly project technical and financial reports submitted to IITA - Annual technical and financial project reports submitted to IITA These results directly contribute to the ESA logframe administrative output: ESA project effectively coordinated and managed

Theme I: Integrated maize-legume production systems

Specific objectives - To (re)establish at least 30 adaptive on-farm mother trials comprised of the crop technologies prioritized by communities (also as informed by reflection workshops) - To facilitate farmer adaptive experimentation and co-learning through between 1000-1500 baby trials - Explore crop combinations, sequences and spatial arrangements for efficacy determination - To enhance the productivity and adoptability of climbing bean through improved high yield varieties, management practices and staking options - Estimate actual yield of grain legumes and residual benefits to rotational cereal crops - Evaluate and compare economic benefits of technologies

Description of work (activities) - Multi-location on-farm experiments testing options for sequential use of organic sources and nutrient inputs under different soils, rainfall and land management - Multi-location on-farm adaptive testing of SI technology options prioritized and designed with communities to restore degraded soils/lands - soil fertility management technologies to be reflective of farmer resource endowments and capabilities - implementation of appropriate crop sequences to harness ecological benefits of preceding legume crops in rotation - Participatory evaluation of technologies through field days and farmer workshops - Determine the land allocation/crop patterns at field scale as a result of Africa RISING initiatives - Economic analysis of the technologies

Expected results - At least four preliminary best-fit SI technologies for different agro-ecologies and socio-economic conditions identified - At least 2000 women and men farmers, and youths, directly participating in project initiatives and at least double this number participate indirectly by 2016 - Scientific evidence on the place of SI under farming systems constrained by inherent poor soil fertility and limited levels of inputs by farmers generated - marketed-oriented grain legumes production potential for farmers in different typologies determined - Improved knowledge of farmer assessment of technologies and the adoption process - Profitability assessed of SI technologies These results directly contribute to ESA logframe Output 5: Innovations that increase resilience and productivity of farming systems deployed and ESA logframe Output 7: Innovations that increase availability and consumption of safe and nutritious food products deployed

Theme II: Livestock intensification

Objectives: - To demonstrate the yield potential of selected tree fodder species under smallholder management systems - To demonstrate the profitability of the smallholder dairy system and goat production based on leaf biomass leaf meal. - To investigate the potential for enhanced goat production using simple feeding regimes and disease control techniques - To evaluate and compare economic benefits of technologies

Description of work (activities) - Identify and select farmers, capacitate and support them to establish fodder banks for feeding livestock (goats and dairy cows) - Collect and analyze data (number of trees, area of stands, leaf biomass yield) for farmers involved in tree leaf fodder production for own use or for sale. - Assess the potential market opportunities for leaf fodder - Train farmers on farm-based feed preservation, feed formulation and utilization - Collect milk yield data of cows fed with different feeds (commercial feeds, farmer local feeds, leaf fodder) and conduct an economic analysis of the profitability of the different feeding strategies used by farmers - Economic analysis of the technologies

Expected results - Productivity of different fodder trees species and seed sources under smallholder farming systems determined and suitable/preferred species and seed sources recommended - Local market potential of leaf fodder determined - Profitability of smallholder dairy based on leaf fodder, commercial feeds and local farmer practices determined - Increased market participation by farmers in goats and dairy products These results directly contribute to ESA logframe Output 5: Innovations that increase resilience and productivity of farming systems deployed

Theme III: Food processing and nutrition outcomes

Specific objective: - To evaluate efficacy of different local food processing approaches and nutrition provision through various food crops (micronutrients, calories, proteins)

Description of work (activities) - Conduct a nutrition studies on food consumption patterns among diverse households - Collect food samples from households for quantification of nutritive value - Map food calendars from harvest to the next across diverse households - Provide training on processing and nutritional value of legumes and dairy products to households, including farmer friendly training and reference materials, capturing a wide range of recipes - Train farmers on appropriate practices on preservation of farm produce (preserve quality, local drying, minimize contamination and losses) - Conduct at least one community nutrition workshops and open days in each of the 4 intervention sites

Expected results/outputs - At least one training and reference material developed - At least 100 trainers/lead farmers trained in nutrition and processing of grain legume food products - Food calendar, budgets and recipes for households in intervention sites documented and alternatives developed These results directly contribute to ESA logframe Output 7: Innovations that increase availability and consumption of safe and nutritious food products deployed

Theme IV: Research for Development (R4D) Platforms and Networking

Specific objectives: - To consolidate R4D platforms for Dedza and Ntcheu districts at both district and action site level - To enhance knowledge and skills of smallholder farmers and partners for decision making in SI across diverse farming systems

Description of work (activities) - Hold quarterly R4D platforms meetings for each of the districts - Promote dissemination of targeted SI technologies through training and capacity development of partners - Develop appropriate extension/dissemination materials for use by stakeholders (extension agencies, lead farmers) - Conduct participatory action research workshops (co-learning processes and space for feedback) - Document and share best-fit technologies/approaches in agro-ecologies, including adoption and adaptation strategies - Link Africa RISING with other USAID-funded programs (e.g. INVC) and other initiatives (e.g. N2Africa) with similar goals

Expected results - Functional R4D platforms - Technical extension material developed and disseminated through partner networks These results directly contribute to ESA logframe Output 4: R4D and Innovation platforms influencing stakeholder practices established

Expected results/deliverables, quantifiable and to include short term, long term

- Knowledge of processes associated with rehabilitating soil through sustainable
intensification technologies enhanced (2014-2015)

- Soil fertility improving technologies appropriate to diverse farming households developed (2014-2015)

- Diets of households significantly improved with increased prominence of protein -rich products based on intensified grain legume production (soyabean, common bean, groundnut) (2014-2016)

- The role and decision making capacity of women in technology development, evaluation and application increased (2014-2016)

Others deliverables to include short and long term

- Household food utilization and  consumption patterns before and after nutrition interventions established (2016)

- Graduate students from LUANAR and MSU gain valuable insights into farming systems functioning through on-farm research training (2014-2016)

- Presentations on Africa RISING experience made at various international and regional conferences (2014-2016)

## Expected outcomes - short, long term

- Sustainable intensification technologies being used more widely by farmers in the intervention sites, including those that did not directly host trials (2016)

- Extension personnel delivering coherent and scientifically sound extension messages, and equipped to train their peers (2016)

- Farmers increasingly becoming food self sufficient, and participating more meaningfully in input and output markets (2016)

## Literature references

- Bezner Kerr R, Berti PR, Shumba L. 2010. Effects of a participatory agriculture and nutrition education project on child growth in Northern Malawi. Public Health Nutrition

- Chikowo R, Zingore S, Snapp, S., Johnston A, 2014. Farm typologies, soil fertility variability and nutrient management in smallholder farming in Sub-Saharan Africa. Nutr Cycl Agroecosyst:1–18.

- Government of Malawi 2011. Malawi Agricultural Sector Wide Approach: A prioritized and Harmonized Agricultural Development Agenda 2011-2015, Lilongwe Malawi.

- Rowhani P, Lobell DB, Linderman M, Ramankutty N. 2011. Climate variability and crop production in Tanzania. Agricultural and Forest Meteorology 151: 449-460.

- Saito KA, Mekonnen H, Spurling D. 1994. Raising the productivity of women farmers in sub-saharan Africa. World Bank Discussion Paper # 230. World Bank. Washington, D.C. 110 pp.

- Snapp SS, Blackie MJ, Donovan C. 2003. Realigning research and extension services: experiences from southern Africa. Food Policy 28:349-363

- Snapp SS, Kanyama-Phiri G, Kamanga B, Gilbert R, Wellard K. 2002. Farmer and researcher partnerships in Malawi: developing soil fertility technologies for the near-term and far-term. Experimental Agriculture 38:411-431.

- Stoorvogel JJ, Smaling EMA, Jansen BH. 1993. Calculating soil nutrient balances in Africa at different scales. I. Supra-national scale. Fertilizer Research 35:227–235

- Tenge AJ, De Graaff J, Hella JP. 2004. Social and economic factors for adoption of soil and water conservation in west Usambara Highlands, Tanzania. Land Degradation and Development 15:99–114

## Global project activity schedule

| ## Activity | ## Oct 2014 | ## Nov-Dec 2014 | ## Jan -Feb 2015 | ## Mar - May 2015 | ## Jun-Aug 2015 | ## Sept –Oct 2015 | ## Nov-Dec 2015 | ## Jan -Feb 2016 | ## Mar - May 2016 | ## Jun-Jul 2016 | ## Aug-Sep 2016 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ## Consolidation of action sites (including selection of new farmers), nursery establishment for fodder, procurement of inputs, etc |  |  |  |  |  |  |  |  |  |  |  |
| ## Organize participatory training workshops, distribute seed and other inputs, |  |  |  |  |  |  |  |  |  |  |  |
| ## Establish adaptive trials (field crops, tree fodder bank experiments) |  |  |  |  |  |  |  |  |  |  |  |
| ## Conduct targeted nutrition surveys/studies |  |  |  |  |  |  |  |  |  |  |  |
| ## Field trials evaluations, field days, harvesting, nutrition workshops |  |  |  |  |  |  |  |  |  |  |  |
| ## Organize nutrition workshops, livestock, etc. |  |  |  |  |  |  |  |  |  |  |  |
| ## Feedback workshops/write-shops, data analysis |  |  |  |  |  |  |  |  |  |  |  |
| ## Annual report writing/planning meetings |  |  |  |  |  |  |  |  |  |  |  |
| ## Final workshops |  |  |  |  |  |  |  |  |  |  |  |

# USAID Indicator targets

| Indicator title | Target 2013/14 | 2012/13 achievements | 2013/14 achievements | Projection for 2014/15 | Projection for 2015/16 |
| --- | --- | --- | --- | --- | --- |
| Number of farmers and others who have applied new technologies or management practices as a result of USG assistance | 320 | 451 | 1386 | 1600 | 2000 |
| Number of hectares under improved technologies or management practices as a result of USG assistance | Not set target | 180 ha | 414 ha | 500 ha | 600 ha |
| Number of individuals who have received USG supported short-term agricultural sector productivity or food security training | No set target | 38 extension, 167 women farmers trained in value addition and nutrition | 820 | 900 | 1000 |
| Number of new technologies or management practices in one of the following phases of development: …in Phase II: under field testing as a result of USG assistance |  | 4 crop SI technologies | 2 SI crop-based technologies 2 SI livestock technologies | 1 | 1 |
| 4.5.2(42): (4.5.2-28) Number of private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) that applied new technologies or management practices as a result of USG assistance (RIA) (WOG) |  |  | 3 | 3 | 2 |

# Consolidated budget 2014/2015

| Item | LUANAR (Agronomy WP) | LUANAR (Nutrition Dept) | LUANAR (Livestock Dept) | DAES (Dedza and Ntcheu _R4D) | CIAT (Beans WP) | ICRAF (Livestock WP) | IITA (hosting funds) | MSU | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Personnel | 4,800 | 4,800 | 4,800 | 3,400 | 19,325 | 29,740 | 0 | 90,000 | $ 156,865 |
| Equipment | 0 | 1,000 | 0 | 2,000 | 0 | 0 | 0 | 3,600 | $ 6,600 |
| Research | 6,000 | 8,000 | 7,900 | 0 | 18,000 | 18,300 | 0 | 62,000 | $ 120,200 |
| Travel | 2,000 | 2,000 | 2,000 | 3,000 | 6,000 | 6,200 | 0 | 22,511 | $ 43,711 |
| Workshops | 1,700 | 1,500 | 1,500 | 5,000 | 2,000 | 2,000 | 0 | 15,000 | $ 28,700 |
| Supplies/Other | 5,500 | 2,700 | 3,800 | 1,600 | 14,675 | 13,760 | 14,000 | 18,000 | $ 74,035 |
| Subtotal |  |  |  |  |  |  |  | 211,111 | $ 211,111 |
| Overhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54,889 | $ 54,889 |
| Total | 20,000 | 20,000 | 20,000 | 15,000 | 60,000 | 70,000 | 14,000 | 266,000 | $ 485,000 |

| ## Budgets notes: LUANAR Agronomy |  |  |
| --- | --- | --- |
| Item | Budget allocation (US$) | Key budget notes |
| Personnel | 4,800 | Graduate student stipend at $400 per month |
| Equipment | 0 |  |
| Research | 6,000 | Field expenses, laboratory expenses |
| Travel | 2,000 | Various trips to and from sites |
| Workshop | 1,700 | Various on-farm workshops with farmers |
| Supplies/Other | 3,680 | Chemicals, experimental inputs (seeds, fertilizers, sampling material, etc) |
| Subtotal | 18,180 |  |
| Overhead | 1,820 | 10% of non-equipment expenses |
| Total | 20,000 |  |

| ## Budgets notes: LUANAR Livestock Department |  |  |
| --- | --- | --- |
| Item | Budget allocation (US$) | Key budget notes |
| Personnel | 4,800 | Graduate students stipend at $400 per month |
| Equipment | 0 |  |
| Research | 7,900 | Field expenses, laboratory expenses |
| Travel | 2,000 | Various trips to and from sites |
| Workshop | 1,500 | Various on-farm workshops with farmers |
| Supplies/Other | 1,980 | Chemicals, field supplies, surveys |
| Sub-total | 18,180 |  |
| Overhead | 1,820 | 10% of non-equipment expenses |
| Total | 20,000 |  |

| ## Budgets notes: LUANAR Nutrition Department |  |  |
| --- | --- | --- |
| Item | Budget allocation (US$) | Key budget notes |
| Personnel | 4,800 | Graduate student stipend at $400 per month |
| Equipment | 1,000 | Laptop |
| Research | 7,000 | Field expenses, laboratory expenses |
| Travel | 2,000 | Various trips to and from sites |
| Workshop | 1,500 | Various on-farm workshops with farmers |
| Supplies/Other | 1,880 | Chemicals, experimental inputs (seeds, fertilizers, sampling material, etc) |
| Sub-total | 18,180 |  |
| Overhead | 1,820 | 10% of non-equipment expenses |
| Total | 20,000 |  |

| ## Budgets notes: CIAT |  |  |
| --- | --- | --- |
| Item | Budget allocation (US$) | Key budget notes |
| Personnel | 19,325 | 100% research assistant, 10% scientist salary |
| Equipment | 0 |  |
| Research | 18,000 | Field expenses, laboratory expenses |
| Travel | 6,000 | Various trips to and from sites |
| Workshop | 2,000 | Various on-farm workshops with farmers |
| Supplies/Other | 5,962 | Chemicals, experimental inputs (seeds, fertilizers, sampling material, etc) |
| Subtotal | 51,283 |  |
| Overhead | 8,713 | At rate of 17% |
| Total | 60,000 |  |

| ## Budgets notes: ICRAF |  |  |
| --- | --- | --- |
| Item | Budget allocation (US$) | Key budget notes |
| Personnel | 29,740 | 80% research assistant, 30% PMMT officer, 10% scientist salary, |
| Equipment | 0 |  |
| Research | 18,300 | Field expenses, laboratory expenses |
| Travel | 6,200 | Various trips to and from sites |
| Workshop | 2,000 | Various on-farm workshops with farmers |
| Supplies/Other | 4,589 | Chemicals, experimental inputs (seeds, fertilizers, sampling material, etc) |
| Sub-total | 59,829 |  |
| Overhead | 10,171 | 16% of budget |
| Total | 70,000 |  |

| ## Budgets notes: MSU |  |  |
| --- | --- | --- |
| Item | Budget allocation (US$) | Key budget notes |
| Personnel | 90,000 | Summer salary for Prof. Snapp, Postdoc Research Associate (50%), Technical Assistant (100%), 2 graduate students |
| Equipment | 3,600 | 2 laptops for graduate students, 1 for Research Assistant |
| Research | 62,000 | Field expenses, laboratory expenses, R4D platforms |
| Travel | 22,511 | Various trips to and from sites, trips MSU-Malawi |
| Workshop | 15,000 | Training workshops with extension, R4D platforms |
| Supplies/Other | 18,000 | Chemicals, experimental inputs (seeds, fertilizers, lab analytical material, etc) |
| Subtotal | 211,111 |  |
| Overhead | 54,889 | 26% of non-equipment expenses |
| Total | 266,000 |  |