Minutes of Africa RISING meeting during lunch time on 27/02/2015

Agenda:

- Contracts with NGOs

- Construction of wells in the technology parks

Participants: Albert Rouamba, Clarisse Umutoni, Mary Ollenburger, Joachim Binam, Birhanu Zemadim and Catherine Dembele

Rapporteur: Catherine Dembele

- Contracts with NGOs

Circumstances: During the presentation, MOBIOM has complained to have signed contract with only ICRISAT but supported ICRAF and AVRDC in their work. They have suggested to get contract with these two institutes (ICRAF and AVRDC) as well. Discussion is needed to come up with an appropriate solution.

Resolution: After discussion, it was decided to get only 1 contract including concerns of all the 3 institutes (AVRDC, ICRAF and ICRISAT) which are interacting with MOBIOM for the implementation of their activities. As ICRISAT is handling the funds, it was suggested that it signs such contract. However, it was mentioned that ICRISAT cannot make a contract with MOBIOM for more than $20,000 because MOBIOM does not have a 3 year account audit. Mary will send the 2014 contract signed with ICRISAT to be amended by AVRDC and ICRAF before determining the amount to grant MOBIOM which might be less than &20,000.

- Construction of wells in the technology parks

Circumstances:  Marc has mentioned in his presentation about the development of 2 technology parks (Mpessoba and Flola), that contract has been signed with an operator who has started basic infrastructure construction including fence, shallow wells etc. However according to AVRDC and ICRAF shallow wells do not meet the requirement for water needed for vegetable production during dry season as defined in their workplans.

Resolution: Boreholes supplied with manual pump are found more suitable for the technology parks. They might be also used for dry season production of improved annual crop seeds. All participants have agreed with the idea and are favorable to share the cost of the infrastructure. Therefore, AVRDC and ICRAF were mandated to define technical specification for the borehole supplies with manual pump and estimate the cost for both sites, Flola and Mpessoba and then share with other members the soonest (within 1 week).