## Slide 1
Monitoring, Evaluation, and Data Management in ESA
Daniel Mgalla, Beliyou Haile, Carlo Azzarri
IITA-IFPRI
Africa RISING ESA Planning and Review Meeting (online)
September 29, 2020

## Slide 2
    Outline
    Key 2020 activities
      AR direct and scaling beneficiary data
      AR scaling partnerships (and additional details)
      Online AR data management
      FtF data
    Planned M&E activities
    Ongoing/planned research and program-wide synthesis

## Slide 3
    Direct beneficiaries
    Data harmonization and documentation using the Beneficiary and Technology Tracking Tool (BTTT):
    Malawi: completed!
    Tanzania: in progress
    Zambia: just started (names of beneficiaries with technology submitted)
    Next Step:
        Researchers to continue submitting names/information of direct beneficiaries along with technologies applied (8 PIs submitted the names with technologies; 2 pending in Tanzania)
        Researchers to submit missing information for some villages (e.g., Dr. Swai for Njoro,…)

## Slide 4
    # of direct beneficiaries reached as of Sept 2020 (against 2020 cumulative targets)
Chart: 
| Tanzania | Malawi | Zambia | Total
Target | 2073 | 3986 | 2200 | 8259
Achieved | 2526 | 4340 | 1028 | 7894
% Achieved | 1.2185 | 1.0888 | 0.46727 | 0.95581

## Slide 5
    Scaling beneficiaries
Strong development partners participation (IoP, Lead foundation, AR NAFAKA, TLC, SANE, ZARI)
61% scaling beneficiaries reached so far against 2020 cumulative targets
Clear documentation needed on scaling to support scaling efforts (focusing on scaling approaches, achievements, success stories, lessons learned and challenges)

## Slide 6
    # of scaling beneficiaries reached as of Sept 2020 (against 2016-20 cumulative targets)

## Slide 7
    Direct & Scaling beneficiaries Targets 2020-21
Impact targets | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Households participating directly in AR research | 2,965 | 5,063 | 6,014 | 6,603 | 7,338 | 8,259 | 9,410
Tanzania | 1,659 | 1,710 | 1,773 | 1,852 | 1,950 | 2,073 | 2,228
Malawi | 1,306 | 1,633 | 2,041 | 2,551 | 3,188 | 3,986 | 4,982
Zambia |  | 1,720 | 2,200 | 2,200 | 2,200 | 2,200 | 2,200
Households participating in AR development partner activities | 4,011 | 58,411 | 169,201 | 203,342 | 242,851 | 275,197 | 298,038
Tanzania | 2705 | 16,070 | 82,800 | 91,080 | 100,188 | 110,207 | 121,227
Malawi | 1306 | 12,796 | 39,645 | 65,506 | 95,907 | 118,234 | 130,055
Zambia |  | 29,545 | 46,756 | 46,756 | 46,756 | 46,756 | 46,756
Total households in FTF zones of influence | 2,192 million | 2,656 million | 2,740 million | 2,823 million | 2,906 million | 2,988 million | 3,072 million
Tanzania | 1,004 million | 1,037 million | 1,070 million | 1,102 million | 1,135 million | 1,167 million | 1,200 million
Malawi | 1,188 million | 1,226 million | 1,265 million | 1,303 million | 1,341 million | 1,379 million | 1,417 million
Zambia |  | 392,893 | 405,229 | 417,566 | 429,903 | 442,240 | 454,577

## Slide 8
    Status of Technology Scaling & Partnerships
Are several development partners inactive (NAFAKA, IOP, SANE, others)?
Are we on track to achieving our scaling targets? How feasible is to bring in more development partners? And to increase engagement with local and regional government bodies?
What specific/additional scaling strategies can be introduced to increase outreach?
Status of partnerships

## Slide 9
    Technology Scaling & Partnerships: Malawi
2020: 118,234 targets versus 78,036 -> why?
2021: how feasible is it to reach 130,055?
New partnerships possible? Which ones, what methods?

## Slide 10
    Technology Scaling & Partnerships: Tanzania
2020: 110,287 targets versus 68,426 -> why?
2021: how feasible is it to reach 121,227?
New partnerships possible? Which ones, what methods?

## Slide 11
    Technology Scaling & Partnerships: Zambia
2020: 46,756 targets versus 20,741 -> why?
2021: how feasible is it to reach 46,756?
New partnerships possible? Which ones, what methods?

## Slide 12
    Technology Scaling & Partnerships: general
1. Which of these partners are collecting data about beneficiaries of AR validated technologies?
2. What kind of data are they collecting? Using which tool? Are the data they are collecting enough for our reporting (using our scaling tool)?
3. For partners who are not collecting scaling beneficiary data, what would it take (human and $$) to collect minimum scaling data using our scaling tool?

## Slide 13
Online AR data management using Dataverse: 2020 data submission

## Slide 14
# of datasets uploaded on Dataverse (as of Sept 2020)

## Slide 15
    FtF data: key items
Some researchers submitted data without providing narratives for 10% difference nor filling IM performance narrative sessions
Missing targets for some researchers (only six researchers set targets from 2019 to 2021)
Six researchers have submitted FtF data so far
Submit by Oct 10:
1. FY2020 indicator results (i.e., actuals)
2. FY2021-22-23 targets (if applicable), and FTF-related performance narratives
Daniel will be working with you in the next couple of weeks to compile the data for timely submission to USAID

## Slide 16
    FtF data: to be incorporated into workplans
    Deliverables against targets for FtF indicators( )
    Deliverables against project-level output level indicators
    Required: targets for researchers who did not submit!

## Slide 17
  Finalize BTTT data harmonization for all countries
  Monitoring different types of AR beneficiaries (old, new and dropped out), also through collection of basic information through Lead Farmers
  Support researchers in FtF & other indicators data collection
  Monitoring of scaling up partnerships, activities, and beneficiaries
  Collaborate with communication team to create various knowledge products
Planned M&E activities

## Slide 18
Ongoing/planned studies and program-wide synthesis/1
Malawi follow-up data collected in 2019, data cleaned. Panel analysis of program impact including on longer term economic indicators such as poverty and food security has just started
Tanzania follow-up planned for 2021, baseline survey conducted in 2014 covering about 800 households from Babati, Kongwa, and Kiteto
    Potential to sample additional/new households who joined the program since baseline (based on updated beneficiary data in the BTTT)

## Slide 19
Ongoing/planned studies and program-wide synthesis/2
Assessment of the adoption and the impact of AR technologies among scaling beneficiaries as part of NAFAKA (with Haroon et al.)
    Contributed questions to NAFAKA’s annual survey on technology adoption, NRM, and post harvest management practice
    Collaborate on the analysis and write-up of data to be collected
  Assessment of welfare impacts of participation in multiple output markets (with Julius)
    Contributed to a survey tool to gather data on participant's knowledge about AR technologies

## Slide 20
Cross-country study on scaling (approaches, achievements, etc.) for a knowledge/legacy product (with help from Jonathan).
What is needed?
  Case 1. A scaling partner already has a database of scaling beneficiaries (e.g., NAFAKA) → AR to formally request NAFAKA access to its scaling database and pull out necessary information for AR reporting
  Case 2. A scaling partner does not have a database of scaling beneficiaries (e.g. IoP?) → M&E team to work with AR researchers to figure out how and what it takes to gather minimum data on scaling beneficiaries using AR scaling tool
We will work with PIs/researchers to compile info about which partner has what scaling-related info
Ongoing/planned studies and program-wide syntheses/3

## Slide 21
E.g., plan under way with Scaling of Terrace Technologies by Lead Foundation in Dodoma
  The objective is to assess the extent of scaling, strategies impact of these technologies on welfare of smallholder farmers in Dodoma districts
  What is needed? Access to farmers’ info in the selected location (collaboration with Dr. Swai)
Similar study is needed in Malawi through DAECC and Zambia to produce legacy products
  Regis/Christian: how/what can we collaborate on this effort?
Ongoing/planned studies and program-wide syntheses/4

## Slide 22
Program wide synthesis:
  Study #1: Linkages between agricultural market integration, agricultural production, livelihoods, poverty, and food security
  Study #2: Analysis of linkages between on-farm production and dietary diversity
Case study completed for Ghana (guinea-pig)
Work to be expanded to other AR countries including in ESA
Ongoing/planned studies and program-wide syntheses/5

## Slide 23
Example of program-wide synthesis:
Agricultural INPUT market integration and economic outcomes in Ghana
Higher cereal yield and economic outcomes with higher level of integration into INPUT markets (seeds, pesticides, fertilizers, labor, etc.)

## Slide 24
Example of program-wide syntheses:
Agricultural OUTPUT market integration and economic outcomes in Ghana
Better agricultural and economic outcomes among households that are integrated into OUTPUT markets (i.e., have higher marketable surplus)

## Slide 25
Example of program-wide syntheses:
On-farm production diversity and dietary diversity in Ghana
Higher on-farm production diversity associated with more diverse household diets
The lower the access to markets, the stronger the association between production and dietary diversity

## Slide 26: Acknowledgements
Notes: ESA Africa

## Slide 27
Thank You