MINUTES SECOND (SKYPE) MEETING:  04.03.2014

Time: 11.12 – 11.55

Participants:

1. M. Bekunda 	Project Chief Scientist / Chair

2. P. Hillbur 		PI- WP9

3. E. Koyano 		Collaborator - WP 4

4. G. Sikumba 	Co PI -WP 3

5. A. Charles 		Co PI -IFPRI

6. T. Stoilova 		Co PI -WP6

7. J. Kihara 		PI - WP1

8. F.S. Ngulu – Facilitator and secretary

Absent with Apologies

S.D. Lyimo – Co PI -WP1

Agenda

1. Communication from the Chair

2. Work package progress update

3. USAID mission itinerary

Communication from the Chair

The USAID Mission is visiting Africa RISING sites in Babati district from 17th – 18th March

2014. It comprises of 2 delegates from USAID Washington, 3 from USAID Dares Salaam, IITA

Deputy Director and Africa RISING Project Coordinator.

The purpose of the meeting is to have latest updates on each work package; as a basis

for drawing up an itinerary for the USAID mission visit

Work package updates:

WP9. Hillbur:  At present, the work package doses not have activities on the ground. The PI is developing a poster on R4D plat form. He may not manage to come to Babati but will send the poster a few days before arrival of   the delegation.

Comment: 	Identify someone who can explain the poster on your behalf.

WP1: Kihara: He was working on the one- page summary that captures progress of the work package. He indicated there were suitable sites in Matufa and Seloto. Further information will be provided by Mr. S.D.Lyimo who was out in Babati, visiting the trial sites. .

Comment:

- Link up with F. Kizito (WP7) to explore the possibility of demonstrating instruments for measuring farm-scale and landscape level water and nutrient flows.

- All PIs urged to submit summaries and protocols by Friday 7th March, 2014

- In mid February, the project offered small quantities of climbing bean seed to 50 farmers in Long village using the coupon seed system. The plan is to plant this set as a relay crop in fields which were under common bean/round potations. The secretary will make follow up with the local extension agent to establish progress and decide whether or not to include this component in the itinerary

WP 2:	Not represented but the meeting emphasized the need to follow up with Jumbo to identify potential MLNV sites

WP3: Sikumba: Completed planting the forage demonstration sites in Long, Seloto and Sabilo in the first week of February. Seloto trial site is the most probable suitable site. It was planted much earlier than the rest. The second site is in Long village (Lucia Kamara’s farm)

WP4: E.Koyano: There are ongoing studies in Long, Seloto and Sabilo villages. Long site is the most suitable. The work package was also developing 2 posters; one on integration and the other one on mycotoxin. The posters shall be displayed in the village storage premises.

WP5: Not represented but Koyano hinted they have integrated activities in Long and Sabilo

WP6: Stoilova: The team had already identified demonstration sites in Seloto and Matufa and sowed the trials on 27-28 February.. The demonstrations are focused on improved management practices of three crops: Tomato (Tengeru 2010), Amaranth (Madira 1 & 2) and African eggplant.

Deployment of healthy tomato seedlings is a fundamental management practice for profitable tomato production. This work package will produce healthy seedlings at AVRDC-Eastern and Southern Africa office and distribute them to collaborating farmers in the two villages. The WP integrates with WP8. It has already offered Madira 2 seed to raise amaranth for feeding poultry. It intends to promote poultry manure to boost vegetables productivity.

WP7: Kizito. Not present. Ref. comment under WP1

WP8: Not present

Itinerary USAID Team field trip: Prof. Mateete, S.D.Lyimo, L.Yangole and the Secretary shall visit the proposed sites on 10 -12 March 2014, to ratify their suitability and thereafter prepare the final field trip schedule