Minutes of discussion on Africa RISING External Review Report

Date 		08/01/2015

Location	ICRISAT, Samanko, New Conference Hall

Starting Time	9AM

Participant list:

| Name | Institution | E-mail |
| --- | --- | --- |
| Albert Rouamba | AVRDC | Albert.rouamba@worldveg.org |
| Asamoah Larbi | IITA/Ghana | a.larbi@cgiar.org |
| Birhanu Zemadim | ICRISAT | b.birhanu@cgiar.org |
| Caroline Makambo Sogbui | AVRDC | Caroline.sobgui@worldveg.org |
| Catherine Dembélé | ICRAF | c.dembele@cgiar.org |
| Eva Weltzien | ICRISAT | e.weltien@cgiar.org |
| Irmgard Hoeschle-Zeledon | IITA/Nigeria | I.zeledon@cigiar.org |
| John Nzungize | ICRISAT | j.nzungize@cgiar.org |
| Mary Ollenburger | WUR/ICRISAT | mollenburger@gmail.org |
| Ousmane Sanogo | IER/Sikasso | Sanogo_ousmanem@yahoo.fr |
| Ramadjita Tabo | ICRISAT | r.tabo@cgiar.org |
| Tignegre Jean Baptiste Yvette Dossa | AVRDC AVRDC | Jean-baptiste.tignegre@worldveg.org Yvette.dossa@worldveg.org |

Africa RISING Project Coordinator, Dr. Irmgard Hoeschle-Zeledon, gave a brief presentation about the Africa RISING West Africa external review commissioned by IITA from October 06 to 12, 2014 in Mali. The reviewers’ comments were then distributed to all partners to help in revising the workplan for the remaining two years of the program (2015 and 2016). In addition, a summary of the external reviewers’ comments that required action by the implementing partners in Mali were presented.   The main topics highlighted included: management, resources, Implementation, partnership, monitoring and data Management. These issues were discussed in great depth as presented below.

The issue of funds transfer and the challenges with the disbursement has two components; delays in getting contracts signed, and the justification of the advance taken. Delays in signing of contracts were largely due to delays in compiling the West Africa work plan as few institutes submitted their work plans in time. ICRISAT had received a commitment letter from IITA to witness receiving US$ 700,000 every year, however, ICRISAT’s financial system doesn’t allow pre-financing of activities, as budgets are committed to projects and CRP programs. It was therefore agreed that IITA will look for options to send advance money to ICRISAT (nearly US$400,000) ahead of the signing of the official agreement, which will take place after the regional planning meeting scheduled from 24 to 26 March 2015 in Accra, Ghana. It was suggested that ICRISAT Finance Office need to work closely with partners to get correct financial statements as early as possible without waiting for the prescribed deadline in the agreement letters with partners.

In line with this and to ensure quick start of activities before the rainy season, streamlining the approval of work plans and budgets was another point of discussion. It was admitted that the work plans for both Mali and Ghana, are big and require enough time to get approval by the steering committee. Some members of the steering committee came-up with detailed comments that need to be addressed by implementing partners. This creates further delays in contractual arrangements thereby adding extra delays in addition to delays occasioned by partners failing to submit their work plans in time, a case example for Ghana was given. Partners were advised to submit their workplan in-time to avoid delays in compiling and submission to the steering committee for approval. Once the compiled workplan is submitted to the steering committee the project coordinator facilitate the approval process.

There is a strong interest by the program to have site coordinators to smooth the implementation of activities in different locations and avoid silos approach. ICRISAT advertised two positions at a scientific officer level for coordination of the two planned research hubs in Koutiala and Bougouni. The Terms of Reference (ToR) had been shared with the project Chief Scientist before advertising the positions. It is anticipated that partners of the program in Mali will be invited to evaluate applications from potential candidates and be in the selection panel. Partners were requested to help in disseminating the advert widely. The two incumbents will liaise with partner institutes in the implementation of trials and other field research activities. In line with this the location of two technology parks (one in Bougouni and one in Koutiala) were identified and currently discussions are going on regarding acquisition of the land from the villages. The chief scientist stressed the importance of the technology parks as learning sites for research and dissemination of developed technologies to the local communities, mother trials are established in the parks and communities choose to implement baby trials in their farmland. In addition Dr. Zeledon noted that not all activities can be included in technology parks (e.g. most livestock trials, many nutrition activities). But the technology parks should become the core of the Africa RISING research program in West Africa.

There is a need to synergize widely with other USAID development programs near the Africa RISING program implementation villages. One example is the work of FARMSEM. However not much detail information is currently available and Dr. Eva was asked to share the project document and the progress so far, and identify and elaborate how the achievements in FARMSEM project would be beneficial for the remaining two years of the program. The project coordinator, Dr. Irmgard suggested the next two final year project reports should include at least a paragraph how FARMSEM and Africa RISING projects create synergies.

Dr. Asamoah Larbi stressed in the remaining two years of the program any work on situation analyses can’t be tolerated. These have been done by multiple partners and IFPRI at large. Now we need to look into options how to draw important global information from the already existing reports and data. One option is hiring an international consultant for the job and Dr. Irmgard was willing to take the issue forward and take action on the same. The consultant is expected to work with partners and come-up with Mali situation analysis booklet. It is known that IFPRI has been leading the work on situation analysis and conducted detailed surveys both in Ghana and Mali. However The job of the consultant is to come up with a synthesis report of all the surveys that have been done in Mali by ICRISAT, AVRDC, ILRI and local NGOs working for the project. Partner institutes were advised to make available existing reports and any form of data collected so far.

Cost benefit analyses of sustainable intensification options were not done to the greater level and ICRISAT advertised a position to hire a Socio-economist partly funded by Africa RISING program to work on the already collected information and further in the remaining two years. The interview was scheduled on January 15, 2015 and the successful candidate is expected to work on monitoring and evaluation as well. Africa RISING program also hired economist based in Tamale in charge of West Africa and East and Southern Africa. He will work closely with the new ICRISAT economist to have consistency across countries.  Also because the economist in Tamale doesn’t speak French there is a lot to do and  in particular the additional work force is welcomed.

Project partners were advised to use the project data management tool (PMMT) as it becomes mandatory for future fund releases. There is a concern of lack of efficient training program on the use of the tool. Dr. Irmgard promised to discuss with IFPRI for possibility of conducting the PMMT training for partners in Mali.

It is important to have exchange visits by members of the project, and three levels of visits were suggested; between Mali and Ghana, between West Africa and Ethiopia, and between West Africa and Tanzania. While the exchange visits are important and helpful in learning region-wide program implementation, the time availability was an issue. However the visit to Ghana by Malian participants was considered important and is planned for September 2015. In addition, a visit for selected scientists from across Africa RISING to Ethiopia to see the Ethiopian  initiatives on landscape and watershed management was welcomed, this would be facilitated by Dr. Irmgard.

Other suggestions made by participants after rigorous discussion were the following:

- Reporting need not be too wordy and should include quantitative analysis.

- Resource persons need to be identified by ICRISAT to train local partners on financial reporting

- Some partners get lots of money, but the value of money was not reflected on the ground, or it was not reported. This should be planned properly during the preparation of the workplan.

- Need to have a regular communication among partners (at least once in two months physically, and every month using available technologies, like e-mail, phone, Skype etc…). The minutes of meetings need to be circulated widely to all contributing partners and individuals who are unable to attend meetings because of other commitments.

- Ensure site coordinators are qualified and able to work with local communities and partner institutes.

- In allocating resources identify people who can play key role and release others with minor contribution to be effective in other projects.

- Need to have cross team meetings; site coordinators would facilitate meetings in the project areas with partners and local communities.

- Facilitate handling and analysis of data through regular organization of statistical training workshops.

- Innovation Platforms (IPs) were established in Bougouni and Koutiala and launching events were held on 10th and 12th December, 2014. Ensure the IP meetings prioritize demand driven activities of Africa RISING program.

- Partners should coordinate their field visits and try to go together to the field so to know what everybody is doing. This also reduces the time requested from farmers who should be present in the field visits.

- Partnership issues; timely submission of reports, working as a team, use of communication tools, like the wiki

- Need to conduct a West Africa scientific symposium towards the end of 2015 to present major findings and publish a proceeding. Selected papers will be published in a peer reviewed journals.

- There is a need to have closer and broadened collaboration with IER for better ownership of results.

- Use the established IPs to feedback research results to the wider groups and include representative farmers and their organizations. Also look for options to print the findings of the research in the local languages.

The meeting was concluded at 12:30PM

The minutes were compiled by Birhanu Zemadim

(Africa RISING Mali Activities Coordinator)

http://africa-rising.net/