## Slide 1
Deliverables | Status (March 2021) | Status (August 2021)
Mother trials for water limited yields established | Trials for 2021 established as planned | Benchmark yields from trials being integrated in analysis
Revised protocol finalized | Protocol updated and approved as part of 2021 workplans | All three modules implemented. Data available and being processed
Detailed farm profiles documented (Data sets by farm typologies; estimates of yield gaps; farm-scale SI scaling compiled.) | Data collected from Module 1; electronic survey instrument created using surveystack and used to implement both Modules 1 and 2 | Modules 2 and 3 successfully implemented. Data files submitted for dataverse upload
Activities by implementing students monitored | Students have begun synthesizing Module 1 data | Graduate students collected data; now synthesis ongoing
Estimates of yield gaps; farm scale SI scaling (formerly Data sets by farm typologies; estimates of yield gaps; farm-scale SI scaling compiled) | Yield cuts data collection for yield estimations currently underway for mother trial host farms, baby farmers, and local controls | Whole farm yield measurements were completed. Datafiles available; data being processed; Data also submitted for dataverse upload.
Data uploaded on to dataverse | To be done at a later date(August/September 2021) | Data files submitted for dataverse uploading
Sub-activity 5.1.1.4 b. Case studies: Application of SI technologies use among farmers interacting with Africa RISING at different intensities. Regis Chikowo

## Slide 2
Deliverables | Status (March 2021) | Status (August 2021)
FtF indicators data submitted to M&E/IFPRI for upload | NA | NA
Survey instrument verified (Module 3) | Survey instrument was verified in November/December 2020 https://bit.ly/2OoLlBH New sites were selected for the survey; instruments shared with partners | Module 3 implemented and all data collected, Analysis partially completed and results are put into a report (Consultancy Report from Munyaradzi Mutenje)
Econometric model set up | This is still under development | Data was all collected and analysis is in progress
Model Results after validation | No results are yet available, which will be finalized after the 3rd wave | Data was all collected and analysis is in progress
Data generated and uploaded into Dataverse | No results are yet available. It will be finalized in July/August 2021 | Data is still being analysed – upload expected by End of September 2021
 |  | Drivers of Sustainable Intensification technology uptake; Implication on adaptive capacity, food security and scaling Submission in October to:Technology forecasting and social change Student thesis of Module 3 (no link yet)
Sub-activity 5.1.1.4. Continued (CIMMYT)

## Slide 3
Deliverables |  | 
List new deliverables planned after above submission | In depth study of a subset of intensified and stagnant farms Mansciprt submitted by April 2022 | 
Proposed action for 2021/2022: Continue with data synthesis, link modules 1,2 and 3. Follow up with a subset of intensified farms and contact in-depth analysis of their circunmstances. Also a subset of stagnant farms toi be revisited. |  | 
Sub-activity 5.1.1.4. Continued (CIMMYT)

## Slide 4
Deliverables | Status (March 2021) | Status (August 2021)
Updated panel survey instrument | Instrument for legumes survey available and being used for implementation grain legumes yield cuts | Instrument available and was used at harvest to track grain legumes production for 120 farms.
Panel survey implemented | Panel legumes survey implementation being completed by end of April 2021 | Grain legumes survey implemented. Datra submitted for dataverse; Data analysis has began on this new dataset
Meta-analysis data collated | Some data fully analysed, papers published, some in progress (Bill and Jayne, 2020; Bill et al. 2020 | Innocensia Festo John, Sieglinde Snapp, Alison Nord, Vimbayi Chimonyo, Chiwimbo Gwenambira, Regis Chikowo 2021. Marginal more than mesic sites benefit from groundnut diversification of maize: increased yield, protein, stability, and profits. Agriculture, Ecosystems and Environment 320:107585 (https://doi.org/10.1016/j.agee.2021.107585) Burke B and Jayne T. 2021. Disparate access to quality land and fertilizers explain Malawi’s gender yield gap. Food Policy. 100: 102002. https://doi.org/10.1016/j.foodpol.2020.102002
Sub-activity 5.1.1.5: Panel survey, soils processing and meta-analysis studies for maize-grain legumes sequences and implications for sustainability. Regis Chikowo

## Slide 5
Deliverables | Status (March 2021) | Status (August 2021)
Meta-analysis dataand publications (continued) | WJ Burke, SS Snapp, TS Jayne - Agricultural Economics, 2020. An in‐depth examination of maize yield response to fertilizer in Central Malawi reveals low profits and too many weeds. Agricultural Economics; 923-940 | 
 | Kopper SA, Jayne TS, Snapp SS, 2020. Sifting through the weeds: Understanding heterogeneity in fertilizer and labor response in Central Malawi Ecological Economics 169, 106561 | 
List new deliverables planned after above submission | More publications.. | 
List new deliverables planned after above submission | Data integration in meta-analysis manuscripts | 
Sub-activity 5.1.1.5. Continued