## Slide 1
Deliverables | Status (April 2021) | Status (August 2021) & means of verification where applicable
Manuscript on the effect of soil and water conservation technologies on maize yields, net returns, household income, and food security | Manuscript submitted to Land use Policy | http://docs.google.com/viewer?url=https://iaae.confex.com/iaae/icae31/mediafile/Handout/Paper18226/Manuscript%2520IAAE.pdf
Data uploaded on to DataVerse |  | Data submitted to M & E officer
Success story? | Manuscript under review | Dependent on the manuscript publication date
Sub-activity 5.1.7.4: Assess the effect of tied ridging, residual tied and rip tillage on maize productivity, net crop returns, household income and food security. J. Manda

## Slide 2
Deliverables | Status (March 2021) | Status (August 2021) & means of verification where applicable
Manuscript on the yield and income effects of the joint adoption improved maize and maize-legume rotations identified. | A consultant was hired to help in the generation of variables, clean and merging of the data sets from the Malawi panel survey data (2014-2018) | The data was cleaned, relevant variables were generated and preliminary analysis has been done Additional climatic data collected Manuscript will be developed by December 2021.
Data uploaded on to DataVerse |  | Data already on dataverse
Proposed action for 2021/2022: Linked to this sub-activity, we want to combine the Malawi panel survey with spatial data climatic data to explore the link between the adoption of SI technologies and adaptation to climate change. Co-researchers. Francis Muthoni, Sieglinde Snapp and Regis Chikowo. |  | 
Sub-activity 5.1.7.5: Determine the effect of the joint adoption of improved maize varieties and maize-legume rotation on maize productivity and crop incomes in Malawi. J. Manda

## Slide 3
Deliverables | Status (April 2021) | Status (August 2021) & means of verification where applicable
Manuscript on the impact of AR investments on ROI, productivity, food security and poverty. | Data collection underway for the estimation of ROI for the AR-NAFAKA investments. | Data collection completed and some preliminary analysis done. Draft manuscript by February 2022 (NAFAKA)
Data uploaded on to DataVerse | Data collection completed | Data will be uploaded by March 2022
Proposed action for 2021/2022: Linked to this sub-activity, we want to conduct ROI (ex-post) using panel data for Malawi and Ghana and Ex-ante (using demonstration trial data). Co-researchers. Bekele Kotu, Carlo Azzarri , Ricker-Gilbert Jacob (Purdue University) and Oyakhilomen Oyinbo (University Ahmadu Bello University) |  | 
Sub-activity 5.1.7.6: Determine Africa RISING research on household welfare and return on investment