## Slide 1
Interactive radio to scale-up agriculture and nutrition technology in Africa RISING Mali - pilot
Jonathan Odhong’
Africa RISING WA & ESA CKM Leader
West Africa Review and Planning Meeting
6– 8 June 2018

## Slide 2
Outcome no._ _ _ |  | Output no._ _ _ | Activity no._ _ _
Sub-activity title | Interactive radio to scale-up agriculture and nutrition technology in Africa RISING Mali - pilot |  | 
Location/sites for sub-activity | Bougouni District, Southern Mali. |  | 
Implementation timeframe (start/end date) | June 2017 – December 2017 |  | 
Objective | Awareness creation for dual purpose sorghum varieties validated by Africa RISING and knowledge sharing. |  | 
Deliverables achieved | 9 interactive radio programs focused on different facets of producing dual-purpose sorghum were developed and broadcast on KAFO KAN radio—one of the most widely listened to stations in the district. Recordings of this program available at: https://cgspace.cgiar.org/handle/10568/16926 Formative evaluation workshop & report summative evaluation workshop & report Training materials developed for training broadcasters on program presentation and development Total interactions through the programmes – 1361 [live calls - 87, incoming calls - 1110, outgoing calls: 164] Approximately 36,300 people reached |  | 
Team involved | Mali research team (ICRISAT) and partners Farm Radio International Africa RISING communications team |  | 

## Slide 3
Lessons learnt
Start off activities should align well with the farming calendar
Longer term intervention
Involvement of all stakeholders in each step of design, production, and broadcast is critical
*reported in more detail in the latest technical report to USAID

## Slide 4
Thank You