| FIFTEENTH MEETING (SKYPE) MINUTES OF THE BABATI RESEARCH TEAM FRIDAY, 10TH MARCH 2017: 09.00 -09.50 hrs |  |
| --- | --- |
| Participants M.Bekunda Chief Scientist /Chairman F.Kizito PI- Natural Resource Management J.Ochieng PI- Integration of vegetables into maize farming system B.Lukuyu PI – Integrated Livestock Feeds G. Fischer Gender specialist G.Ndibalema Research Communications Assistant /Secretary F.S.Ngulu PI- R4D Platforms Not Connected A.Gaspar PI – Food storage, Value addition and Mycotoxin management Absent J.Kihara PI- Crop management efficiency |  |
| Agenda: 15.1 Updates from the Chief Scientist 15.2 Implementation progress from PIs 15.3 Preparations for A-R Project Manager’s visit to Babati 15.4 Updates on publications based on deadlines as per Dar July 2016 15.5 AOB |  |
| Agenda | Remarks/Follow-ups |
| 15.1: Updates from the Chief Scientist (CS) | The update covered three main areas: i. Revision of Africa RISING Logframe: the revised version will be circulated to PIs ii. Auditing of Africa-RISING-ESA Project: Coming soon and will compare project outputs against what was planned, and determine value-for money. PIs may be called upon for clarifications iii. Emphasized role of team engagement with development partners for taking technologies to scale. It is a budgeted line item in the teams’ workplans. He updated the meeting on a recent engagement with CRS Tanzania during which vegetables, legumes and youth were prioritized as partnership activities. Response: Justus mentioned he had held discussions with DAICO in Babati; to identify potential development partners to collaborate with. He promised to share the list with other PIS once he gets the list of partners from DAICO. iv. CS commend the good work done by ESA team during the Science meeting in Dar, July 2016. |
| 15.2: Implementation reports from PIs | i. Vegetables Integration: In his presentation, Justus indicated that all planned activities are in progress since January 2017; except for the trial on poultry manure. He has already held quite fruitful discussions with CIAT (yesterday/Thursday) on how to integrate vegetables with manure. Comments: Bekunda: - Commended the vegetable team but requested a revision what the Project Manager should visit in place of the poultry manure experiment she had proposed. - PIs are requested to prepare research protocol for their respective sites ii. Natural Resource Management: Fred highlighted the range of trials in progress including normal maize trials, and Napier grass sown to contour bands. He also touched on fruitful discussions with Justus on integration Comments: there is need for closer integration with the Livestock component. Face to face discussions between CIAT and ILRI would be quite helpful. For instance determining optimal contour band intervals on steep slopes iii. Integrated Livestock Feeds: Initial focus was on introduction of improved fodder species; now due for scaling up. Ben expressed the need for other types of social economic analyses and not just benefit-cost studies only. Comments: Agreed: - ILRI and CIAT will engage more in planning and implementing together rather than post-experiment installation requests. - Justus, an economist, will provide economic analysis support to Babati colleagues as need arises, given his closeness to the teams. iv Gender Comments: a. CS noted that some of the teams have not been engaging cross cutting themes, including like gender. b. CIAT having been singled out, Fred promised initiation of face to face interactions with Gundula. v. Platforms Chief scientists urged PIs to integrate platforms in their activities. Ngulu referred to a report he circulated in respect of the inception meetings at ward level as an initial step towards initiation of R4D platforms at ward level. The meetings captured challenges and opportunities for agricultural development. The next step is to organize a meeting for all PIs and JUMBA secretariat to develop plan for the ward platforms. CS urged the PIs to conduct their activities through the platform process rather than holding parallel community group meetings. Comments: Agreed: The coming together of the PIs to Babati during the Project Manager’s visit presents an opportunity for a Babati Team Meeting in the morning of 29th March to review progress and plan further integration. Jumba Chair to be invited. |
| 15. 3: Preparations for Project Manager’s visit | - The Project manager will be in Babati from 29th March afternoon to 31st March afternoon. - On the basis of 2016/17 work plans developed by PIs, the Project Manager circulated research experiments and other activities she wished to visit, preferably new activities. - CS requested PIs to select sites corresponding to the identified activities and submit these to Ngulu who will propose the most efficient routing. To be effected by Wednesday 15 March. - The gender team was contemplating organizing field visits coinciding with the Project Manager’s schedule, but will adjust accordingly once the final itinerary is developed. |
| 15.4: Updates of publications | - CS reminded members about their commitments during the Phase I Legacy meeting in Dar during July 2016. - Meeting agreed with the proposal to work with CABI on a handbook of SI innovations for ESA, and that planning for this should be put in motion. |
| 15.5: AOB |  |
| 15.5.1: Preparations for upcoming Agricultural Show in Arusha | The meeting endorsed the idea and requested Ngulu to update the team with the requirements during the Babati Team Meeting on 29th March. |
| 15.5.2: Skype meeting schedule | Once a month, especially when field activities are at a peak |