## Slide 1
Sub-activity 1.3.1.4: Ex ante impact assessment with Trade-off Analysis Model for Multidimensional Impact Assessment (TOA-MD) for regional relevance of Africa RISING technologies. . Lieven Claessens
Deliverables | Status (March 2021) | Status (August 2021)
Inventory of existing bio-physical data from Africa RISING experiments. | NA | 
TOA-MD model set up for Tanzania | NA | 
Ex-ante impact assessment implemented and analyzed | Analysis completed and documented as a Chapter in the PhD thesis of Shrabashi Ray. Draft journal article is pending final verification of some data and will be submitted before the next report. | Missing/erroneous data were received, analysis redone. Article will be submitted Sept21.
Data uploaded on to DataVerse | NA | 
FtF indicators data submitted to M&E/IFPRI for upload | NA |