## Slide 1
A trip report on forage establishment and data collection in Babati District, Tanzania
5-21 April 2017
Report prepared by
David Ngunga and Alphonce Haule
Notes: <number>

## Slide 2
ILRI research activities focuses on (i) improving utilization of locally available livestock feeds (crop residues and grains) and (ii) introduction of improved forages such as Napier grass, Brachiaria spp and Cenchrus ciliaris grass in the six AR action villages in Babati district.
So far ongoing research has achieved noticeable results like increased green forages on farms, increased use of crop residues in the dry season, increased milk production from 3-8 litres milk on average and reduced work load to women who tends animals in six villages
The innovation of improved forages, especially Napier grass and use of crop residues has attracted interest of many farmers across all villages in Babati, as a result a call has was made by the district and village leaders for the project to expand the technologies to more villages.
Introduction

## Slide 3
Objective of this activity
To scale up the use of forages amongst more farmers in Long, Sabilo, Seloto, Hallu, Matufa and Shaurimoyo villages.
To collect data on the performance of improved forages (growth, biomass, disease and drought resistance) data were collected in mother demo plots.
Notes: <number>

## Slide 4
Counting Napier grass tillers in a stool before cutting weighing biomass
Specific field trip objectives
Identify new farmers for scaling up the use of improved forages (30 new farmers were targeted)
Gap filling in all existing mother plots in the six AR villages
Select and prepare fields for establishing large plots of improved forages (Rhodes grass and Legumes - Desimodium)
Data collection biomass yield and follow up on management of plots with farmers

## Slide 5
Identify 30 new farmers for scaling up improved forages
Activities conducted during he field trip
Meetings were held with participating farmers in new five villages of Singu, Riroda, Sayura, Kisangaji and Endabegi to discuss and get common understanding of the activity
Farmer groups and individual farmers were selected to implement this activity
Eighty (8) forage plots were established for learning and obtaining planting materials.
A plot planted with Napier grass in Riroda village

## Slide 6
Details on establishment of improved forages in both old and new villages in Babati district in 2017
Village | Participants |  |  |  |  | Total land size (Acre) established with forages
 | No of Individual farmer |  | No of farmers in a group |  |  | 
 | Men | Female | Men |  | Female | 
Long/Bashineti | 3 |  |  |  |  | 0.75
Sabilo | 2 | 2 |  |  |  | 1.0
Seloto | 2 |  |  |  |  | 0.25
Haysam | 4 | 6 |  |  |  | 2.5
Singu (New village) |  |  | 11 |  | 9 | 1.5
Riroda (New village) |  |  | 10 |  | 6 | 2.0
Sayura (New village) | 1 |  |  |  |  | 0.25
Kisangaji (New village) | 3 | 1 |  |  |  | 
Endabegi (New Village) | 2 |  |  |  |  | 
Shaurimoyo | 2 | 5 |  |  |  | 
Hallu | 3 | 2 |  |  |  | 1.5
Wang’warai famers training center | Owned by Babati district platform |  |  |  |  | 2.0
Total No Farmers | 74 (43 men & 31 female) |  |  | 2 farmers group (21 men and 15 females) |  | 11.75

## Slide 7
A summary of activities and lesson learnt
More than ten (10) acres were planted improved forages (Napier grass, Rhodes grass, Desmodium silver leaf and Lablab purpureus) in their respective villages
A total of 74 (43 men and 31 women) participated in establishing (land preparation and planting) improved forages
The activity created awareness to more than 200 farmers who participated in meetings on the importance of planting improved forages, building proper cattle houses and feed troughs.
The activity created opportunity and link with farmers to organize for the forth coming study in improved use of crop residues following harvest of maize

## Slide 8
Observations and issues raised by farmers during the field visit during field work
Farmers received improved dairy cows through different projects like Heifer Project Tanzania, they need improved bulls to avoid inbreeding.
Farmers in new villages lacked knowledge and skills on improved forages, harvesting, processing and feeding of crop residues (feed rations).
Farmers don’t have proper feed storage structures and feeding troughs thus animals waste feeds.
Farmers expressed great interest in being trained on using Gidawali salt for supplanting feeding in the dry season to increase palatability. They said this knowledge can help farmers to store more feeds for feeding their livestock in the dry season.
A dairy cattle and her calf in Signo village

## Slide 9
Lessons learnt
Farmers seemed very interested in learning by seeing and doing: Our training and actual demonstration attracted many farmers and hence has high potential to enhance adoption of the technology.
Farmers were so cooperative and seemed to have huge trust in researchers when they participated in our activity from the beginning.

## Slide 10
Other photos taken during field activities in Babati district
A dairy cattle eating natural grasses in Endaberigi village
Integrating forages (Napier grass and Desmodium silver leaf) in a banana plantation in Endaberigi village