Progress report July-October 2012: Transforming Key Production Systems: Maize Mixed East and Southern Africa

(Take AIM: Agroecological Intensification in Malawi and Tanzania through action

Research with women and men farmers)

In paragraphs or bullet point, please provide the following information (3 pages):

Purpose, objectives, planned outputs: from submitted proposal

Purpose: The purpose of the Michigan State University-led component of the Africa RISING Program in Malawi is to enhance farmer knowledge and support intensification (SI)  pathways for productivity gains in maize-legume diversified systems.  The main objective of the project is therefore to set up a research approach that systematically assesses SI best-bet options that appropriately respond to the needs of resource-poor farmers - particularly female headed households. Building on successful examples of participatory action research and experiences from biophysical research on smallholder farms in Malawi over the past 2 decades, the research team has begun taping into these products of agricultural research to move towards more sustainable smallholder production systems. Using a Randomized Control Trial (RCT) design, the project plans to establish the efficacy of intervention strategies by comparing project outcomes from intervention and counterfactual cluster of villages over a 4-year period. We envisage that farm-scale production strategies employed by different farm/farmer typologies will be further distilled through scenario analyses using farming systems simulation modeling approaches. This project was deemed to be a long-term initiative from the very on-set (unlike the 6-months quick-wins), and thus the activities over the past six months largely centered around building a credible long-term research implementation framework. To this end, in each of the two intervention districts in Malawi (Ntcheu and Dedza), a comprehensive RCT design has been established that will be a credible basis for systematic and scientifically sound evaluation through both baseline, midline and endline surveys.

Partners: provide a comprehensive list of partners involved in project implementation and their roles

- Smallholder farmers in target districts - adaptive testing of technologies through mother and baby experiments. Lead farmers who host the mother trials during the forthcoming  2012-13 season that begins this November

- Malawi Agricultural National Extension Department - mobilizing farmers, extension services, convening meetings/workshops (district agricultural development officers for Ntcheu and Dedza districts).

- Concern Universal (Ntcheu and Dedza ditricts) -joint training of farmers, and stakeholders

- World Vision  (Ntcheu and Dedza ditricts) -joint training of farmers, extension and other stakeholders

- Extension workers in Extension planning areas (EPAs)  - extension services, local level monitoring

- IFPRI -monitoring and evaluation input - Klaus Droppelmann (Agricultural economist/soil scientist) -

- Bunda College of Agriculture  -field protocols and participatory action research support -Dr Wezi Mhango (Crop Science Faculty)

- IITA scientists and administrators - project support, administration support

- N2Africa Project -joint farmer training workshops, legume seed support -Dr Anne Turner

- ICRISAT scientists - appropriate legume seed advice - Dr Moses Siambi

- NGO – LOMADEF - Lipangwe organic manure demonstration participating farmers - testing technologies

- NGO – Soils Food and Healthy Communities Project (SFHC) - extension methodologies and joint farmer and partners training -Lizzie Shumba SFHC Ekwendeni and Dr Rachel Bezner Kerr Cornell University

Achievements against plan: describe the achievements and deliverables.

Milestone 1. Contribute to a report by the FtF research approach committee that identifies research approaches for Africa RISING.

During the first six months of the Africa RISING program,  MSU has contributed to the development of the research approach, with Professor Sieglinde Snapp leading in the production of the first draft of the research approach. The 'mother and baby' experimentation approach for co-learning with rural farming communities is a powerful research and extension tool, that has been accepted as potential strategy for use by Africa RISING researchers, especially for the East and Southern Africa region. The MSU research team participated in the July Ibadan Research Framework meeting, the September Addis Ababa M&E meeting and the recent October ESA project meeting in Arusha.

Milestone 2. Develop a portfolio of educational materials for the participatory action research approach, including a training of trainers manual and a field trial manual.

Building on our past and on going on-farm research work in east and southern Africa, we have started consolidating 'best-fit' technical options that respond to the needs of farmers from different typologies as defined by resource endowment (access to land, capital, labour, etc). These will be packaged into pamphlets in local languages for use by farmer action groups during the next cropping season. Graduate student training is one of our core mandates. We continue to identify niches where postgraduate students can meaningfully contribute to the research agenda.  One of the graduates students, Alex Smith, has put together Integrated Pest Management (IPM) training materials. Another student, Krista Isaacs, has started consolidating participatory research training materials. These will be used during a training workshop scheduled for 6-10 November in Dedza, Malawi.

Milestone 3. Contribute to a narrative report led by IFPRI on a scan of research literature and activities at the sites, including institutions present, data sets available for modelling and characterization.

We have worked closely with IFPRI to identify sites and provided basic data for site characterization, especially for Malawi. Working with local agricultural extension services in Dedza and Ntcheu districts, we have completed the project sites identification exercise. These sites conform to the overall Africa RISING research framework - a matrix of high and low agro-ecological potential and market access.  An inventory of all the institutions working in the intervention districts has now been completed. We are still to carry out a formal baseline characterization, which will be done in collaboration with IFPRI.

Milestone 4. Host a workshop with scientists, extension educators and farmers working in the action sites, to build on the participatory research underway ....

During August, we held two project planning workshops with project stakeholders for in Ntcheu and Dedza districts.   As per plan, the workshops involved lead farmers from farmer groups, the national agriculture extension personnel at district and grassroots levels, non-governmental organizations operating in the districts (CADECOM and Concern Universal), NASFARM - which is a farmer association,  researchers from Bunda College, and Dr Turner, an IITA N2Africa project scientist. A project officer with the Ekwendeni-based Soil Food and Healthy Community project also participated in these meetings. The meetings were convened by the District Agricultural Development Officers (DADOs) from the respective districts. We have now firmly established a working relationship with these government officials in Malawi, who were also invited to participate in the 1-5 October Africa RISING workshop in Arusha.

- Key Deliverable Deviation: if specific key deliverables were not met according to proposed plan, discuss the reasons.

Some of the deliverables are work in progress and deliverables are of long-term nature. We will be meeting our obligations in the months and years to come as we fully implement the project

- List of geo-tagged locations/sites were activities took place: when activities where site specific

We have identified districts in Malawi (Dedza- 14°22S; 34°20'E and Ntcheu -14°48S; 34°37'E) and extension planning areas where field-level interventions will take place during the next cropping seasons. More specific mother and baby geo-tagged experimental locations will be available in the next few weeks.

- Support of AFRICA RISING: how will the outputs support the longer term objectives of Africa RISING?

Africa Rising has been in the process of developing a Research Framework for implementation of projects beyond the 'quick-wins' phase.  Our input to the process will advance the program objectives. We are also currently contributing to the Africa Rising M&E  framework. The MSU team has experience with the Outcome Mapping M&E methodology that tracks behavior changes on project stakeholders as a result of project activities.  MSU contribution in this regard will thus contribute to a sound project M&E framework in the longer term.

- Scalability: if these deliverables are intended to increase in scale during years 2-5 of Africa RISING, what actions do you propose to be implemented in future?

- Characterize biophysical and socio-economic farmer circumstances, to lead to farmer typologies for better targeting of technologies

- Conduct several capacity building training workshops with stakeholders, emphasizing  on participatory methodologies and approaches

- Secure inputs (seed, fertilizer) for participatory experimentation at scale - these should not be limited to only a few villages

- Lessons learnt: what lessons, including about the partnership you had within the project, have been learnt during the implementation of the project that will help Africa RISING to succeed in future?

- we have had only a few months of interacting with partners, but is clear that partners should be closely involved at different stages of the project to ensure 'ownership' of the process

- Publicity: Africa RISING encourages publication of the study results in refereed publications and presentation in conferences for wider public consumption. Advise the potential of your work getting to this stage

- This will be part of our core focus in the coming years. We will publish the results through graduate student training. We will present our work in different fora, including the Afnet workshop this coming October, in Kenya.