MINUTES OF AFRICA RISING MONTHLY MEETING

Date 08/05/2015

Time 9AM

Venue ICRISAT conference hall

Africa RISING team in Mali conducted the first monthly meeting at Samanko. The welcome and opening remarks were made by Dr. Ramadjita TABO, Director of ICRISAT for West and Central Africa. Dr. Birhanu, Africa RISING program coordinator in Mali highlighted participants the agenda of the monthly meeting as follows:

- Feedback from team members on their progress

- Discussion on field activities in partnership with non CG members

- Site coordinators in Bougouni and Koutiala

All participating institutions made brief presentation on their activities during the meeting. Then each CG institution was requested to discuss with its NGO partner to harmonize and identify activities in Africa RISING intervention villages. This exercise helps to prepare a consolidated contract with partners. ICRISAT on behalf of other CG centers will prepare one contract for each local partner. Finally the two site coordinators were briefly introduced to participants and shared contact details.

Feedback from team members on their progress

Dr. Birhanu informed participants that the work plan for 2015/2016 was finalized and submitted to IITA. IITA the same week sent the document to the steering committee for approval. He thanked all partners who contributed to the development of the work plan.

Dr. Eva insisted on the participation of women in the nutrition component and highlighted the importance of a local NGO AMASSA in the program. She also expressed concern about the involvement of other partners CAAD and GRADCOM and duplication of activities in the villages. According to Dr. Haile however no duplication will occur. The Africa RISING activities are part of the major groundnut program activity in West Africa. Hence, there will rather be a complementarity instead of duplication.

Mrs. Clarisse Umutoni and Dr. Augustine Ayantunde reflected on ILRI’s on-going activity. With support from a local NGO activities to demarcate livestock routes have been completed in two communities (Sirakele and Zanzoni). In addition, the approval process by the regional administrative body for the local conventions developed is still underway.

Dr. Albert Ruamba reflected on AVRDC’s current activity plans and informed participants same activities will be conducted this year similar to past activities. These include: Intercropping and pure cropping.

Dr. Caroline of AVRDC stated that training modules are about to finish for the nutrition theme and a meeting is scheduled next week to decide conducting farmers training.

According to Dr. Catherine from ICRAF, improved plant material, grafted and non-grafted seedlings of indigenous fruit tree species have been planted. These include Shea, baobab, jujube and tamarind. The importance of fresh leaves of moringa and baobab consumed as vegetables was discussed. She also stated that protocols were delivered to MOBIOM and AMEDD for data collection on these various local species. Regarding the innovation platforms, characterization study was carried out. All stakeholders involving in agricultural development were identified and characterized as well as the level of interaction among different stakeholders.

Discussion on field activities in partnership with non CG members

Scientists from each CG centers were advised to discuss with each local partner to come up with activity plans to implement in the coming rainy season. There were group discussions and the agreed activities will be included in the newly prepared contract agreement by ICRISAT and local partners.

Site coordinators in Bougouni and Koutiala

Dr. Birhanu informed participants that the two newly hired site coordinators will be in the offices of MoBioM (in Bougouni) and AMEDD (in Koutiala). The site coordinators will coordinate activities on the ground with different partners. All participating institutes were advised to make use of the site coordinators. The site coordinators will also be responsible to the data collection in each activity. Scientists and local NGOs were advised to handover data to the site coordinators in time. Data collection and management has become one of the major concern of USAID. IFPRI prepared the data monitoring tool called PMMT and the two site coordinators will get training in August by IFPRI team to work on the data monitoring and management.

The meeting ended at 10:05AM.

Compiled by Karamoko Traoré ,Marc Traoré and Birhanu Zemadim