Africa RISING Mali Partners Meeting

18 October, 2016

ICRISAT West Africa Regional Office – Bamako, Mali

Present

- Dr. Ramadjita Tabo , ICRISAT – Chair

- Dr. Irmgard Hoeschle-Zeledon, IITA

- Mr. Jonathan Odhong’, IITA – Taking minutes

- Dr. Birhanu Zemadim, ICRISAT

- Dr. Clarisse Umutoni, ILRI

- Dr. Augustine Ayantunde, ILRI (joining via Skype)

- Dr. Jean-Baptiste Tignegre, AVRDC

- Mr. Bougouna Sogoba, AMEDD  (joining via Skype)

- Dr.Kalifa Traoré, IER

- Dr Fatimata Diallo Cissé, IER

- Dr Caroline Sobgui, AVRDC

- Mr Diakité Adama, ICRAF

- Dr Catherine Dembélé, ICRAF

- Dr Hippolyte Affognon, ICRISAT

- Dr Hamidou Nantoumé, IER

- Dr Bekele Kotu, IITA/Ghana

- Dr Felix Badolo, ICRISAT

- Dr Baloua Nebie, ICRISAT

- Mr Boubacar Sinaré, ICRISAT

Apologies

- Asamoah Larbi, IITA

Agenda

- Africa RISING program Phase II - what is new?

- Upcoming Scientific workshop in Mali

- Communication update for AR phase II

- Planning for the national livestock consultation workshop in Mali, progress of activities

- Review of field visit program of activities

The meeting started at 2:10 pm and was chaired by ICRISAT West and Central Africa Hub Director, Dr. Ramadjita Tabo.

To get the meeting underway, Dr. Tabo introduced the agenda for the meeting and then invited participants to introduce themselves. In his brief opening remarks, he thanked everybody for taking time to join the meeting noting that the meeting was an opportune moment for members to acquaint themselves with changes in the recently approved second phase of Africa RISING program and to also  transparently discuss any emerging issues that affected project implementation in phase 1 that will need to be addressed in the new phase.

Africa RISING program Phase II - what is new?

Dr. Zeledon thanked all present at the meeting for making time to attend. She also congratulated the Mali team for always holding regular meetings where partners can appraise each other on project implementation noting that it is on the merit of good project implementation (facilitated by these meetings) that a second phase of Africa RISING was approved. Zeledon also expressed special appreciation to USAID for having and showing confidence in the Africa RISING team by granting a second phase for the program (and particularly mentioned Jerry Glover) as a great ambassador for the program both within USAID and beyond. She noted that this phase II approval was therefore  a very welcome challenge for all partners involved in the project to deliver even greater impact for smallholder farmer communities who are targeted by the project. Zeledon highlighted the following changes in Africa RISING phase II (see bullet points below) as significant ones that partners needed to take note of. She also encouraged partners to take time and read in detail the phase 2 proposals available for download from the project wiki page - https://africa-rising.wikispaces.com/Phase+2

- Phase 2 has new scaling targets. USAID expects more collaboration and partnerships with development projects/ partners to reach these new targets. Target figures for Mali can be seen in the West Africa regional proposal on the wiki.

- There is also change in thinking of the project – from R4D to R-in-D . We are expected to start working with development partners from the beginning and developing solutions that directly address their needs (develop technologies demanded). This is meant to ensure better and more adoption of the technologies developed and promoted by the project.

- USAID expects much more harmonization across the program and across countries. Despite all the differences we are expected to harmonize how we work. How this is to be achieved is espoused in the Africa RISING umbrella proposal. This will increase impact, faster learning and avoid duplications. One of the ways to achieve this is through Communities of Practise (CoP) that will be implemented across the program. Some discussions on this started two weeks ago at the Africa RISING ESA phase 2 planning meeting in Lilongwe, Malawi.

- In phase 2 partners are expected to start measuring sustainable intensification indicators to help an ex-ante assessment of technologies per the five SI domains. A systems research specialist will be recruited by the program to help the project have better focus on addressing systems research questions.

- Data management plan used in phase 1 is not new, but is expected to continue. Rather partners are expected to do it better and be more pro-active to upload data to CKAN. This will be enforced more strictly in phase 2 and failure to do it will lead to no funding for those who don’t adhere.

- The budget hasn’t changed from phase 1 as we get the same level of funding, but have to reach more people.

- There will be an official launch of phase 2 in 16 – 19 January, 2017 (Will also involve a scientific discussion). This will be done instead of the annual learning event.

Upcoming Scientific workshop in Mali

Updates about the upcoming scientific workshop  for Africa RISING West Africa project were given by Dr. Birhanu Zemadim. He noted that the planning for the meeting was ongoing. So far a call for abstract was sent out to all project partners and 21 abstracts in total had been submitted from both Ghana and Mali.  The aim of the meeting is to consolidate the research outputs from phase 1 (the past 3-4 years) of the project by publishing papers in peer reviewed journals. Next, the Africa RISING West Africa Chief Scientist will send guidelines on the next steps for partners to follow leading up to the meeting which is scheduled for 12 – 13 December, 2016.

Members discussed the planning for this event and the expected outputs from the meeting. The following points were enlisted for further discussion by the organizing team:

- Consider publishing the manuscripts in Thompson indexed peer reviewed journals

- Consider production of a book (on sustainable intensification in the Sudano Sahelian zone) or publish a booklet on workshop proceedings

- The timelines may be quite short so there needs to be quick follow ups on the process/planning for the meeting. The Africa RISING ESA project held a similar meeting in July so it would be best to consult with them also on how they planned for their own meeting and any lessons learnt from there.

Communication update for AR phase II

Mr. Odhong briefed member on the following (see bullet points below) adjustments to the approaches to be used for communication in phase 2 of the project. He explained that most of these proposed changes had been informed by experiences and lessons learnt from phase 1.

- 3 extra areas of delivery had been added to the 5 which were focused on by the communications team in Africa RISING phase 1. The new additions were: cross-project and cross-issue exchange, Use communication tools to directly support scaling, and wider engagement with sister / complementary projects. The other standing delivery areas (from phase 1) that communications team will continue to work on are: Promoting external communication, pushing project and program research for policy impact, knowledge sharing and learning, publishing, and internal communication.

- The communications team will therefore continue to: document project successes through stories and case studies; support annual learning event, review and planning meetings; training partners on different communication tools; facilitating open access; and use of innovative ICT tools to support scaling of select Africa RISING technologies.

- Slight change of approach in Mali – A communications intern (who will focus attention on Africa RISING only) to be brought on board to support efforts by Agathe and Jonathan  in documenting each and every activity by Africa RISING partners in Mali. A similar approach to be used in Ghana as well.

A suggestion was made by participants for the communication team to also consider using high profile visitors to the project sites as a means of creating greater project visibility.

Planning for the national livestock consultation workshop in Mali, progress of activities

Drs Nantume and Kalifa provided an update regarding the progress in planning for this meeting. He however noted that partners seemed to have divergent understanding on the terms of reference for this meeting and this was resulting in delays in terms of planning for the event. A date agreeable to all partners was also yet to be agreed. Some of the sticky points that members discussed were:

- What is supposed to be the main output of the meeting?

- What is the scope of the invitees to the meeting? Is it national or only focused on the relevant regions to Africa RISING?

- What focus – large ruminants, small ruminants or both?

- What is supposed to be the nature of presentations at the meeting?

- How long should the meeting/workshop last?

- How many participants should take part at the meeting?

Partners discussed the above issues at length and decisions were made as follows:

- Workshop to be held on 8-9 December, 2016 in Bamako (the week prior to scientific workshop on 12 – 13 December). This was to ensure that the travel schedule isn’t hectic for participants travelling in from outside the country to take part in the meeting.

- A maximum of 30 participants  to be invited for the event.

- Invitees to be those working within Africa RISING project regions.

- Terms of Reference to be refined by Drs Nantume Kalifa, and Augustine  and then circulated to members for comments.

Review of field visit program of activities

Led by Dr. Birhanu Zemadim, members reviewed the planned itinerary for the three days of field visit to Africa RISING project sites. No changes were made to the final version of the itinerary which had been circulated to partners.

Any Other Business

There being no other business, the meeting was ended at 4:30 pm.