Minutes of Africa RISING Mali partners Meeting

Date: Friday 10, 2015

Venue: ICRISAT/Samanko

Agenda of the Meeting:

- Allocation of 2015/2016 budget for partners

- Contracting and sub-contracting Issues

- Evaluation of sound activity costing system

- Location of site coordinators (MoBioM office in Bougouni & AMEDD office in Koutiala)

- Technical support provided by partners for Theme 3 component: Intensive livestock and integrated crop-livestock production

- Other issues

The meeting was opened by Dr Ramadjita Tabo and participants were given chance to present themselves. List of participants is presented in Annex 1. After the opening remarks Dr. Birhanu Zemadim introduced the five agendas to the house. We had a thorough discussion and came to the final remarks presented below:

- Allocation of 2015/2016 budget for partners

- It was agreed that the amount allocated to AMEDD to facilitate the IP meetings (for Theme 1) in Koutiala and Bougouni was not enough. Additional $5000 USD was allocated to be shared by ICRAF ($3000 USD) and ICRISAT ($2000 USD).

- Currently ICRISAT charges 16.7% on all fund transfers, a value changed from 5% previously. If the former is applied partners will be subjected to reduce activity items. It was agreed to seek further guidance from ICRISAT finance. Dr. Birhanu was tasked to communicate the finance unit and inform partners on the outcome.

- The current proposed budget for nutrition activities in Mali is $207,000 USD. The presented 3 activities in the work plan do not reflect the amount. Hence it was agreed to revise the budget in consultation with Drs Caroline, Eva and Fatimata. In line with this it was not clear how the current estimate of $25,000 was made for IER for the nutrition activities. Dr. Fatimata agreed to send a final version of activity detail that justifies the new figure needed which is $40,000 USD.

- The total budget for MoBioM was limited to $20,000USD. This is because MoBioM failed to present the due diligence document required by ICRISAT finance.

- The initial budget for CAAD and GRADCOM on groundnut intensification option was $7000 USD for each institute. However representative from CAAD presented a detailed activity plan with a new figure $ 9000 USD. The increased budget reflected the need to conduct the intensification options in the villages of the technology parks (M’Pessoba in Koutiala and Flola in Bougouni). Hence the revised budget by the two institutes was accepted.

- AVRDC indicated that one of its proposed activities was not included in the current shared working document. This might have occurred during compilation and it was agreed to include the activity with its budget allocation. The allocated budget for the missed activity was $25,000USD.

- MoBioM stressed why they are not part of the nutrition program. Mr. Sidibe, a representative from MoBioM indicated that they participated in the nutrition meeting and expected to be called to participate in the activities. However participants discussed that there is lack of the right expertise in MoBioM to involve in the nutrition activities. It was agreed that in the long term the project needs to fill this capacity gap in local partners.

- Participants agreed to continue the work of biomass assessment with AMEDD and the proposed budget was $15,000 USD. However there has to be a report coming out that contributes to the Africa RISING program in Mali.

- Contracting and sub-contracting Issues

- In the entire program there should be one contract signed by ICRISAT for all local partners. ILRI has an ongoing contract with AMEDD and in the present work plan it was agreed that ILRI’s component of partner cost is to be maintained within ILRI’s budget.

- MOBIOM has been asked to improve and update its due diligence to allow accommodating more demand driven activities in Bougouni.

- Evaluation of sound activity costing system

- Participants agreed that the proposed budget should reflect the activities presented in the work plan. Budget should be allocated to each activity and need to be consumed in time. There shouldn’t be under/over spending.

- Location of site coordinators (MoBioM office in Bougouni & AMEDD office in Koutiala)

- Recently two scientific officers (Mahamodou Dicko and Karamoko Traore) were recruited to coordinate the research activities in Koutiala and Bougouni. AMEDD and MoBioM expressed their willingness to host each of the site coordinator. Detail logistical issues will be discussed with ICRISAT management at Samanko.

- Technical support provided by partners for Theme 3 component: Intensive livestock and integrated crop-livestock production

- Initial briefing was made to the Theme 3 component of Africa RISING program in Mali. Dr. Sapna Jarial was leading the Intensive livestock and integrated crop-livestock production proposal development in consultation with Drs Augustine Ayatunde from ILRI and Nantoume Hamidou from IER. This component was not done in the past mainly because of lack of capacity on the ground. The proposed work plan was discussed by participants and issues mainly the design and data collection protocol were discussed at large. Dr. Ayatunde briefed participants the difficulty of conducting on-farm feeding trials. The type of animal species, quantity of feed, experimental design and monitoring of the experimentation are important items to be looked in detail.

- Dr Sapna was assigned to finalize the work plan based on the information gathered from the meeting. It is expected that the revised version will be circulated on Monday 13, April 2015 for final review.

- Other issues

- Reporting requirements were discussed in great length. Participants argued that lots of undocumented good works exist on the ground by partners. Each scientist from the CG center is responsible on the implementation of the planned activities and report what has been done on the ground in close collaboration with the local NGOs.

- ICRISAT and other CG partners need to work closely with the local NGO to improve the latter’s reporting system.

- ICRISAT finance unit will provide appropriate training to local NGOs regarding the rules of financial reporting.

- A reminder was made by Mrs. Agathe regarding the development of success stories in the field. This is in harmony with the discussion that was made in the recent regional meeting in Accra (23-27 March 2015).  Each Scientist is responsible to generate and compile success stories or any other events from project implementation to be shared widely.

The meeting ended around 12:30AM and Dr Tabo thanked all participants for their useful contribution and their availability especially those on Skype (Mary, Augustine, Bougouna and Sapna.

Compiled by Birhanu Zemadim and Marc Traore

Annex 1: List of participants:

| N° | Name | Institution |
| --- | --- | --- |
| 1. | Dr Ramadjita Tabo | ICRISAT/Mali |
| 2. | Dr Fred Rattunde | ICRISAT/Mali |
| 3. | Dr Kalifa Traoré | IER/Sotuba |
| 4. | Dr. Fatimata Cissé | IER/Sotuba |
| 5. | Dr. Joachim Binam | ICRAF |
| 6. | Dr Albert Ruamba | AVRDC |
| 7. | Dr. Augustine Ayantunde | ILRI (via Skype) |
| 8. | Mrs. Mary Ollenburger | ICRISAT/WUR (via Skype) |
| 9. | Dr. Sapna Jarial | ICRISAT/Niamey (via Skype) |
| 10. | Mr. Bougouna Sogoba | AMEDD/Koutiala (via Skype) |
| 11. | Mr. Karamoko Traoré | ICRISAT/Mali |
| 12. | Dr. Birhanu Zemadim | ICRISAT/Mali |
| 13. | Ms. Agathe Diama | ICRISAT/Mali |
| 14. | Mr. Gaoussou Diawara | CAAD/Koutiala |
| 15. | Mr. Toumani Sidibé | MoBioM/Bougouni |
| 16. | Mr. Marc Traoré | ICRISAT/Mali |
| 17. | Ms. Clarisse Umutoni | ILRI/Mali |