## Slide 1
INVC
Bridging Activity Concept Note
Authors:
Arega Alene
Regis Chikowo
Mateete Bekunda
Irmgard Hoeschle-Zeledon
Lilongwe
13 June 2016
Notes: <number>

## Slide 2
Background
From USAID Presentation: What the bridging activity is…
Proviso for the CN Development :
Do not re-invent the wheel: adapt to and build upon the current project situation; engage and learn from current implementers of the INVC Project & partners

## Slide 3
Activity Goal:
Reduce rural poverty through increased household incomes from soybean and groundnut production and marketing
Activity Objective:
Inclusive agricultural sector growth, increased incomes, a diversified diet and improved soil health.
Activity Components:
Advancing value chain competitiveness
Improving productivity
Capacity development (embedded)

## Slide 4
Advancing value chain competitiveness
Expected results | Output indicators | Outcome indicators
Increased marketing as a result of improved end-market competitiveness and trade Increased access to market information and financial services Increased commercial relationships in the value chains, including vertical coordination of smallholders and SMEs Increased household incomes and assets Increased lending to smallholder farmers and other value chain participants | Volume and value of soybean & gnut sold in the domestic markets Value of agriculture and rural loans disbursed to smallholder farmers and small businesses Number of smallholder farmers, SMEs, producer organizations, and trade and business associations receiving marketing and business development services | Value of incremental sales of soybeans and groundnuts attributed to project implementation Gross margin per hectare of soybean and groundnut production Daily per capita expenditures of project beneficiaries

## Slide 5
Activities
Activity | Sub-activities
1. Identify market activities for farmers, traders & processors | 1.1 Assess domestic market demand and opportunities 1.2 Facilitate business relationships between farmers & buyers
2. Facilitate access to market information and collective marketing | 2.1 Promote market information centres 2.2 Strengthen market information systems 2.3 Expand market opportunities and options 2.4 Promote community-level product aggregation & bulking
3. Facilitate access to information services | 3.1 Link farmers to financial institutions 3.2 Facilitate bank lending through credit guarantees
4. Promote household food processing, utilisation and storage | 

## Slide 6
Improving agricultural productivity
Expected results | Output indicators | Outcome indicators
Increased yields for legumes and associated crops by at least 50% Increased access to, and use of productivity-enhancing technologies by male and female smallholders Enhanced implementation of better soil fertility management, water conservation practices and other GAPs by male and female smallholders | Increased volume of grain legume products available for household consumption, dietary diversity and marketing Increased land area under legume crop production Volume of improved seed, rhizobia and other inputs used at HH level . | Maize production increased through intensification approaches More diversified and steady food supply Increased income from sale of legumes

## Slide 7
Improving agricultural productivity cont’d
Expected results | Output indicators | Outcome indicators
Enhanced use of agricultural extension and advisory services | Constructed water resource management structures Number of implemented GAPS for increased productivity Increased farmer capacity to practice and transfer knowledge and information on legume cropping GAPs. | Expanded, more diversified income sources from new enterprises and employment opportunities related to legume value chain development

## Slide 8
Activities
Enabling farmers’ access to improved seed using: Approaches piloted by INVC Seed fairs, tapping into CRS experience
GAPs technology delivery and transfer working with lead farmers, supervised by researchers and extension staff
Improved advisory services and extension delivery systems, driven by hands-on training of lead farmers
Environmental mitigation through demonstration of climate smart practices and emphasising climate-smart messages during training.

## Slide 9
High potential, high achiever 15 EPAs in 5 districts
Seed Fairs to be conducted in the districts of:
Balaka, Mangochi, Machinga
Target Areas

## Slide 10
Target EPAs & beneficiaries
NASFAM; CADECOM; FUM
District | EPAs and number of beneficiaries in brackets |  |  |  | Total bene-ficiaries
Mangochi | Ntiya (607) | Katuli (1455) |  |  | 2062
Michingi | Chicoshya (3460) | Mlonyeni (4573) | Mikindi (2725) |  | 10758
Ntcheu | Njolomole (217) | Manjawira (13) | Bilira (895) |  | 1125
Lilongwe | Nyanja (1768) | Mpingu (2509) | Chileka (5201) | Chitsma (4067) | 13545
Dedza | Chifumbwa (1407) | Kanyana (3884) | Linthipe (6312) |  | 11603
Seed fairs Districts | EPAs and beneficiaries to be determined |  |  |  | 

## Slide 11
Develop the Project M&E Plan (Logframe/Workplan developed at inception workshop).
Agree methods of tracking and reporting achievements
Monitoring and Evaluation

## Slide 12: Thank you
Notes: ESA Africa
<number>