Africa Research in Sustainable Intensification for the Next Generation

Research in Sustainable Intensification in the sub-humid maize-based cropping systems of Babati: Providing alternative integrated technologies to improve food security and income

ESA Project Proposal – Babati Research Team

(Refreshed for 2015/16 season)

Submitted to:

International Institute for Tropical Agriculture (IITA)

October 2015

The Africa Research In Sustainable Intensification for the Next Generation (Africa RISING) program comprises three research-for-development projects supported by the United States Agency for International Development as part of the U.S. government’s Feed the Future initiative.

Through action research and development partnerships, Africa RISING will create opportunities for smallholder farm households to move out of hunger and poverty through sustainably intensified farming systems that improve food, nutrition, and income security, particularly for women and children, and conserve or enhance the natural resource base.

The three regional projects are led by the International Institute of Tropical Agriculture (in West Africa and East and Southern Africa) and the International Livestock Research Institute (in the Ethiopian Highlands). The International Food Policy Research Institute leads the program’s monitoring, evaluation and impact assessment. http://africa-rising.net/

This document is licensed for use under a Creative Commons Attribution-Noncommercial-Share Alike 3.0 Unported License

This document was made possible with support from the American people delivered through the United States Agency for International Development (USAID) as part of the US Government’s Feed the Future Initiative. The contents are the responsibility of the producing organization and do not necessarily reflect the opinion of USAID or the U.S. Government.

# Table of Contents

Core research team	ii

Summary	1

Babati Site consolidated budget 2015/16 (USD)	2

Refreshed Thematic Proposals	3

Theme 1: Crop Management Efficiency	3

Theme 2. Integrated Livestock Feed (ILF)	15

Theme 3. Integration of vegetables in to maize-based farming systems in Babati	24

Theme 4. Food storage, value addition and mycotoxin management	43

Theme 5. Management of maize lethal necrosis disease	57

# Core research team

Team Leader: Mateete Bekunda,  IITA

| Name | Institution | Disciplinary expertise | Theme | % time |
| --- | --- | --- | --- | --- |
| Job Kihara | CIAT | Soil fertility | Crop management Efficiency | 17 |
| Stephen Lyimo | Selian ARI | Agronomy |  | 20 |
| Fred Kizito | CIAT | Water resources |  | 15 |
| Ben Lukuyu | ILRI | Animal nutrition | Improved livestock feeds | 40 |
| Leonard Marwa | TALIRI | Research methods |  | 100 |
| Gregory Sikumba | ILRI | Animal nutrition |  | 20 |
| Victor Afari-Sefa | AVRDC | Ag Economist | Vegetable integration | 7 |
| Inviolate Dominic | AVRDC | Horticulture |  | 15 |
| Danny Coyne | IITA | IPM |  | 5 |
| Adebayo Abass | IITA | Food technology | Food storage, value addition and mycotoxin management | 5 |
| Boniface Simon | IITA | Entomology |  | 50 |
| Gabriel Ndunguru | Consultant | Food Science |  |  |
| George Mahuku | IITA | Plant pathology |  | 5 |
| Bright Jumbo | CIMMYT | Crop breeding | Management of maize leaf necrosis disease | 25 |
| Dan Makumbi | CIMMYT | Crop breeding |  | 10 |
| Lava Kumar | IITA | Virology |  | 5 |
| Per Hillbur | Consultant | Human Geography | Institutional cooperation and co-learning |  |
| Festo Ngulu | Consultant | Agronomy |  | 20 |
| Jeroen Groot | WUR | Farming Systems | Farming systems analyses and impact assessment |  |
| Carlo Azzarri | IFPRI | Ag Economist |  |  |
| Gundula Fischer | IITA | Gender | Gender analysis |  |
| Bekele Kotu | IITA | Ag Economist | Economic validation of technologies |  |

Note: More research members are given at thematic level

# Summary

This is a 2014-16 refreshed proposal that is updating activities which have been informed by progress observed during 2014-15. The Research Team has identified technologies under the different themes that are ready for delivery to scale and identified gaps to be addressed in order to mature those that are feasible to be concluded during the remaining cropping season. The action sites remain the same as described in the 2014-16 proposal.

Babati Site consolidated budget 2015/16 (USD).

Details are given under each thematic component

| Main budget category | Theme 1 | Theme 2 | Theme 3 | Theme 4 | Theme 5 | Theme 6 |
| --- | --- | --- | --- | --- | --- | --- |
|  | CIAT | ILRI | AVRDC | IITA | CIMMYT | IITA |
| Personnel | 80400 | 31049 | 21000 | embedded | 44000 | 36700 |
| Research | 42280 | 93000 | 44174 | 96500 | 83543 | - |
| Training | 14280 | 24500 | 17176 | 60000 | 35859 | 24900 |
| Other | 6200 | 10000 | - | - | - | - |
| Overheads | 18611 | 8037 | 12187 | - | 12865 | - |
| Totals | 161771 | 166586 | 93537 | 156500 | 175777 | 61600 |
| Cumulative Total | 161771 | 328357 | 421894 | 578394 | 754171 | 815771 |

# Refreshed Thematic Proposals

## Theme 1: Crop Management Efficiency

Adaptation of promising crop management technologies to land and production environments in Babati, Tanzania

1.1 RESAERCH TEAM (Theme leader: Job Kihara, CIAT)

| Name | Gender | Institution | Job title | Discipline | Qualification. | Project role |  | %time |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Job Kihara | Male | CIAT | Scientist | Agronomist | PhD | PI | 17 |  |
| Stephen Lyimo | Male | SARI | Agronomist | Farming systems | MSc | Co-PI | 20 |  |
| Fred Kizito | Male | CIAT | Scientist | Soil Scientist/ Water Resources | PhD | Co-PI | 15 |  |
| Ben Lukuyu | Male | ILRI | Scientist | Animal Nutrition | PhD | Co-PI | 15 |  |
| Jetrida Kyekaka | Female | MAFSCO | DAICO | Horticulturalist | BSc | Field operations | 10 |  |
| TALIRI | Mixed | NARS | Scientists | Multidiscipline | Various | Collaborators | 25 |  |

1.2 SUMMARY

During 2015/16, we will (1) fine-tune manure technologies through assessment of causes of their yield limitation (2) refine N and P recommendations for maize in Babati, and (3) conduct further demonstrations of technologies for improving yields with best bet improved germplasm and pigeon pea intercropping together with fertilizers, including potential for enhancing soil cover. As in the past year, farmers will be exposed to the technologies under demonstrations. In relation to the above activities, we shall assess soil moisture variations in the crop-forage systems and investigate the role of different soil-water conservation measures as mitigation options for nutrient losses through measuring leaching, soil loss through measuring and detecting erosion and runoff. These will be followed up by conducting a landscape level assessment of associated ecosystem responses on impacts of erosion and land degradation on water quality, soil carbon storage and nutrient retention under different crop-forage systems in Babati; we shall then provide feasible scenario-based recommendations for interventions that promote sustainable intensification for crop-livestock systems and guide scaling up efforts.

1.3 RESEARCH JUSTIFICATION

The best bet technology of “improved germplasm with pigeon pea intercropping and inorganic fertilizer” has been tested and demonstrated during the 2012/13 and 2013/14 cropping seasons and is at the uptake and adaptation stage. The follow-up work for 2014/15 was inconclusive due to drought that affected most of the demonstrations. During 2015/16 cropping seasons, selected demonstrations will be continued in order to move this technology further towards the adoption stage. Further, our work over the last 3 years has shown potential to increase yields (reduce yield gaps) through “improved germplasm with pigeon pea intercropping and inorganic fertilizer”. Therefore, 100 farmers will test this best bet practice alongside their current practice and yield improvements and economics benefits assessed. In addition, manure application, first tested in 2013/14 cropping season, did not improve maize yield. The pH of the manure was rather high, as was K content. It requires therefore, that a specific experiment be undertaken with a purposive selection of manure with known best preparation methods (including one common manure) to understand what is needed to increase crop response. Also, and because biophysical characterization work conducted in 2012/13 period identified land degradation as a common occurrence in Babati, provision of additional soil cover through lablab relay-cropped into the best bet technology of “improved germplasms with pigeon pea intercropping and inorganic fertilizer” is proposed. Lablab is already doing well and in Babati offers potential to protect the soil, especially after maize harvest. This also offers an excellent opportunity of forage integration in the mainstream cropping system. In essence, this ushers in new ways of conceptualizing water and nutrient fluxes in a manner that is interdisciplinary, integrative and multi-scalar with particular attention paid to the linkages across scales. The quantification of crop responses to specific nutrients, and identifying appropriate forage options for crop-livestock integrated systems presents an inevitable need to understand systems which present opportunities for enhancing productivity and resource use efficiencies while maintaining environmentally healthy landscapes through sustainable intensification.

1.4 RESEARCH OBJECTIVES

- To fine-tune crop response to combined fertilizer and manure applications

- To test potential of relay-cropping for increased crop and land productivity within the improved germplasm and pigeon pea intercropping with fertilizer application in Babati

- To assess the applicability of tools for site-specific fertilizer recommendations

These objectives relate to the integration, adoption and trade-off framework hypotheses of AR in that they will integrate improved varieties, fertilizers and organic resources within established cropping systems and coupled with considerations of affordability. Further, the technologies are tested in varied soil and climate conditions and lessons can be easily applied to other similar contexts and thus addressing scalability hypothesis.

In addition to the above objectives, there are other NRM related objectives that build on work conducted in 2013-2015 because field monitoring and assessment of these trends helps justify the impact of the various proposed technologies in co-located sites with the crop-fertilizer and the forages work highlighted above and intends to:

- Assess soil moisture variations in crop-forage systems;

- Evaluate the role of proven soil-water conservation measures to mitigate nutrient and soil loss;

- Conduct landscape level assessment of associated ecosystem responses on impacts of erosion and land degradation on water quality, soil carbon storage and nutrient retention under different crop-forage systems in Babati;

- Provide a feasible scenario-based recommendations for interventions that promote sustainable intensification for crop-livestock systems and guide scaling up efforts.

1.6 METHODOLOGY

- Manure demonstration trials

Manure was first integrated in the ISFM trials during 2013/14 cropping season but performed poorly. During 2015/16, the specific trials that were set last year will be repeated in Seloto to test manure from different sources. We will have 4 sets of manure treatments (manure from chairman Seloto, and 3 preferred manure from 3 other farmers within Babati). These will be tested alone (as done by farmers and at a mean rate of 3.5 t/ha) and also in combination with Minjingu-Mazao at recommended rate. A control treatment without fertilization will also be included. Thus, in this manure trial, there will be a total of 9 treatments (Table 1) that will be replicated 3 times. Each manure used will be fully characterized to explain observed responses. The selection will ensure that well prepared manure by farmers within Babati is tested. In addition to this trial, a farmer technology assessment will be undertaken and training on appropriate manure and compost preparation conducted.

Table 1. Treatments in manure trial in Seloto village

| T1 | Control |
| --- | --- |
| T2 | Manure 1 |
| T3 | Manure 2 |
| T4 | Manure 3 |
| T5 | Manure 4 |
| T6 | Manure 1 +Minjingu Mazao |
| T7 | Manure 2 +Minjingu Mazao |
| T8 | Manure 3 +Minjingu Mazao |
| T9 | Manure 4 +Minjingu Mazao |

- Improving soil cover in maize pigeon pea intercropping with Minjingu-mazao

The best bet technology of “improved maize and pigeon pea intercropping with Minjingu-Mazao” requires further refinement to provide more soil cover after the maize is harvested. Soil cover remains a key challenge to soil and water conservation in Babati because most farmers remove all the crop residues after harvesting. Seloto provides an appropriate climate for relay-cropping of lablab at flowering stage of maize. Lablab is well established in Matufa village, but, has not yet been incorporated in the maize-pigeon pea intercropping system. Lablab performs well when planted as forage (in intercropping with napier) and it is important to get it integrated in the common maize-pigeon pea intercropping system of Babati. Lablab planted last year established very well but was destroyed during the excessive drought experienced. Therefore, in 2015/16, the trial of our matured improved maize-pigeon pea intercropping with Minjingu-Mazao will be implemented together with relay cropping of lablab. This will have 4 treatments: control (i.e., the matured technology), control with lablab at half population, with full population, with full population established 3 weeks earlier than in other treatments.

Table 2. Treatment in relay-cropping in Seloto village

| T1 | Best bet technology |
| --- | --- |
| T2 | As T1+lablab at half population relay-cropped at 10 weeks after planting |
| T3 | As T1+lablab at full population relay-cropped at 10 weeks after planting |
| T4 | As T1+lablab at full population relay-cropped at 7 weeks after planting |

Using the manure demonstration trials and the relay-cropping trials for the crop management work package, we shall conduct tied-ridges as a proven technology for soil-water conservation. Soil moisture variation (measured with diviner 2000 probes), nutrient losses (measured with suction lysimeters) and erosion, soil losses (estimated using overland flow runoff detectors which can be measured with non-recording overland flow detectors made of aluminum cubes (15cm by 15cm)).

The relay-cropping trial in Seloto serves as an ideal case where NRM, crop and forage integration will be brought to the fore and test these feasibility of the associated technologies. Overland flow detectors will be monitored following rain events to determine the presence or absence of runoff. Runoff water samples will be collected from the detectors and analyzed for NO3-. The soils in these trials will also be characterized for pH, texture, water holding capacity, bulk density, CEC, and C & N contents. The quantities and quality of the applied manure will be recorded on a regular basis. In addition, tension lysimeters constructed by attaching ceramic cups (Soil Moisture Corp., Goleta, CA) to a 1-1/4inch diameter polyvinyl chloride (PVC) pipe tube sealed at the end with a rubber stopper will be installed in pairs, one at 50cm and the other at 100cm depth and placed at upper, mid and lower slopes of the farm. One lysimeter pair will be installed at each distance. Leachate samples will be collected regularly throughout the growing season for measurement of NO3- levels.

In collaboration with the work on forages, we shall assess root depths and canopy characteristics of the different forage species at plot level while measuring soil moisture variations. This will then be scaled up to landscape level through scenario generation on forage land use changes and their associated fluxes i.e. runoff, sediment and water quality. In addition, we shall evaluate the influence of topography (different slope categories) on the fluxes e.g. sloping lands vs flat areas in order to provide a suite of case-specific intervention options for the crop-forage intensification with different slope categories in Babati.

- Selected continuation and exposure of best-bet ISFM to farmers

Demonstrations of farmer-preferred maize varieties using best-bet ISFM practices (i.e., variety trials) will be continued in 4 villages where this system is most preferred (Long, Seloto, Sabilo and Hallu) and will involve 2 demonstrations per village). This is at the uptake and the adaptation stage in the research to uptake trajectory. Two farmer field days and farmer technology assessments will be conducted to sensitize farmers further on this technology. Unlike in previous years, two improved maize varieties (those that performed best in the just ended season) identified for best performance (priority ones being PAN691 and SC 627 in “Long” and SC627 and Pioneer 3253 in the other villages will be used in the demonstrations. Each maize variety will be intercropped with the improved pigeon pea variety Mali (a long maturing variety) at the inter-row spacing recommended for each agro-ecozone. The fertilizer treatments/sources are as in previous season, namely: 1) Minjingu Mazao in intercropped system, 2) Minjingu Phosphate Rock (Minjingu Granular) with maize pigeon peas intercropping; 3) Di-Ammonium Phosphate, DAP (18%N, 20%P, 0%K); 4) 3t FYM/ha (quite affordable by many farmers in Babati) + Minjingu Mazao; and 5) 6t FYM/ha alone (option for farmers with more manure). The P rates applied from each fertilizer source will be 20kg/ha at planting. A total of 60kg N/ha (with supplementation from Urea) will be the target for all the fertilizer treatments. The plot size for each treatment will be 7m x 7m.  In addition, 100 farmers will test a sub-set of this matured technology against their local practice. A student from Makerere University will be engaged in this and other uptake/adaptation activities to provide further understanding of the constraints and potential challenges that need to be addressed.

The fertilizer trials (called response trials conducted in 2014/15 cropping season and which are at the research stage in the trajectory) have shown a lot of variability in responses to fertilizers across the fields in Babati so far, with some fields not responding at all and others responding highly. A selection of the N and P response trials will be continued (2 farmer fields in each of the 4 villages) to refine the responses in those responsive fields. There is no need to fine-tune responses in non-responsive fertile fields.

Table 3. Number and fields to be continued in 2015/6 according to the set-up of the previous season

| Components\village | Long | Seloto | Sabilo | Hallu |
| --- | --- | --- | --- | --- |
| Trial type 1 | 2 (Lulu and Hillary) | 2 (Rosalia & Sisti) | 2 (Zadakiya, Stanslaus) | 2 (Simon, Tumaini and Quawanga) |
| Trial type 2 | 2 (Lulu and Hillary) | 2 (Rosalia & Sisti) | 2 (Zadakiya Pombo, Nicodemus Stanslaus) | 2 (Simon and Benjemin Quawanga) |

The associated NRM field measurements will include the assessment of crop-forage system impacts on water and nutrient fluxes through measuring erosion, leaching and runoff to waterways. To address this objective which contributes to managing crops and livestock production at landscape levels of representative farms currently being used for crop productivity trials and for improved forages will be used as monitoring test beds. These farms are located in Seloto, Long, Sabillo and Hallu as exemplified in Table 3 above.

- Participatory economic and gender analyses

A participatory assessment of fertilizer technologies by 25-30 farmers categorized by gender (males, females and youths) will be undertaken in each of 2 villages where field days will be conducted during 2015/16 period. Further, partial budget analysis, sensitivity analysis and benefit cost ratios will be conducted with farmers.

- Modeling and Scaling

We intend to use the APEX (Agricultural Policy Extender) Module within SWAT to inform on smaller scale processes which will in turn help in predicting larger scale nutrient dynamics in the Babati landscape, including N-loading in adjoining water bodies as a result of fertilization and integration of improved forages under different land cover types. Data captured from the different crop and forage systems will form the basis for parameterization of the Soil and Water Assessment Tool (SWAT) modeling platform.

Land use/remote sensing-derived maps (used as inputs for SWAT) will be used to determine spatial patterns from specific areas for measurements of stream water quality based on delineations of predominant landscape level activities. This will cover, for example downstream of irrigation areas, grazing lands, high intensity cropping lands and forested areas. Samples will be collected at monthly intervals over the whole year to capture temporal patterns in the cropping calendar and the associated activities. The samples will be analyzed for silt, N load, and common chemical residues. This activity will thus involve acquisition and analysis of freely available remote-sensing images to derive up to-date land use maps, data collection in the specified locations which serve as pre-requisites for the landscape level water, nutrient and soil flow modeling. This modeling component will also integrate the spatially-defined management data such as the manure application on farmer-fields as captured in the agronomic survey conducted by WP1 previously (and what will be collected this year). We will also utilize rainfall data being collected in the different villages to relate rainfall with erosion prevalence.

In addition, we shall conduct linkage analyses of the modeled results that relate the farm level to landscape scale interactions. The fluxes from water movement induce surface runoff, sediment movement and deposition from upslope areas to the subsequent downslope regions (will be quantified by the modeling). In addition, conceptual interventions are proposed (based on scenario outcomes from the modeling) that relate to crop-water-livestock interactions from the farm level to landscape scale. Critical to this process, both biophysical and socioeconomic scales need to be matched for effective uptake and impact. Vertical scaling-up through the extension of ideas and management processes across stakeholder groups (through community level meetings to discuss perceptions) and institutions, as well as policy makers to private sector interests will be explored in coordination with the other work packages. Ideally, this will take place through the field days in a simplified visual mode that communicates informative messages. This will be complemented by biophysical-socioeconomic tools (InVEST and RIOS) that incorporate landscape process with stakeholder preferences.

- Sustainable intensification indicators

In addition to production and economics data which we are assessing, additional data on consequences of intensification on environment, human/nutrition and social aspects will be gathered. This will be done through a questionnaire survey but also through specific analyses such as grain quality. In this regard, the sustainable intensification indicators household questionnaire developed by IFPRI will be filled for 30 farmers that the theme will be working with.

- Training, communication and dissemination strategies

During the 2015/16 period, 10 extension personnel will be trained on trial design and data collection for key variables, fertility management, optimum spacing and fertilizer application. Another 10 extension personnel will be trained on role and measurement of environmental services while also a training of trainers for 15 extension staff, agro-dealers and representatives of farmer groups to access market information (e-soko) will be undertaken.

Besides capacity building among extension and farmers in Babati, results of the research will be presented in scientific forums and published in peer reviewed journals. Extension materials will also be prepared in collaboration with other partners working on the same theme in the district. During 2015/16, this will include development and communication to 1500 farmers of leaflets targeting manure quality improvement and benefits of P fertilizers microdosing.

1.7  FtF INDICATOR TARGETS

| Indicator / Disaggregation | 2016 |
| --- | --- |
|  | Target |
| 4.5.2(2):Number of hectares under improved technologies or management practices as a result of USG assistance (RIA) (WOG) | 40 |
| Technology type |  |
| soil-related | 40 |
| Sex |  |
| Male | 30 |
| Female | 10 |
| 4.5.2(5):Number of farmers and others who have applied new technologies or management practices as a result of USG assistance (RIA) (WOG) | 400 |
| New/Continuing |  |
| New | 300 |
| Continuing | 100 |
| Disaggregates Not Available |  |
| Sex |  |
| Male |  |
| Female |  |
| Disaggregates Not Available |  |
| 4.5.2(7):Number of individuals who have received USG supported short-term agricultural sector productivity or food security training (RIA) (WOG) | 700 |
| Type of individual |  |
| Producers | 700 |
| Sex |  |
| Male | 500 |
| Female | 200 |

1.8 BUDGET (USD) FOR 2015/16

| Description | CIAT | Selian | Total |
| --- | --- | --- | --- |
| A. Staff time |  |  |  |
| Scientists | 52,500 | 15,000 | 67,500 |
| Field allowances | 10,700 | 6,200 | 16,900 |
| Sub-total | 63,200 | 21,200 | 84,400 |
| B. Other direct costs |  |  |  |
| Travel/motor vehicle use/hire | 11,000 | 6,200 | 17,200 |
| Plant and soil processing & shipping | 800 |  | 800 |
| Plant and soil analyses | 2,100 | 500 | 2,600 |
| Supplies and communication | 6,200 | 2,000 | 8,200 |
| Field monitoring, characterization and equipment maintenance | 9,000 | 3,000 | 12,000 |
| Scaling up and field days | 4000 | 5,000 | 9,000 |
| Sub-total | 33,100 | 16,700 | 49,800 |
| Research and Technical support (RTS) Sub-total | 8,960 |  | 8,960 |
| Sub-total | 105,260 | 37,900 | 143,160 |
| C. Indirect costs (Sum of overhead at 13%) | 13,684 | 4,927 | 18,611 |
| D. Total direct and indirect costs | 118,944 | 42,827 | 161,771 |

  - ACTIVITY SCHEDULE 2015- 2016

1.10 PROJECT ACTIVITY PLAN 2015-2016 (THEME 1; TEAM BABATI)

| Target Outputs (ESA Logframe) | Activity (Technology, tool…) | Activity description | Deliverables (end product on/technology) | Responsible Person and Institution |
| --- | --- | --- | --- | --- |
| Output 3: Potential impact of various SI technologies in different development stages assessed | 1.1 Maize/Pigeon pea intercropping with P microdosing | To evaluate the effect of P fertilizer applied to maize alone or to both maize and pigeon pea in 4 fields | Grain yield and other benefits associated with P fertilizer targeting determined | SARI and CIAT |
|  | 1.2 Maize/Pigeon pea intercropping with P microdosing | Testing of maize and legume performance with different sources of FYM in 3 fields | Different sources of manure characterized; Yield from different sources of manure determined | CIAT and SARI |
|  | 1.3 Relay cropping with Lablab in maize/pigeon pea intercropping with P microdosing | Testing role of lablab in provision of environmental services and productivity within maize and legume system in 3 fields | Tradeoff between lablab and pigeon peas understood | CIAT and SARI |
|  | 1.4 Maize/Pigeon pea intercropping with P microdosing | Further evaluation of different P sources in 8 farmer fields | Preferred P sources that are economically proven demonstrated | SARI and CIAT |
|  | 1.5 Maize/Pigeon pea intercropping with P microdosing | Further testing of N and P application rates and determination of economic evaluation | Nutrient management recommendations for N and P based on soil and crop responses and profitability assessments refined | CIAT and SARI |
|  | 1.6. Maize/pigeon pea intercropping with P microdosing | Assess effects of nutrient management on nitrogen leaching | Calibrated functional models that showcase water and nutrient processes from farm scale to landscape produced | CIAT and SARI |
|  | 1.7 Napier/desmodium intercropping | Investigate the role of different soil-water conservation measures as mitigation options for nutrient losses through measuring leaching, soil loss through measuring and detecting erosion and runoff | Validated options for integration of soil and water conservation practices in cropping systems produced | CIAT and SARI |
|  | 1.8 Improved crop-forage systems | conducting landscape level assessment of associated ecosystem responses on impacts of erosion and land degradation on water quality, soil carbon storage and nutrient retention under different crop-forage systems | Landscape level GIS maps of scenario-based recommendations for interventions that promote sustainable intensification and guide scaling up efforts provided | CIAT and SARI |
| Output 8: Innovations that address emerging agricultural production challenges deployed | 1.1 Capacity building | Training of 10 extension personnel in trial design and data collection for key variables, fertility management, optimum spacing and fertilizer application | 10 extension personnel training in trial design, agronomic data collection, fertility management, spacing, fertilizer application | CIAT and SARI |
|  | 1.2 Capacity building | Training of trainers for 15 extension personnel, agro-dealers and representatives of farmer groups to access market information (e-soko) | 15 extension personnel, agro-dealers and representatives of farmer groups using e-soko to access market information | SARI and CIAT |
|  | 1.3 Capacity Building | Training of 10 extension personnel on role and measurement of environmental services | 10 extension personnel trained on role and measurement of environmental services | CIAT (FRED) |
| Output 9: Scaling approaches for targeted integrated innovations identified and piloted | 1.1. Field days | Field day conducted in each of 2 villages to increase awareness of fertilizer and FYM utilization | 300 farmers (30-40% females, 15-20% youth) exposed to technologies involving fertilizer and FYM use and best practices | SARI and CIAT |
|  | 1.2 Farmer technology assessment/evaluation | Participatory assessment of fertilizer technologies by 25-30 farmers categorised by gender (males, females and youths) | Farmer's criteria for preference identified | SARI, CIAT and IITA |

|  | 1.3 Participatory economic assessment | Conduct partial budget analysis, sensitivity analysis and benefit cost ratios with farmers | Net benefits, sensitivity analyses and BCR determined for different fertilizers in four villages | Bekele (IITA) |
| --- | --- | --- | --- | --- |
|  | 1.3 Communication materials | Development of communication materials | 2 leaflets targeting manure quality improvement and benefits of P fertilizers microdosing developed and communicated to 1500 farmers | SARI and CIAT |
|  | 1.3. Uptake of fertilizer technology by farmers | Conduct survey to determine adoption of the technologies | No. of farmers (by gender) who adopt technology identified | CIAT and SARI |

## Theme 2. Integrated Livestock Feed (ILF)

Fodder and feed as a key opportunity for driving sustainable intensification of crop-livestock systems in Tanzania

2.1 RESEARCH TEAM (Theme leader: Ben Lukuyu, (ILRI)

| Name | Gender | Institution | Job title | Discipline | Qualification | Projectrole | % time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Peter Thorne | Male | ILRI | Principal Scientist | Livestock scientist | PhD | ILRI, Africa RISING Coordinator | 2 |
| Ben Lukuyu | Male | ILRI | Scientist | Animal Nutrition | PhD | Lead Scientist | 40 |
| Leonard Marwa | Male | ILRI | PhD Student | Research Methods | MSc | PhD Student & Field coordinator | 100 |
| Gregory Sikumba | Male | ILRI | PhD Student | Animal Nutrition and production | MSc | PhD student | 20 |
| Alphonce Haule | Male | ILRI | MSc. Student | Tropical Animal Production | BSc | MSc Student | 100 |
| N.N. | Mixed | TALIRI –Kilimanjaro West | Scientists | Multidiscipline | Various | Collaborators | 20 |
| Bekele Hundie Kotu | Male | IITA | AgriculturalEconomist | Agricultural Economics | PhD | Economic analysis | 5 |

  - SUMMARY

This proposal focuses on forages and feed as a key opportunity for driving sustainable intensification of crop livestock systems in Tanzania. In 2013-2014, the livestock component was divided into two work packages (i) Screening and integrating forages in systems and improved use of crop residues and (i) developing feeds for indigenous poultry from local feed resources. In 2014-2015, the two work packages have been merged into an integrated livestock feeds component (ILF) to enhance integration. This component is designed to have three sub components as follows:

- The first sub component revolves around screening forages, testing them with farmers and integrating them into existing farming systems.

- The second sub component is enhanced integration of crop residues in smallholder farms through improved storage, processing and utilization for ruminants.

- The third sub component is concerned with improved management and feeding strategies with emphasis on utilization of local feed resources for indigenous poultry.

Our activities from 2012-2014 have focused on generating research outputs i.e. improved forage species. By 2014 a number of the outputs are ready for use by farmers. In 2014-2015, the proposal sought to disseminate and promote promising forage species and varieties. The proposal also sort to continue with both on station forage screening and participatory action with farmers’ to mature technologies that are still under research such as more forage options, feed choppers, rations for poultry and ruminants; and also to initiate integration activities on selected farms.   It is hoped that the integrated livestock feed activities for 2014-2015 will contribute immensely towards intensification mixed crop-livestock systems in Babati district through improved feed supply and land management hence increased milk production and reduced environmental degradation. In 2015-2016, we aim to mature the technologies, determine their economic implications and gender analysis, develops business models around some of them and package them for dissemination.

  - JUSTIFICATION

Livestock has a multiple potential to enhance the sustainable intensification in mixed crop-livestock systems while mitigating climate change and reversing environmental degradation. A problem diagnosis at the inception of the project using the FEAST tool clearly identified three main livestock constraints in Babati district (Sikumba et al. 2014). The included (i) absence of improved forages which is aggravated by lack of information about forages and feeds in generals. (ii) Abundance of crop residues (14% of the total feed diet) available during harvested season are poorly stored, utilized and go to waste. (iii) There is no supplementation using balanced diets despite the abundance of locally available feed resources such as legume and cereal by products due to crop production dominance in the system. These problems are exuberated by strong seasonal feed variations that result into farmers meeting about 55% of their feed needs under the best conditions. Our livestock component designed interventions in 2013-2014 to (i) integrate improved forages into smallholder crop-livestock systems as a land management/feed strategy and enhance processing and utilization of crop residues (previously work package 3) and to also improve utilization of locally available feed resources to enhance productivity of indigenous chicken (previously work package 8).Beginning 2014, we integrated activities of the two former work packages into one proposal while clearly defining activities and matching them to our major outputs.

Forages

The year 2012-2013 was committed to on-station screening of selected forages based on expert analysis of their biophysical characteristics match to agro ecological zones. Clear ‘best bet’ forages emerged from this study including ILRI 16835 and Kakamega 2 that yield 10 and 20 kg DM per acre respectively. The rest of the varieties ILRI 16803,ILRI 16837,ILRI 14984 and Kakamega 1 recorded average yields 7-10 kg DM per acre. Given these results a decision was made to test all the Napier grass varieties with farmers in 2013-2014. In addition, two outstanding varieties of herbaceous legumes (Desmodium uncinatum and Lablab perpureum) and fodder trees and shrubs Leucaena pallida and Leucaena diversifolia were also selected for on-farm testing.

In the 2013-2014 on farm testing, intercropping trials of maize – desmodium or lablab intercrops, Napier grass - desmodium or lablab intercrops and their controls were set up on selected farms in study sites. Fodder trees and shrubs were planted on trials across the gradient in all experimental plots. The trials demonstrated clear benefits in terms of biomass quantity and quality at varying levels in different agro ecological zones (AEZs). In long, Kakamega 2 and ILRI 16835 were identified as best bests, in Sabilo, Kakamega 2 and ILRI 16837, In Long all varieties were suitable as best bets except ILRI 16803. Meaning farmers have a variety of Napier grass variety options to choose from depending on their needs. We hypothesize positive benefits in the ongoing measurements of soil characteristics study. The lessons and feedback from the trials showed that we have a limited choice of herbaceous legumes given the diversity in the farming systems and farm typologies. Although we demonstrated potential benefits of Napier grasses there was necessity to extend this screening to other grass types. In 2014-2015 we identified two more hybrid varieties with high potential for all study sites. Overall, the need to integrate forages and demonstrate benefits at farm level continues to be our next focus.

Crop residues

The livestock component aims to improve the storage, processing and utilization of crop residue strategies of farmers in Babati district. In order to achieve this, an MSc. student is assessing types, quantity, quality, post-harvest handling and use of crop residues and other local feed resources for livestock in Babati district. The study is currently ongoing. The information obtained will enable formulated of total mixed rations (TMR) for livestock in Babati in 2015-2016. To improve on crop residue utilization, the component fabricated three feed choppers (manual, diesel and electric) for testing with farmers. The testing will cover both efficiency of processing and effect on feed quality as well as the efficiency of the machines themselves with a view of developing a feed processing model as well as using the machine to enhance the TMR concept (feed quality).

Indigenous poultry

Finally, the livestock component aims to integrate indigenous chickens in mixed crop-livestock farming systems through improved management and use of local feed resources. The ongoing doctoral study has already evaluated types and quality of local feed resources. The key findings show that more than 90% of chicken are left to scavenge while there is abundant cheap by products – cereals, legumes, and vegetables etc. that are not efficiently used to feed indigenous chickens. The most used energy feed ingredients include maize grain, maize bran, sorghum grain, rice and rice polish. While the commonly used protein source ingredients were sunflower seed cake, blood and fish meals. Other locally found potential chicken feed ingredients found in Babati but not used by farmers are pigeon pea, leucaena leaf meal, moringa leaf meal, Lablab purpureus and soya bean.  Most of the available local feeds especially cereals are spoilt and of poor quality and will require post-harvest handling strategies before being in cooperated into the livestock feed chain. Our focus for 2015/16 will include formulating indigenous chicken rations based on locally available feed resources, developing strategies to process and handle these feed resources post-harvest and testing with farmers.

2.4 REQUIREMENTS TO MATURE TECHNOLOGIES

Activity 1: Forages

The forage varieties suitable for various agro ecological zones were selected in 2013-2014. The strategies for 2015-2016 are as follows:

In the current study sites (Sabilo, Long and Matufa) where activities are ongoing, the focus will be to integrate the forages in existing farming systems on 9 farms representing 3 different farm typologies. This will include on-farm forage trials (more forage options - inclusive of new CIAT material) + different treatments (monocrop, intercrop, different input levels etc.) The aim will be to show case ‘best bet’ Napier grass and legume varieties along with proven fertilizer and maize technologies on one farm in an integrated manner.

Specific activities will include:

- Conduct participatory cost and benefit /gender analysis of improved forages

- Establishing seed multiplication plots for 'best bet' varieties in new sites

- Train farmers in seedling production and handling of vegetative planting materials for new technologies.

- Capacity development around forage production and utilization

- Develop and test a model on how to use forage choppers amongst farmers as a business.

The outputs from these activities should clearly define potential ‘best bet’ forages or combinations of forages for different ecologies and recommendations on how these could be integrated with other improved technologies into existing framing systems of Babati district . As a result, 2015-2016, will be committed to scaling up and out packaging of these technologies and promoting them through the across stakeholder groups (through village level meetings to discuss uptake) and institutions, policy makers, private in coordination with the other relevant work packages. The channels of dissemination will include field days, R4D platforms and planned meeting with all stakeholders.

Activity 2 and 3.Crop residues

An ongoing study will provide knowledge on the available types of crop residues and their estimated quantities in the system. This study is being conducted as part of an MSc thesis. Forage choppers and a stover baler were fabricated locally in collaboration with a government training institute - CARMATEC and tested on farm during farm visits of project stakeholders. In 2014-2015, the focus was on:

- Refining the machines together with fabricators and do more on farm testing with farmers

- Determining the economics, affordability and effect on forage quality and use of forages choppers and baler.

- Formulating total mixed rations based on locally available crop residues for cattle and determine their quality

- Determining the performance of these rations with cattle on three farms in three villages.

- Determining the cost and benefits of these rations

These technologies will be promoted in 2015-2016 through field days, R4D platforms and planned meeting with all stakeholders. In addition, we expect to generate an MSc thesis and a journal paper from this work.

Activity 4: Indigenous poultry

The focus for 2014-2015 was to:

- Formulate total mixed ratios based on locally available feed resources based on nutritional requirements of indigenous chickens.

- Determine the effects of supplementation with these rations on growth and egg production in the free-range systems of Babati district.

- Determine the cost and benefits of these rations

- Develop packages for enhancing knowledge of the promising feed ration options

These activities will enable us to mature one technology and develop an indigenous chicken feeding package that will be ready for promotion in 2015-2016.We shall also produce an indigenous chicken feeding package pamphlet and train extension personnel. In addition, we expect to generate a PhD thesis and a journal paper from this work.

  - LOGICAL FRAMEWORK

| Narrative summary (Outputs) | Objectively verifiable indicator (OVI) | Means of verification (MOV) | Lead Institutions |
| --- | --- | --- | --- |
| 2.2 Appropriate feed conservation methods for forages and crop residues developed | - A crop residue (CR) baler tested and evaluated with farmers and recommendation for use produced. - Cost benefits of CR baler determined and reported - Feed conservation strategies evaluated | - Report on improved baling for crop residues produced. - Benefits and economic of baler disseminated through a leaflet on use. - A report on potential use of different feed conservation methods produced. - At least 50 farmers trained | ILRI, TALIRI West Kilimanjaro and Government extension |
| 2.3 Balanced rations for ruminants | - Study to determine available types of crop residues and their estimated quantities in the system completed. - At least two total mixed rations formulated for different classes of cattle and tested on a least 6 farms. - Cost and benefits of balanced rations for ruminants determined and reported | - A report on balanced rations for ruminants based on local feed resources produced. - Leaflet on ruminant ration balancing produced |  |
| 2.5 Balanced rations for indigenous chickens | - At least two total mixed rations formulated for different classes of cattle and tested on a least 6 farms. - Cost and benefits of balanced rations for indigenous chickens determined and reported | - A report on balanced rations for indigenous chickens based on local feed resources produced. - Leaflet on indigenous chickens ration balancing produced |  |
| 2.6 Appropriate feed processing machines developed | - Three types of feed choppers tested and evaluated with farmers and recommendation for use produced. - Cost benefits of choppers determined and reported | - Report on improved feed choppers produced. - Benefits and economic of the choppers disseminated through a leaflet on use. |  |
| 2.7 Indigenous chicken production systems and their constraints defined | - Factors hindering development of indigenous chickens identified | - A report indigenous chicken production systems and their constraints |  |
| 3.2 High yielding forage species for different AEZ’s | - In existing sites, showcase the integration of forages into existing systems in different AEZs and along with other proven technologies - In new sites, at least two high yielding forage varieties under Babati conditions identified and reported by September 2015. | - A report on the integration of forages into existing systems produced - A report on new high yielding forage options in new sites identified. |  |
| 4.1 Best bet forage species and varieties economically evaluated | - The costs and benefits of all forages under test determined | (i) A report on the costs and benefits of all introduced forages |  |
| 4.6. Cost benefit of rations for ruminants and chicken | - The costs and benefits of all formulated rations for ruminants and chicken determined | (i) A report on the costs and benefits of all formulated rations for ruminants and chicken |  |
| 5.2. Capacity building for all technologies for farmers and extension staff | - A package for enhancing knowledge on ruminant ration balancing produced - A package for enhancing knowledge on indigenous chickens ration balancing produced - A leaflet on utilization of crop residues disseminated. | - At least 50 farmers trained on use of crop residue baler - At least 50 farmers trained on use of feed choppers - At least 50 farmers trained on the importance of ruminant ration balancing and feed supplementation - At least 50 farmers trained on the importance of indigenous chickens ration balancing and feed supplementation - At least 50 farmers trained on forage production |  |
| 6.5 Scaling up of screened promising forage species and varieties | - Planting material disseminated to farmers in the three villages where bulking sites were set up. | - Planting materials distributed to at least 50 farmers |  |

  - ACTIVITY SHEDULE FOR 2015/16

A broad outline of activities for mature technologies in 2015/16 is summarized below.

| Sub component | Activity |
| --- | --- |
| Forages | - Developing a package of integration of forages into existing systems - Scaling up of screened promising forage species and varieties - Capacity building for forage production for farmers and extension staff |
| Crop residues | - Scale out a package on crop residue based ration formulation through participatory action research to generate evidence for follow up dissemination activities. - Capacity building for crop residue utilization for farmers and extension staff |
| Enhanced feeding of indigenous chickens | - Scale out a package on crop residue based ration formulation through participatory action research to generate evidence for follow up dissemination activities. - Capacity building for crop residue utilization for farmers and extension staff |
| Collect data for initial definition of SI indicators | - A structured survey in study sites |

  - BUDGET DETAILS

2.8 FtF PROJECTED INDICATORS 2015/16

| Indicator / Disaggregation | 2015/16 |
| --- | --- |
|  | Target |
| 4.5.2(2): Number of hectares under improved technologies or management practices as a result of USG assistance (RIA) (WOG) | 50 |
| climate mitigation or adaptation | 50 |
| 4.5.2(5): Number of farmers and others who have applied new technologies or management practices as a result of USG assistance (RIA) (WOG) | 1550 |
| New/Continuing |  |
| New | 1500 |
| Continuing | 50 |
| Disaggregates Not Available |  |
| Sex |  |
| Male | 550 |
| Female | 1000 |
| Disaggregates Not Available |  |
| 4.5.2(7): Number of individuals who have received USG supported short-term agricultural sector productivity or food security training (RIA) (WOG) | 1265 |
| Type of individual |  |
| Producers | 1243 |
| People in government | 22 |
| Sex |  |
| Male | 595 |
| Female | 670 |
| Disaggregates Not Available |  |
| 4.5.2(11): Number of food security private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) receiving USG assistance (RIA) (WOG) | 7 |
| Type of organization |  |
| Producers organizations | 7 |
| New/Continuing |  |
| New | 5 |
| Continuing | 2 |
| Disaggregates Not Available |  |
| 4.5.2(12): Number of public-private partnerships formed as a result of FTF assistance (S) | 3 |
| Agricultural production | 1 |
| Agricultural post harvest transformation | 2 |
| 4.5.2(39): Number of new technologies or management practices in one of the following phases of development: (Phase I/II/III) (S) |  |
| Phase 1 Number of new technologies or management practices under research as a result of USG assistance | 8 |
| Phase 2 Number of new technologies or management practices under field testing as a result of USG assistance | 15 |
| Phase 3 Number of new technologies or management practices made available for transfer as a result of USG assistance | 20 |
| Disaggregates Not Available |  |
| 4.5.2(42): (4.5.2-28) Number of private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) that applied new technologies or management practicies as a result of USG assistance (RIA) (WOG) | 4 |
| Type of organization |  |
| Private enterprises (for profit) | 2 |
| Producers organizations | 2 |
| New/Continuing |  |
| New | 2 |
| Continuing | 2 |
| Disaggregates Not Available |  |

## Theme 3. Integration of vegetables in to maize-based farming systems in Babati

3.1 RESEARCH TEAM (Theme leader: VictorAfari-Sefa, AVRDC)

| Name | Gender | Institution | Disciplinary expertise | Qualification | Project role | % time |
| --- | --- | --- | --- | --- | --- | --- |
| Victor Afari-Sefa | M | AVRDC | Agricultural Economist | PhD | Scientist | 7% |
| Tsvetelina Stoilova | F | AVRDC | Genetic Resources | PhD | Scientist | 3% |
| Inviolate Dominic | F | AVRDC | Horticulturalist | MSc | Research Assistant | 15% |
| Philipo Joseph Lukumay | M | AVRDC | Agricultural Economist | BSc | Research Assistant | 10% |
| Danny Coyne | M | IITA | IPM on vegetables | PhD | Scientist | 5% |
| Mary Maganga | F | IITA | ISFM | MSc | Research Assistant | 10% |
| Aika Aku | F | Egerton University | MSc. Agric. Economics student | MSc candidate | Research student | N/A |
| Mary Aloyce Mtui | F | Egerton University | MSc. Agric. Economics student | MSc candidate | Research student | N/A |
| Selina Nombo | F | Sokoine University | MSc. Agric. Economics student | MSc candidate | Research student | N/A |

3.2 SUMMARY

Nutrition has in recent times captured the international spotlight in an unprecedented way, as persistent global hunger and under-nutrition have underscored the need for urgent action. There is increasing political interest and growing public health awareness and advocacy for diversifying diets with highly nutritious traditional vegetables and fruits and other nutrition-sensitive crops. Traditional African vegetables in particular can make an important contribution to food and nutritional security and can enhance the livelihoods of marginal and smallholder farmers as is currently being demonstrated within the integrated farming systems project of the Africa RISING Eastern and Southern Africa project in Babati, Tanzania. Baseline socioeconomic survey results and subsequent community sensitization efforts and farmer managed on-farm demonstration trials indicated that: (i) elite vegetable varieties, particularly those released from AVRDC’s germplasm, (ii)healthy seedlings, and (iii) good agricultural practices, including integrated crop and pest management compared to business-as-usual (standard) farmer practices enhance production under good agricultural practices and offer an exciting and much promising scope to improve farm productivity and household nutrition. Such demonstration plots have particularly been used as training and learning centers and the means to disseminate the technologies within the four project communities and neighboring locale. Demonstration plot data from the four villages in Babati District shows that farmers increased tomato production from 35.6 t/ha to 58.0 t/ha, African eggplant production from 50.49t/ha to 86.54 t/ha, and amaranth production from 51.5 t/ha to 72.2 t/ha. Results from the Dunnet F-test (a post-hoc test, see Appendix 3) show a significant (P < 0.05) increase in tomato and African eggplant yields and profits following the combination of the use of AVRDC good quality elite seeds of improved varieties as healthy seedlings, GAP and integrated pest management, compared to farmers’ normal practices. However, the test shows no significant differences in yields or profit for amaranth between treatments. The data obtained further demonstrates that, on an area of only 12 m2, a household could produce enough vegetables to increase household consumption to meet the daily per capita recommended requirement of 200 g/person/day. In addition, increased vegetable production in the four villages in Babati District generated an income for the household of 59.4 USD/season from tomato, 21.04 USD/season from African eggplant and 8.28 USD/season from amaranth. A second set of farmer-managed field demonstrations (with increased farmer resource use and control as compared to the 2 previous project years) was implemented in each of the four villages in the Babati district in October 2014 and is being monitored for the 2014-2015 production season to provide the needed second set of data for cost-benefit analysis of good agricultural practices to enhance production. Results will be made available in the last quarter of 2015. In addition to and in line with Africa RISING Research objective 3, three additional vegetable crops, namely, Sweet pepper (Yolo Wonder), African nightshade (Nduruma) Ethiopian mustard (Rungwe) and one additional variety of Amaranth (Madiira I) have been introduced as part of the scaling out strategy requirements of the program to the over 209 current direct beneficiaries and several other non-direct beneficiaries in this research theme of the program.

Additional flagship technologies introduced to the initial three earlier enumerated, two additional flagship technologies have been introduced viz, mobile garden technology to enhance household consumption and vegetable poultry integration, both of which encourage the use of low-input and easily available household resources. In the 2015-2016, emphasis will be placed on a participatory outcome evaluation of a 5 technologies on smallholder livelihoods and inclusion of 2 additional flagship technologies (community healthy seedling establishment and affordable water harvesting technologies) with possible inclusion of vegetable-rabbit integration on a pilot basis, given anecdotal evidence of likely promise for increased and diversified income and enhanced nutrition for beneficiary households.

Finally, the agronomic, profitability and food safety aspects of the vegetable integration and diversification into existing farming systems will be further investigated. In addition, efforts in the 2015-2016 production seasons will focus on postharvest training of benefiting farmers, integration of vegetables in combination with poultry production, as well as water use optimization management practices and harvesting, particularly in communities that are not well endowed with irrigation facilities as part of the scaling up technologies to benefit at least 200 additional farmers.

3.3 RESEARCH HYPOTHESIS

The research theme is based on the premise that increased consumption of elite and improved vegetable varieties, produced using improved and safer practices, will contribute to more diverse, healthier and balanced diets while increasing farm household income through higher farm gate values of vegetables accrued from their intercropping or rotation with staple cereals such as maize while enhancing nutrient recycling through integration of activities with poultry improvement technological packages.

3.4 RESEARCH OBJECTIVES

The specific research objectives are to:

- Validate data for already introduced improved varieties of 3 crops (i.e., Tengeru 2010 tomato, Madiira I amaranth and Tengeru white African eggplant). The aim is to validate and disseminate best-bet management packages around the most promising farmer selected new crop varieties suited to semi-arid agro-ecological zones with emphasis on the differential outputs of males and females. In line with the integration hypothesis of the Africa RISING program, this output will contribute to Research Objective 2 (and partially to Objective 3) of the Africa RISING program.

- Introduce and evaluate improved varieties of additional vegetables or species of same crop type in cereal-based farming systems. So far one variety each of Tomato (Tengeru 2010), Amaranthus (Madiira I&II) and African eggplant (Tengeru white) have been selected as preferred farmer alternatives in the four project communities. In the 2014-2015 production season, 3 new crop varieties (i.e., Yolo Wonder Sweet pepper), Nduruma African Nightshade, Rungwe Ethiopian mustard and one additional variety of Amaranth (Madiira I) was introduced in the cereal-based farming systems via demonstration plots under good agricultural practices compared with standard farmer practices. Consequently, we are conversant with the anecdotal evidence of massive adoption from previous project years on individual farms after the first crop harvest in early January 2015. We subsequently intend to following up on this successful progress in early late October and in early 2016 and access in tandem the preferences of males and females in household production and consumption decisions. Consequently, in the 2015-2016 production seasons, emphasis will be placed on validating the yield and cost and return data for both old and newly introduced varieties while exploring opportunities for new varieties of other vegetable to be likely be of interest to farmers in the last quarter of 2015. The purpose is to increase the pool of diverse vegetables that offer enhanced productivity and horticultural traits while conferring resistance to biotic and abiotic stresses as well as cultural acceptability of selected nutrient-dense varieties for enhanced nutrition. This objective will contribute to Research Objectives 1 and 2 of the Africa RISING program.

- Integrated crop and pest management practices& food safety analysis. So far evidence from the pest and disease survey and from assessments conducted on demonstration plots show that themajor vegetable diseases are Early blight, Late blight, Bacterial wilt, Bacterial spots, Tomato yellow leaf curl Virus (TYLCV) and root-knot nematodes. Major insect pests observed in the field were Whiteflies and Leaf minor. Major damage from these diseases were seen on demonstration plots managed by farmers. Field observations consequently, indicate that farmer lack knowledge in pest and disease identification and management frequently apply pesticides, as the incidence of pests and diseases is undoubtedly the major production constraint. Furthermore, limited knowledge of pest and disease identification was shown to lead to improper and incorrect use of pesticides. A critical observation from the baseline survey is that farmers do not use healthy seedlings. Increased awareness of the benefits, therefore, of using healthy seedlings (e.g. through the use of sterilized media for nursing seedlings) was a priority for the farmer-replicated demonstration plots that were set-up during this reporting period. Preliminary results more than support the importance of healthy seedlings to achieve good pest and disease control, ultimately increasing crop productivity as well as quality. Results also demonstrated that the additional use of GAP further improved the benefits of healthy seedlings. A field manual on the identification and management of pests and diseases was produced and translated to the Swahili language by IITA and distributed to extension officers and some lead farmers in the project communities. Further laboratory analysis is still pending from a second round of samples collected for analysis and was validated in the 2014-2015 production season. Results will be made available in late 2015. In addition, detailed integrated crop and pest management (ICPM) recommendations for the various crops will be developed once laboratory analysis has been completed and validated in the 2015-2016 production season. We will continue with field and laboratory diagnosis of diseases and recommend ICPM packages most suited for farmers over the next production seasons. A critical intervention envisaged in this activity, as earlier observed from the previous season, is the production, use and demonstration of healthy seedlings. This needs to be maintained to fully ingratiate farmers to the benefit of using healthy seedlings. It is essential that farmers wishing to take this on board are provided with support and guidance to ensure that their seedling production is of healthy seedlings, and not seedling production of ‘unhealthy’ seedlings. This is a concern given that a number of farmers have shown enthusiasm and taken the initiative to produce seedlings for use and sale, but are not employing the standards required to produce healthy seedlings, such as were used in the demonstrations in the 2013-2014and 2014-2015 production seasons. Failure to oversee and support this will undo any gains made on the use of and awareness of healthy seedlings for beneficiaries. The objective will make a direct contribution to safe and sustainable intensification of mutually beneficial mixed cropping systems (Objectives 1 and 2 of the Africa RISING program) through a participatory problem analysis and intervention strategy development process involving stakeholders and research and development actors. Participatory identification and mapping of pest and disease problems, which are a  critical bottlenecks to vegetable production and marketing for sustainable intensification of horticultural value chains in association with maize in the targeted district, can be realized. At the same time detailed data for outcome evaluation on farmers’ fields in the 2015-2016 production season and ultimately for a project wide impact study the M&E team will be realized through this activity. Results will be used to develop and strengthen key partnerships, responsibilities to deliver a time-bound set of activities, outputs, outcomes and impacts in the subsequent season to increase the adoption, efficiency and safety of vegetable production and consumer access to safer vegetables. Results from the project can subsequently be adapted to other cereal-vegetable based systems within Tanzania and across East and Southern Africa (Africa RISING Research Objectives 2 and 3).

- Market linkages and validated postharvest processing and utilization practices for enhancing produce shelf-life. As part of targeted trainings, male and female farmers will be empowered to enable access to market information through targeted training skills in farm business and entrepreneurship. Particular emphasis will be placed on involving women farmers as technical innovators, resource managers and homemakers and developing their capacity, particularly in the area of postharvest handling and processing. This objective will contribute to Research Objective2 of the Africa RISING program.

- Vegetable-poultry integration and productivity enhancement. Initial trials have been implemented in the 2014-2015 production season, results of which are yet to be reported. The emphasis in this activity will be on optimal combinations of resources aimed at using chicken waste (droppings) to replenish the fertility status of soils cultivated to vegetables while exploring the use of vegetable residue (waste) as poultry feed. This objective will contribute to improving household food and nutrition security via the homestead food production models being tested by several organizations such as Hellen Keller International, among the most vulnerable households but with additional focus on nutrient recycling (with inputs from the natural resource management research theme) and to Research Objective 2 of the Africa RISING program. With a fair balance of male and female farmers already selected for the initial trials, time surveys will be conducted to access the gender division of labour that will arise resulting from diverse interests men and women and this impacts on the dynamics of household production and consumption decisions.

- Water harvesting and management practices: Water access is critical for vegetable production, particularly during the off-season. Research activities will be conducted on efficient water application on crops under standard macro-irrigation practices of farmers. Water harvesting techniques that can be applied during the rainy seasons would be introduced to farmers to enable them to conserve water for use during the dry season. This will include the use of shallow wells as well as sensitization and training on the effective use of water as applied in various micro-irrigation practices used by farmers, such as drip irrigation techniques for deployment on small areas of land. This optimises the use of water. This will contribute to Research Objectives 1 and 2 of the Africa RISING program.

- Promote nutritional education on the need for increased consumption of vegetables: Targeted nutritional promotion campaigns will be conducted aimed at meeting the World Health Organization (WHO)’s daily recommended requirement of 200 g of vegetables per capita per day. Results from the baseline survey study and subsequent interaction with beneficiaries during the community sensitization and the community farmer field days held in the 2013-2014and 2014-2015 production seasons have yield very positive results and undoubtedly suggests the need for additional strong promotional campaigns to make farmers aware of the nutritional importance of increased vegetable consumption, and to promote home gardens as a source of vegetables that can diversify diets for all household members. This will contribute to Research Objective 3 the Africa RISING program.

3.5 METHODOLOGY

This will be an action research, awareness creation and capacity building activity for farmers and Agricultural Extension Agents. Activities will be continued in the villages of Matufa, Seloto, Bermi and Gallapo in the 2015-2016 production season. In this production season, water harvesting and management techniques will for the first time be tested in Long village for possible integration of vegetable-poultry activities under the livestock and feed research theme. We also intend to validate data collected on demonstration trials in the 2014-2015 production season through a repetition of the trials in the 2015-2016 production season at this site to provide additional diversity. In the 2015-2016 production season, demonstration trials will be continue to emphasize inclusion of poultry integration (i.e., use of poultry droppings on the productivity of vegetables and complemented by testing of vegetable residue as poultry feed to be led by the livestock and feed research theme) but more emphasis would be placed on scaling-out of validated results of the demonstration trials on elite vegetable varieties, healthy seedlings, recommended good agricultural practices packages, mobile gardens, vegetable poultry integration, water harvesting and management techniques in the four project communities (and selected spillover ones) in collaboration with other upcoming AVRDC initiatives in the study area and beyond. The following activities are proposed over the 2015-2016 production (project) year.

Pre-season stakeholder meetings with partners and beneficiaries for community mobilization:

Led by AVRDC, the activity will involve providing feedback on lessons learnt from the 2014-2015 season and share planned work for the 2015-2016 production seasons. Efforts will be done to mobilize more women to participate in technology validation and experimentations so as to balance gender involvement in activities, particularly demonstration trials and training programs.

Additional community sensitization efforts and complementing field demonstrations for farmer participatory selection of additional vegetables varieties

In addition to the current seven already selected preferred varieties of tomato, amaranth and Africa eggplant, Sweet pepper, Ethiopian mustard and African nightshade farmers would be encouraged to select additional improved varieties for more resistance to identified pest and diseases so far identified on demonstration plots and farmer fields. This will include diverse varieties of the current 6 vegetable crops (or other vegetable types that may be of further interest, either commercially or for home consumption) on demonstration plots to be set up under activity 1.5.3. As species are selected consideration will be given to the need to incorporate knowledge of managing other crops for better crop rotation practice and use of residue as poultry feed supply. Scaling out of tested and preferred varieties from the 2014-2015 production season will be the main focus in the 2015-2016 production season. This will be undertaken in collaboration with AVRDC’s likely upcoming three-year scaling up intervention on vegetable home gardens as well as the proposed Africa RISING scaling up project. The activity will be led by AVRDC.

Repeat of demonstration trials of preferred and selected varieties of currently introduced vegetable varieties:

As usual best bet practices will be based on use of healthy seedlings and basic improvements in crop production practices which reduce pest and disease incidence and increase production. Demonstration sites will continue to create awareness of these practices, while assessment of their agronomic performance and benefits will be compared with those from standard farmer practice plots as detailed above.

Following earlier community sensitization efforts to create more awareness on the nutritional and economic importance of integrating vegetables into the maize-based farming system in Babati district, workable action plans for the best possible outcomes, building on an existing initiative to reconnect production, marketing and enhance increased consumption of vegetables in project communities with possible spillover effects to and neighboring ones were implemented. As of March, 2015,it was realized that adoption had increased from the initial 71 trained farmers to 209 from the 4 villages. A key element of the GAP packages introduced was the evaluation of the benefit and demonstration of the use of healthy seedlings. At the time of reporting it was estimated that over 900 direct and indirect farmers are currently benefiting from the knowledge transfer from the community sensitization, training and demonstration trials established. Consequently, the demonstration plots for 2014-2015 will be repeated in the 2015-2016 production season for the purpose of obtaining consistent results. Also, in order to test the robustness and sensitivity of the yield and cost and return analysis data obtained from the previous season, crops will be planted in different seasons in order to gain sufficient variation in datasets, given the sensitive and perishable nature of vegetables in response to climate variables.

Pest and disease management:

The 2012-2013 production season scoping studies recorded a high incidence of pests and diseases with farmers reporting wilting, chlorosis, necrosis, viral disfigured leaves and pests as the most prevalent and disturbing diseases in the surveyed regions. Chlorosis was mostly seen in tomato and maize, necrosis was common in African eggplant, amaranth and tomato while maize was rarely affected. Results from our baseline survey on pest and disease incidence indicated that pest and disease incidence contributed to yield reduction by 47.5% for African eggplant, 20.8% for sweet pepper, 19.5% for maize, 18.8% for tomato and 17.1% for amaranth. Results from the 2012-2013 production season’s socio-economic scoping study also indicated that just 40% of vegetable farmers reported having applied pesticides on their vegetable fields, out of which only 17% reported using any protection gear when applying pesticides. Also, the majority of respondents (65%) applied pesticides after recognising the pest symptoms in the vegetable field, while a smaller proportion reported their application at regular intervals during a season (15%) with very few (only 2%) reported pesticide application after field sampling was done. In essence, numerous knowledge gaps in pest and disease awareness and understanding was observed which needed to be addressed in the 2013-14 production season. Results from the pest and disease assessment on demonstration plots from the 2013-2014 production season also revealed poor crop management practices including soil and water management and poor understanding and management of pest and disease infections such as fungal blights, nematodes, viral diseases, thrips, and whiteflies, among others, in farmers’ fields that need to be addressed. A poor awareness of the causes of pest and disease symptoms that farmers observe was found to be related to difficulties in understanding how to manage these, while a poor understanding of pesticides and which ones to use was seen as further accentuating the problems, and indeed creating a separate problem around pesticide use. Results from preliminary harvest data show a tremendous improvement when using healthy seedling treatments compared to farmer-grown (non-healthy) seedlings under farmer standard practice with even more pronounced improvement when healthy seedlings were combined with GAP. Thus, appropriate ICPM of vegetable pests and diseases will reduce the misapplication of pesticides that are harmful to human, animal and environmental health. This can be achieved through interventions that focus on the key pest and diseases that were identified in the surveys in the 2013-2014 production season. While the existing production manual will be distributed to additional extension officers and lead farmers, continued deployment/demonstration of varieties resistant against the prominent constraints and improved agronomic practices to minimize infection, spread and impact of pests and diseases will be conducted for results to be compared, assessed and evaluated. Where pesticides are necessary, guidance will be provided on appropriate products, timing and dose of application (pre- and postharvest). Farmers will also be trained on best use of agricultural inputs, including pesticides, for better management of diseases and pests as well as addressing sanitation issues related to good harvesting practices of vegetables. Appropriate ICPM of vegetable pest and diseases will be finalized and disseminated to reduce the misapplication of pesticides that are harmful to human, animal and environmental health. The activity will be led by IITA.

Cost-benefits analyses on integrated intercropping systems for adaptability tested:

To ensure that introduced technologies are widely adopted by farmers, it is again important to undertake gender disaggregated profitability analysis of the incremental changes in existing practices by farmers so as to compare them to standard farmer practices, particularly for the purpose of obtaining a second round of data and for obtaining results of the 4 new varieties of vegetables introduced in the 2014-2015 production season. Thus, farmers must be able to visualize the economic benefits of the proposed technologies including vegetable-cereal crop intercropping and crop rotation trials. Partial budgeting analysis approaches would be used as usual to assess the economic profitability of promising technologies and cropping options to enhance adoption. Three MSc. students from Egerton and Sokoine University will be undertaking their thesis work in this and related areas by examining how newly introduced vegetable related technologies have contributed to vegetable yield and farmers’ returns vis-à-vis standard farmer practices. In addition, an assessment of the spillover effect of the introduced technological interventions on crop diversity, crop concentration and dietary patterns and gender analysis will be undertaken. The proposed MSc. study is expected to be completed in September 2016. The activity will be led by AVRDC.

Vegetable seedling unit established at community level:

Field observations and results from the demonstration trials set-up in the 2013-2014 and 2014-2015 production seasons show a high demand for seeds (and particularly healthy seedlings) of AVRDC’s elite improved cultivars that were provided to farmers as start-up kits following successful training. In response to the overwhelming demand for elite and healthy cultivars, some farmers had even set up their own nurseries to sell to other farmers. In the 2014-2015 season, it is proposed that a community based nursery system will be established where farmers will be instructed and guided on good agronomic husbandry practices including use of specialized nursery trays using the farmer learning group (FLG) concept already tested and validated by IITA in West Africa. Selected farmers will accordingly be trained in the quality declared seed systems could be formally certified for sale within the project district and applicable agro-climatic zones in accordance with the Tanzania Official Seed Certification Institute (TOSCI). This will require a close collaboration with TOSCI which has already collaborated with AVRDC, CABI, HORTI-Tengeru and other national partners in Central Tanzania. This will also ensure that farmers that will be using own-saved seeds in the subsequent season could be confident of the quality of seeds stored for that purpose. We propose to establish one seedling unit per each project community. Given that this requires a fairly large initial financial investment beyond the scope of the allocated budget, this activity is anticipated to attract collaborative attention from the Tanzanian Agricultural Productivity Program (TAPP) who has indicated interest in the development of such healthy seedling production units. The activity will be led by IITA.

Water harvesting and management practices:

In collaboration with the natural resource management research theme, we will explore options for effective water harvesting in the four vegetable related project communities as well as in Long and Sabilo villages. This would mainly occur in the 2015-2016 production season. Research activities will also be geared towards evaluating water use efficiency of existing farmer micro-irrigation systems for recommended improvements to save water. In addition, efforts will be made to strengthen existing farmer groups and/or facilitate the establishment of new ones as appropriate to improve their bargaining power and access to inputs such as water and credit access as well as coordination of sale of produce to access high-value output markets. This activity will be coordinated by AVRDC but with expected strong inputs from CIAT as well as IITA, funds permitting.

Awareness creation and training in postharvest handling practices:

In the 2013-2014 and 2014-2015 production seasons, efforts and resources were adjusted to place more emphasis on technology transfer via on-farm demonstration plots as we later got a better feeling of how critical this was. Thus training targets for postharvest handling were not fully met as a result and will therefore be continued in the 015-2016 production seasons. Selected beneficiary farmers also benefited from exchange visits to the eminent farmer cooperatives in Lushoto. Through such targeted training programs in the upcoming production seasons, beneficiary farmers will be made to understand the factors which contribute to high postharvest losses in vegetable production and marketing. This will lead to reduced seasonal gluts and shortages and enhance year-round availability of produce for sale and increased home consumption. Training activities will be conducted specifically on postharvest handling of vegetables to enhance produce shelf-life while ensuring year-round availability of vegetables including utilization via training on cooking recipes. To this end special emphasis will be placed on ensuring availability of nutrient dense vegetables for women and children in particular. Emphasis will be placed on involving women farmers as technical innovators, resource managers and homemakers and developing their capacity, particularly in the area of postharvest handling and processing. e.g., introduction of Zero Energy Cool Chamber (including charcoal cooler) and simple solar drying technologies. In addition, beneficiaries will be taught techniques for improving market access of their harvested produce including farmers’ information circulation, storage facilities and packaging. This activity will be led by AVRDC with inputs from IITA.

On-farm integration of vegetables with poultry research theme:

This activity along with a possible vegetable-rabbit integration (a new area proposed)is targeted at enhancing income diversification and improve nutrition outcomes of the project. Treatments on the demonstration trials will include inclusion of poultry droppings as organic manure compared with no application of other organic and non-organic fertilizers and compared with treatments under inorganic fertilizers. In parallel, we will provide inputs and information on the use and evaluation of vegetable residues as poultry and rabbit feed under the livestock and feed research theme and collaborate with them and the natural resource management research theme to evaluate the nutrient recycling pool effects on soil fertility and plant nutrition. This activity will be coordinated by AVRDC but with expected strong inputs from ILRI and IITA.

Community–based mobilization of farmers to access viable and/or functional markets and provision of market information systems:

Results from our baseline and community sensitization efforts indicate a need to encourage the establishment of vegetable farmer organizations, while strengthening existing ones as a vehicle for disseminating identified technologies to achieve larger scale impact. One aspect of this is the continued supply of produce to retail outlets, which can be improved through mobilizing farmer market groups to allow their coordinated produce to meet the demands of large volume regional markets, as well as institutional consumers such as schools, hospitals etc. Beneficiary farmers will also be encouraged to form organized groups to access high-value markets. This objective will contribute to improving household food and nutrition security among the most vulnerable households and their members, especially women and children. This will be done in collaboration with other existing project complementary USAID implementing programs.  The activity will be led by AVRDC.

Anchoring farmer sensitization on vegetable nutritional awareness and promotion for widespread adoption of tested technologies:

Once tested technologies from the demonstration trials have been finally validated, we will undertake strategic community sensitization on the nutritional importance of vegetables and demonstrations for selected vegetables along with promotion of the improved best bet agronomic practices to target beneficiary farmers via the existing project R4D platform, schools and hospital gardens in the project district. This will include a combination of community field days, farmer exchange visits, mass rallies and facilitate seed fairs by private seed companies. This will be a major priority of activities in the 2015-2016 production season. The activity will be led by AVRDC.

3.6 DELIVERABLES

The proposed deliverables under this theme for the 2015-2016 production season are:

- At least three additional adapted elite varieties of selected standard and traditional vegetables (i.e., tomato, African eggplant, amaranth, sweet pepper, African nightshade, Ethiopian mustard and a vegetable legume) identified for integration in maize-based farming systems in the target communities.

- At least 300additional farmers aware of and engaged in additional elite AVRDC vegetable variety evaluation for adaptation in target communities of the study area through community sensitization and dissemination of results of demonstration trials from earlier production seasons.

- Appropriate ICPM of vegetable pests and diseases to realize the opportunity for vegetables to be integrated into existing farming systems disseminated to over 500 farmers.

- At least two community seedling units established within two target project villages followinginitial mobilization, training and set-up. Two community seedling production units fully functional and producing healthy seedlings for project beneficiaries with other communities linked to other potential initiatives such as TAPP.

- At least 150 additional farmers trained in postharvest handling, farm business and entrepreneurship skills that add value to produce while improving shelf-life to reduce seasonal gluts and shortages and enhance year-round availability of produce for sale and home consumption.

- At least one market information and/linkages for farmers to access vegetable markets developed.

- Targeted strategies for testing and validation for increased demand creation and promotion of selected elite vegetable varieties and scaling-up of production technologies within maize-based cropping systems identified for potential next phase of the project.

- At least one best-bet technology for optimizing water harvesting and/or water use efficiency for vegetables identified for subsequent dissemination to beneficiary farmers in a possible next phase of the project.

- At least one best-bet technology for enhanced optimal nutrient recycling of vegetable-poultry integration in the farming system (i.e., vegetable residue waste as feed conservation method for poultry feed and poultry dropping as organic manure)of the project area identified and evaluated (in collaboration with livestock and feed research theme).

- At least two M.Sc. studies on the (i) vegetable poultry integration, (ii) ICPM analysis and policy recommendations completed.

- At least 200 farmers trained in postharvest handling practices and farm business and entrepreneurship skills that add value to produce while improving shelf-life to reduce seasonal gluts and shortages and enhance year-round availability of produce for sale and home consumption.

- Targeted strategies for testing and validation for increased demand creation and promotion of selected elite vegetable varieties and scaling-up of production technologies for increased vegetable consumption within maize-based cropping systems identified for next season.

Effectiveness of technological dissemination approaches for increased demand creation and promotion of selected elite vegetable varieties and scaling-up of production technologies for increased vegetable consumption within maize-based cropping systems evaluated.

  - ACTIVITY SCHEDULE PER ESA LOGFRAME OUTPUT FOR THE 2015-2016 PRODUCTION SEASON

| TIME FRAME | Target Outputs (ESA Logframe) | Activity (Technology, tool…) | Activity description | Deliverables (end product/innovation/technology) | Responsible Person and Institution |
| --- | --- | --- | --- | --- | --- |
| Nov., 2015 | Output 1: Intervention sites identified at an appropriate level, and characterized. | 1.1 Set-up on-farm trials of elite vegetable varieties for agronomic adaptability and consumer taste and preferences | Addition sites (villages) outside the current working community selected and 4 current demonstration sites maintained. •Sensitization meeting on vegetable production, nutritional and economic awareness and promotion for widespread adoption of tested technologies | • Additional 3 communities suitable for vegetable farming within the AR sites in identified and by October 2015 • Sensitization meeting on vegetable, maize and legume integration nutritional and economic benefits based on tested technologies conducted in AR selected sites by November 2015 • Community sensitization and farmer participatory selection reports. | • AVRDC scientist • Subject matter specialists at district, ward and village level • Identified stakeholders working in vegetable sector • Local leaders at ward, village level and farmers in selected villages |
| Dec., 2015 |  | 1.2 Set-up demonstration trials in both new sites and reinforce dissemination at old sites/communities | • Set up demonstration trials categorized best practices and normal practices ( use elite vegetable varieties, health seedlings and GAP) • Build Capacity and awareness of extension agent and farmers on GAP, through: - Regular training -Joint Community exchange visits for demo exposure and study tours - Field days and sensitization meetings • Follow up visits for monitoring of activities &provide extension support | • 7 demonstration trials categorized best practices and normal practices ( use elite vegetable varieties, health seedlings and GAP)established • Additional 200 additional farmers aware and able to use and apply GAP, through: |  |
| Jan.,- April,2016 | Output 2: Farm households characterized and typologies in intervention sites determined | 2.1 Community–based mobilization of farmers to access viable and/or functional markets and provision of market information systems | 2.1 Facilitate establishment of vegetable farmer organizations through farmer group formation, while strengthening existing ones as a vehicle for disseminating identified technologies activities to achieve larger scale impact Market linkages and validated post-harvest processing and utilization practices to reduce shelf-life and increase consumption of nutritious vegetables | • At least 1 input and 1 produce market information and/linkages for farm household to access vegetables markets developed Conduct gender analysis study and use the feedback to strengthen gender issues through farmer organizations | As above |
| Jan.,- June, 2016 | Output 3: Potential impact of various SI technologies in different development stages assessed | 3.1 Cost-benefit analysis of best bet technological packages evaluated | • Assess the costs and returns of each promoted technology • Compare results of new technologies with farmer standard practices • Gross margin computation of promoted technologies • Documentation and share results with stakeholders | • Cost and returns analysis of elite vegetable varieties, healthy seedlings and ICPM in comparison with standard farmer practices finalized and shared with farmers during field days and via the R4D platform. • At least one MSc. Thesis on “Effect of newly introduced AVRDC vegetable technologies in reduction of income poverty in the Babati district of Tanzania” completed and extracts drafted for submission to a peer-review journal • Cost benefit analysis report • Compare results of new technologies with farmer standard practices | • AVRDC scientist • Subject matter specialists at district, ward and village level • Local leaders at ward, village level and farmers in selected villages • MSc student (iAGRI) |
| Jan.,- June, 2016 |  | 3.2. Vegetable-poultry integration and productivity enhancement. | Optimal use of chicken waste for replenishing the fertility status of soils cultivated to vegetables while exploring the use of vegetable residue for poultry feed | • At least 1 best-bet technology for enhanced optimal nutrient recycling of vegetable-poultry integration in the farming system | •AVRDC & IITA scientist in collaboration with feedwith livestock and feed research theme • Identified stakeholders working in vegetable sector in and outside Babati |
| June-Aug., 2016 | Output 4: R4D and Innovation platforms influencing stakeholder practices established | 4.1 Communicating research findings to stakeholders through Babati R4D platform | •provide feedback on lessons learnt from the 2014-2015 season and share planned work for the 2015-2016 and 2016-2017 production seasons | • At least 1 R4D meeting and feedback meetings conducted , lesson leant from 2014-2015 and 2015-2016 shared and set the way forward by March 2016 | •AVRDC Scientists • Babati AR theme representatives • Identified stakeholders working in vegetable sector in and outside Babati • R4D team representatives/committee |
| June-Aug, 2016 | Output 5: Innovations that increase resilience and productivity of farming systems deployed | 5.1 Explore options for effective water harvesting in the 4 and new AR vegetable sites and new selected sites | • Identification of best-bet technology for optimizing water harvesting, management and/or water use efficiency for vegetables for subsequent dissemination to beneficiaries | • At least 1 best-bet technology for optimizing water harvesting and/or water use efficiency for vegetables identified for subsequent dissemination to beneficiary farmers by June 2016 | • AVRDC scientist • to be led by CIAT and IITA Scientists |
| June-Sept, 2006 | Output 6: Crop-nutrition and water efficient innovations introduced, evaluated and adapted | 6.1) Integrated crop and pest management practices & food safety analysis. | •Promote nutritional education on the need for use of safe water for irrigation of vegetables and increased consumption of safe vegetables • Development of participatory problem analysis and intervention strategy process • Identification and selection of safe and sustainable intensification of mutually beneficial mixed cropping systems | • At least 2 sensitization meeting on safe water for irrigation and consumption of nutritional vegetables conducted to farmers and other stakeholders in AR project sites in Babati • Participatory problem analysis and intervention strategy process developed by May, 2016 • Safe and sustainable intensification of beneficial mixed cropping systems identified by June, 2016 | • AVRDC & IITA scientist • Subject matter specialists at district, ward and village level • Identified stakeholders working in vegetable sector • Local leaders at ward, village level and farmers in selected villages |
| June-Sept, 2006 | Output 7: Innovations that increase availability and consumption of safe and nutritious food products deployed | 7.1 Validate post-harvest processing and utilization practices to reduce shelf-life and increase production and consumption of nutritious vegetables | Train farmer beneficiaries in postharvest handling techniques that aim at improving shelf-life and year-around availability of nutrient dense vegetables | • At least 150 additional farmers become aware on nutritional importance of vegetable consumption and receive training on post-harvest handling & processing, market linkages, business and entrepreneurship skills and utilize the knowledge to enhance year-round availability of produce for sale and home consumption. • At list 100 farm families are aware of tested and validated post-harvest handling practices that add value to produce and improve shelf-life adopted following their exposure | • AVRDC scientist • Subject matter specialists at district, ward and village level • Identified stakeholders working in vegetable sector • Local leaders at ward, village level and farmers in selected |
| June-Sept, 2006 | Output 8: Innovations that address emerging agricultural production challenges deployed | 8.1 ICPM of vegetable pest and diseases management developed and integrated into existing farming systems | • Development of ICPM of vegetable pests and diseases to reduce the misapplication of pesticides that are harmful to human, animal and environmental health. | Appropriate ICPM of vegetable pest and diseases in place to realize the opportunity for vegetables to be integrated into existing farming systems disseminated to over 500 farmers. | • AVRDC scientist • Subject matter specialists at district, ward and village level • Identified stakeholders working in vegetable sector • Local leaders at ward, village level and farmers in selected villages •Identified stakeholders working in vegetable sector led by IITA |
| June-Sept, 2006 |  | 8.2 Vegetable seedling unit established at community level | Vegetable seedling unit established at community where farmers will be instructed and guided on good agronomic husbandry practices using the farmer learning group (FLG) concept already tested and validated by IITA in West Africa | • Diagnostic protocols for community healthy seedlings systems development identified as common constraints determined and farmer awareness of pests and diseases developed. | • AVRDC scientist • Subject matter specialists at district, ward and village level • Identified stakeholders working in vegetable sector • Local leaders at ward, village level |
|  |  |  |  | Appropriate ICPM of vegetable pest and diseases in place to realize the opportunity for vegetables to be integrated into existing farming systems disseminated to over 500 farmers. | •Identified stakeholders working in vegetable sector led by IITA activity will be led by IITA |
| Aug. – October, 2016 | Output 9: Scaling approaches for targeted integrated innovations identified and piloted | 9.1 Promotion for widespread adoption of tested technologies | • Strategic community sensitization on nutritional importance of vegetables and demonstrations for selected vegetables along with promotion of the improved best bet agronomic practices promoted to target beneficiary farmers through field visits, rallies, schools, field days, meetings, R4D platform and hospital gardens | • At least 300 additional farmers become aware through sensitization on nutritional importance of vegetables tested best bet technologies promoted to target beneficiary farmers via , schools, field days, study tours, meetings, R4D platform and hospital gardens by December 2016 | • AVRDC scientist • Subject matter specialists at district, ward and village level • Identified stakeholders working in vegetable sector • Local leaders at ward, village level •Identified stakeholders working in vegetable sector |

3.8 BUDGET FOR THE 2015-2016 PRODUCTION SEASON

| Line item | Category | Amount ($US) |  |
| --- | --- | --- | --- |
|  |  | AVRDC | IITA |
| Personnel | IRS | 8000 | 5000 |
|  | NRS | 6000 | 2000 |
| Travel |  | 6000 | 2000 |
| Field activities | Community sensitization, demand creation activities to increase nutritional and food safety awareness (e.g., community field days, farmer exchange visits, promotional campaigns) | 6000 | 0 |
|  | Field demonstration (seed and seedling treatment) trials, field demonstration data collection and related field validation visits | 7000 | 1000 |
|  | Sustainable intensification indicators data collection | 8800 | 1200 |
|  | Farmer training in vegetable seed production, seed nursery management, agronomy, postharvest and market information systems, postharvest handling, cooking recipes | 5000 | 0 |
|  | Demo plot and postharvest technology cost-benefit analysis data collection, gender analysis data collection and studentship field validation studies | 6000 | 1000 |
|  | Community nursery establishment (including trainings) and lab-based food safety analysis | 500 | 6500 |
| Supplies & Services | Seed distribution, farm implement & agrochemicals, office supplies, phone and internet communication, publicity, factsheets and reports, open-access peer-reviewed publications | 5850 | 1000 |
|  | Meetings with partners including R4D & innovation platformmeetings, and contracted services on vegetable poultry integrationand water management (harvesting) techniques | 3000 | 500 |
| Sub-total |  | 62150 | 20200 |
| Overheads (18.0%) |  | 11187 | 0 |
| Sub-Total |  | 73337 | 20200 |
| Total ($) |  | 93537 |  |

3.9 FtF INDICATOR TARGETS

| Indicator / Disaggregation | 2015/16 Target |
| --- | --- |
| 4.5.2(2): Number of hectares under improved technologies or management practices as a result of USG assistance (RIA) (WOG) | 8 |
| Technology type |  |
| crop genetics | 8 |
| pest management | 8 |
| disease management | 8 |
| soil-related | 3 |
| irrigation | 2 |
| water management | 2 |
| climate mitigation or adaptation | 5 |
| other |  |
| total w/one or more improved technology | 5 |
| Joint | 265 |
| Association-applied |  |
| Disaggregates Not Available |  |
| 4.5.2(5): Number of farmers and others who have applied new technologies or management practices as a result of USG assistance (RIA) (WOG) |  |
| New/Continuing | 419 |
| New | 200 |
| Continuing | 219 |
| Disaggregates Not Available |  |
| 4.5.2(7): Number of individuals who have received USG supported short-term agricultural sector productivity or food security training (RIA) (WOG) |  |
| Type of individual |  |
| Producers | 200 |
| Disaggregates Not Available |  |
| 4.5.2(11): Number of food security private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) receiving USG assistance (RIA) (WOG) | 5 |
| Type of organization |  |
| Water users associations | 4 |
| Women's groups | 4 |
| Community-based organizations (CBOs) | 4 |
| Disaggregates Not Available |  |
| New/Continuing | 4 |
| New | 2 |
| Continuing | 2 |
| Disaggregates Not Available |  |
| 4.5.2(27): Number of members of producer organizations and community based organizations receiving USG assistance (S) | 6 |
| Type of organization | 0 |
| Producer organization | 6 |
| Non-producer-organization CBO | 0 |
| Disaggregates Not Available |  |

## Theme 4. Food storage, value addition and mycotoxin management

4.1 RESEARCH TEAM (Theme leader: Adebayo Abass, IITA: George Mahuku, IITA)

| Name | Gender | Institution | Discipline | Qualification | Projec t role | %time |
| --- | --- | --- | --- | --- | --- | --- |
| Abass Adebayo | M | IITA | Food Technologist | PhD | Principal Investigator | 5 |
| George Mahuku | M | IITA | Plant Pathologist | PhD | Mycotoxin Coordinator | 5 |
| Leonard Leo | M | IITA | Statistician | BSc | Data management | 10 |
| Gabriel Ndunguru | M | IITA | Food Scientist | PhD | Project consultant | 25 |
| Lunna Hemed-Kyungu | M | (COUNSENUTH) | Nutritionist | PhD | Project consultant | 5 |
| Julius Ntwenya | M | UDOM | Nutritionist | PhD | Food security | 5 |
| Grace Michael | F |  | Food Technologist | B.Sc. | Project consultant | 5 |
| Hossana Ngonyani | F |  | Product Development |  | Project consultant | 5 |
| Simon Boniface | M | IITA | Mycotoxins pecialist | PhD | Handling day to day work on mycotoxins | 50 |
| Emmanuel Koyano | M | IITA | Research supervisor | MSc | Collection, preparation and analysis of mycotoxin samples | 5 |
| Mark Lwakatare | M | IITA | Food Safety | MSc. | Project Consultant | 50 |
| Edgar Lyakurwa | M | Babati District Council | Social scientist | BSc | Refinement and deployment of awareness strategy | 5 |
| Jocelyn Kaganda | F | TFNC | Nutrition & food safety | PhD | Development of awareness raising materials | 10 |

4.2  SUMMARY

Postharvest losses and mycotoxins contamination are caused by poor handling and storage practices accentuated by limited market access and narrow options for processing of foods into more safe and shelf stable products. During the last two years of investigating post-harvest problems in Babati, results showed that for maize, significant losses occur during field and home storage, when insects and pests can damage an average of 30 to 40% of stored maize. The field maize losses ranged from20% caused by rats, pests and improper harvesting while during shelling losses of maize was 5%. But the traditional processing practices were very tiresome to women and also time-consuming. During storage of maize, losses by larger grain borer (Prostephanus truncatus) could be as high as 90% and 15–25% by grain weevil (Sitophilus granarium).Therewere also losses caused by confused flour beetle (Tribolium confusum) and lesser grain borer(Rhyzopertha dominica).

The jump start inception project in 2012,we quantified mycotoxin levels of maize in Babati district. Results showed that total aflatoxin prevalence ranged between 70% and 87% with contamination levels ranging from 5µg/kg to 418µg/kg, making it being among the districts with alarming contamination of the toxin in the country. Results from the analysis of maize samples collected from field (at harvest) and stores (post-harvest) in 2013/2014 showed that aflatoxin and fumonisin ranged from 0 to 6.2µg/kg and0 to 46.2mg/kg, respectively. Moreover the two toxins are prevalent in Babati although with varying levels. Work during the previous years have created some degree of awareness about mycotoxins in Babati, but and ‘fit-for-purpose’ communication strategies and tools are required to target different sections of commodity value chain.

This theme will integrate the previous ‘work packages’ on mycotoxins and post-harvest processing and build on research conducted during the last two years. A link will be created with the theme on integrated Livestock Feed component; to determine the extent o f mycotoxin contamination in feed of free-range poultry.

We will continue to identify and test adaptable postharvest management techniques that reduce post-harvest losses, improve food safety, and increase the income and nutritional status of the communities. This will be achieved by increasing the access of small holder farmers to improved storage technologies (such as oxygen-moisture impermeable bags) combined with appropriate improved mechanical processing technologies( e.g. shelling and drying) by working with lead farmer to test a combination o f these technologies to fully address postharvest loss and nutrition inadequacy among farming households. The project will evaluate labor and time savings from the use of mechanical processing equipment for simple farm operations such as shelling and drying. Pilot centers will be established to provide mentorship directly to farmers on the various technologies available and train the farmers to improve their market linkage expertise; increase both safety and nutrient density of household foods.

Similarly mycotoxin levels will be monitored by taking samples of cereal grains stored by smallholder farmers using improved storage technologies combined with improved mechanical processing technologies. Sample analysis will be carried out at IITA. There will also be integration withTheme2 by determining the safety of feed rations of indigenous of poultry tested under Activity 4 ofTheme2.Thetoxin analysis will be performed by IITA using the methods developed and tested in 2013/2014. TNFC will adapt their experiences on successful campaign for dissemination of knowledge on nutritional security for mycotoxin management messages tailor-made for participants of cereal value chain.

Thisprojectwillcontinuetoidentifyanddeploycontrolinterventionstomitigatemycotoxincontaminationin6targetvillagesofBabatiandhencesafeguardthehealthofpeople,livestockandrealizeincomegeneratingopportunitiesthroughtrade(includingaccesstoregulatedmarketswheremycotoxincontaminationisprohibited).

4.3  JUSTIFICATION

Postharvest food loss is a challenge that contributes to food insecurity and reduces the income of millions of smallholder farmers. Maize is a major staple as well as a commercial crop in Babati. Yield per unit area has the potential to double with the use of improved inputs. While the use of pest control chemicals to control losses is common among the farmers, the effectiveness is not guaranteed and possibility of extensive public poisoning or public health hazard is high because of the existence of fake products and tendency of farmers to apply the chemicals at excessively high levels while the lack the knowledge of establishing the residual compound in the grains when marketing them.

Previous problem diagnosis and study of the extent of postharvest losses in Babati and other districts in northern and central Tanzania suggest that traditional harvesting, shelling and storage practices contribute to between 20-50%, 5%, and15-25% losses of grains respectively. Inappropriate shelling, drying and storage practices lead to high grain damage, contamination by mould, discoloration ( with a consequence of reduced market price) and high aflatoxin levels. Field experience suggests that smallholder farmers have very narrow range of diets although there is a very wide range of cultivated crops. There is an acute knowledge of balanced diet, with monotonous consumption of maize-based meals. To ameliorate these situations; erstwhile‘work-package’ on postharvest management was involved in testing of various processing and storage technologies in Babati. Some lead farmers were involved in the use of various technologies related to maize shelling, drying and storage with much success. Results from the participatory technology testing suggest that while storage of maize in oxygen impermeable bags preserves grains with zero loss after 8-month storage. On the other hand, grain damage in traditional cribs and polypropylene bags was up to 40%d during the same storage period. There are indications that a large number of farmers have requested for access o the tested technologies. This theme has progressively developed a model of using postharvest technologies to boost farming systems intensification through a step-wise approach that include problem diagnosis and testing of possible solutions (technology testing;Figure1). However, the impact of improved postharvest management approach on farmers’ decision and migrations towards farming system intensification needs to be investigated with appropriate socio-economic research methodologies.

Mycotoxins contamination levels of maize in Babati is still a significant problem of public health.  Aflatoxin and fumonisin in maize collected in 2013/14 (about1500samples) from thereof the six target villages showed contamination levels of 0 to 26.2µg/kg in Sabilo, 0 to 4µg/kg in Seloto and 0 to 3.6mg/kg in Long for total aflatoxin and 0 to 42mg/kg in Seloto and 0 to14mg/kg in both Sabilo and Long for total fumonisin.

Mycotoxin levels will be monitored by taking samples in cereal grains stored by smallholder farmers using improved storage technologies combined with improved mechanical processing technologies as compared to the local/traditional practices. In addition, poultry  feed samples will continue to be collected (in collaboration with research theme “Improving productivity of indigenous chicken through better nutrition and management in mixed crop-livestock farming systems in Babati,Tanzania”) and analyzed for mycotoxin. Sample analysis will be carried out at IITA Dares Salaam using the methods developed and tested in 2013/2014.

In the erstwhile ‘work package’ on mycotoxins, some emphasis was placed on creating awareness among farmers and policy-makers. However, enhancing awareness for behavioral change management requires consistent and repeated efforts. In Theme4,we will build on previous experiences on awareness creation about mycotoxins and develop strategies and pilot-testing communication tools for enhancing knowledge about mycotoxin management in t the maize value chain. The Tanzania Aflatoxin Steering Committee has placed emphasis on enhancing awareness among crop value chain participants. This is also in line with the priorities of the Partnership for Aflatoxin Control in Africa (PACA)

Diagnosis of postharvest handling constraints and the causes of postharvest loss of food in Babati; 2012/2013

Participatory field testing of improved processing technologies and postharvest loss prevention technologies; 2013/2014

Pilot-testing of processing/storage technologies at commercial level, farmers’ training & technology dissemination; 2014/2015 & 2015/2016

Future or new locations:

Dissemination and economic viability assessment of postharvest management technologies

Africa RISING Postharvest/processing research activities

Time

Figure2:Step-wise application of improved postharvest management technologies to boost farming systems intensification

4.4 OBJECTIVES/RESEARCH QUESTIONS

The main focus of the work is to promote and disseminate appropriate post-harvest management technologies (Output 6.4 for2014/2015) and as a long term goal is to apply improved postharvest technologies to boost sustainable intensification of maize farming system and improve food safety and security in the project areas. Improved processing and storage will be tested at commercial scale (piloting) for reducing losses and assisting farmers to store and market when the price is most favorable.

Research questions

- Which combination of technology packages can reduce the vulnerability of households to food insecurity, food toxins (e.g. aflatoxins), low income and poor nutrition?

- To what extent can labor and time inputs into postharvest activities be reduced through the use of machines, especially by women?

- To what extent can the various crop management practices (GAP), processing (handling) and storage technologies mitigate mycotoxin contamination in food and feed?

- Are there potential risks of mycotoxins in experimental rations being developed for enhancing productivity of free range poultry?

- What communication strategies and tools are required to enhance knowledge about mycotoxins and their management among various segments of crop value chain?

4.5 METHODS

The on-going establishment of one pilot processing center in each of the project villages will be completed and used in promoting the postharvest technologies. The centres will also be used for the training of women in the project communities on improved nutrition. A package of technologies, extensive training and dissemination efforts will be applied  to save the population from a potential future reliance on purchased foods and to prepare the population for food sufficiency and ability to make own high quality and safe foods. A range of previously tested packaging techniques and crop processing technologies will be evaluated using the centrally-located(community-based) pilot processing areas.

The technologies will be used to promote better harvesting, handling and storage practices to reduce post-harvest losses, mycotoxin contamination and promote processing and value addition, reduce losses and increase diversified food products. We will use dedicated or lead farmers, improved storage techniques, the use of high capacity motorized shelling machines, collapsible dryer cases for drying of maize to13% before storage, high capacity storage bags for maize storage without using chemicals and new approaches for increasing household food nutrient density. Local entrepreneurs and traders will be assisted and linked with the sources of the processing, packaging and storage facilities.

Cereal grains handled/stored by the farmers using improved postharvest technologies and the local/traditional storage structures will be analysed for mycotoxin at IITA using the Neogen system standardized for analysis of maize grains during previous years. Information collected in the sample questionnaire will be interrogated and correlated with analysed mycotoxin levels to ascertain which production; processing and storage practices are most directly linked with mycotoxin contamination.

For the integrated activity with Theme 2, poultry feed ingredients and formulations will be collected and analyzed by IITA. Samples will also be collected from the feeding pans of the chicken from the households in order to assess the status of aflatoxin and fumonisin contamination in course of feeding chicken. Forty-four samples of the intended ingredients have been collected earlier. Samples from the feed formulations and from the feeding pans will be collected later when T heme2starts to implement its activities on the g round. Due to the complex nature of the matrix of feed ingredients, mycotoxin analysis will be conducted by mycotoxin analysis protocols standardized last year.

The manner in which awareness constraints and opportunities for managing the constraints are tackled depends on the nature of the value chain segment. Based on “Previous Experiences of Aflatoxin Management Communication”, TNFC will determine suitable strategies for effective communication along the entire crop value chain. The messages will be pre-tested and most effective ones disseminated.

4.6 LOGICAL FRAMEWORK

Innovations that increase availability and consumption of safe and nutritious food products deployed (Output 7 in ESA logframe)

| Objective statement | Verifiable Indicators | Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| Super Goal |  |  |  |
| Increased economic growth and improved livelihoods in Babati district | Change in GDP from agricultural sector. Change in people living on more than 1.25$ per day | Government statistical report World Bank annual reports |  |
| Goal |  |  |  |
| Enhanced livelihoods of small holder farmers of Babati through integrated farming system. | Percent change in income of farmers growing staple food crops, vegetable and keeping livestock. Improved food security and consumer safety of Babati communities | Annual trade statistics data World Health Organization Reports | Committed funds will be available and on time |
| Purpose |  |  |  |
| Enhanced adoption and application of postharvest technologies and innovations to increase the availability and consumption of safe and nutritious food products | - % of farmers aware of new/improved postharvest technologies by September 2016 - % of maize growers using maize shelling machines and hermetic storage techniques to store produce and reduce pest infestation and losses in Tanzania by September 2016 - % of maize farmers applying other improved postharvest technologies in Tanzania by September 2016 - Number of direct beneficiaries reached through project support by September 2016 - Levels of mycotoxin contamination | Baseline –and end-line M&E reports, subsequent impact analysis report by social economists, food scientists and mycologist; scientific publications technical and non-technical reports, partner reports, project database | - Farmers are willing to take part in postharvest storage experiments; - Farmers are willing to provide their storage facilities for experiments; - Cost of application of postharvest technologies affordable to farmers and traders/technology suppliers - Financial services available for stakeholders to purchase new machines; - Mycotoxin contamination in food and feed properly monitored |
| Project Outputs |  |  |  |
| Output 1: Appropriate post-harvest handling technologies and processing techniques demonstrated and promoted | 1.1 At least three village level postharvest processing pilot centers for processing, storage and preservation of grains, legumes and horticulture products established by September 2016 | Physical pilot center infrastructure, project reports, databases and publications Lab records on samples analyzed for mycotoxins | Lack of maintenance of the postharvest storage tools and pilot facilities in spite of trainings provided |
|  | 1.2 At least three improved postharvest technologies tested and demonstrated with men, women and youth farmers by September 2016 | Reports, databases, village centers, publications | Technologies will be available and affordable by the farmers. Farmers will be ready to form groups and register as Innovation platforms Farmers will be ready to allow scientists to access their storage systems. |
|  | 1.3 At least 30% increase in economic and social profitability of improved postharvest technologies achieved by maize farmers by September 2016 | Farmers’ business records Reports, databases, publications | Social scientist will play their role as planned. |
|  | 1.4 Increased safety of household foods through reduced mycotoxin levels | Lab reports on mycotoxin contamination levels in foods | Grain handling and processing treatments are conducted well by communities |
| Output 2: Safe constituents Poultry feed ration identified | 2.1 Aflatoxins and fumonisin levels in various poultry feed constituents | Lab reports on number of samples tested | Samples (feed ingridients and finished feed formulations) are provided by livestock group |
| Output 3: Awareness created and information on mycotoxins and postharvest technologies generated and disseminated, networking among stakeholders created | 3.1 At least 150 farmers/households trainedby September 2016in novel processing, products development (high nutrient diet formulation) and preservation of locally produced grains, legumes, horticulture crops | Project training records; District authority records | Funds will be available on time |
|  | 3.2 Information prepared for dissemination through various channels by September 2015 | Documents/packages on postharvest technologies and mycotoxins filed Radio and TV programs Reports filed by media organizations | Enough information will be generated during the project implementation |
|  | 3.3 Research and Development Platforms for Babati districts involved in the use of improved postharvest technologies and prevention of mycotoxins supported | Number of R&D Platforms available in the villages Policy documents containing postharvest and mycotoxins issues | Funds will be available Local government of Babati will participate in the project |

4.7 PROJECTED FTF INDICATORS FOR 2015/16

| Indicator / Disaggregation | 2015/16 |
| --- | --- |
|  | Target |
| 4.5.2(5): Number of farmers and others who have applied new technologies or management practices as a result of USG assistance (RIA) (WOG) |  |
| New/Continuing |  |
| New | 770 |
| Continuing | 630 |
| Disaggregates Not Available | 200 |
| Sex |  |
| Male | 300 |
| Female | 400 |
| Disaggregates Not Available | 200 |
| 4.5.2(7): Number of individuals who have received USG supported short-term agricultural sector productivity or food security training (RIA) (WOG) | 200 |
| Type of individual |  |
| Producers | 200 |
| Sex |  |
| Male | 80 |
| Female | 120 |
| Disaggregates Not Available |  |
| 4.5.2(11): Number of food security private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) receiving USG assistance (RIA) (WOG) | 5 |
| Type of organization |  |
| Private enterprises (for profit) | 5 |
| New | 0 |
| Continuing | 5 |
| Disaggregates Not Available |  |
| 4.5.2(12): Number of public-private partnerships formed as a result of FTF assistance (S) | 7 |
| Agricultural production |  |
| Agricultural post harvest transformation | 7 |
| Disaggregates Not Available |  |
| 4.5.2(27): Number of members of producer organizations and community based organizations receiving USG assistance (S) | 250 |
| Type of organization |  |
| Producer organization |  |
| Non-producer-organization CBO |  |
| Disaggregates Not Available | 250 |
| 4.5.2(39): Number of new technologies or management practices in one of the following phases of development: (Phase I/II/III) (S) | 6 |
| Phase 1 Number of new technologies or management practices under research as a result of USG assistance |  |
| Phase 2 Number of new technologies or management practices under field testing as a result of USG assistance | 1 |
| Phase 3 Number of new technologies or management practices made available for transfer as a result of USG assistance | 5 |
| Disaggregates Not Available |  |
| 4.5.2(42): (4.5.2-28) Number of private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) that applied new technologies or management practicies as a result of USG assistance (RIA) (WOG) | 10 |
| Type of organization |  |
| Private enterprises (for profit) |  |
| Producers organizations |  |
| Water users associations |  |
| Women's groups |  |
| Trade and business associations |  |
| Community-based organizations (CBOs) |  |
| Disaggregates Not Available |  |
| New/Continuing |  |
| New | 2 |
| Continuing | 8 |
| Disaggregates Not Available |  |

4.8 DELIVERABLES

- One MSc student registered at the University of Dodoma or UDSM to focus on postharvest management techniques, mycotoxin or nutrition enhancement (IITA).

- At least an additional storage technique tested (e.g.Zerofly, PICS and/or silo)(IITA)

- At least 3 pilot processing and storage centers established (IITA)

- At least 60 farmers in each village trained on postharvest management (IITA)

- At least 3 local entrepreneurs linked to the source of processing machines and packaging materials (IITA)

- Fate (type, incidence, and quantity) of mycotoxins, with focus on aflatoxin and fumonisin, determined  in grains processed, handled and stored under various practices(IITA)

- Mycotoxin risk profile in various crop constituents of poultry rations considered for decision   making of optimal feed needed for enhancing poultry productivity (IITA).

- Communication tools for various segments of crop value chains tested (TFNC)

4.9 ACTIVITY SCHEDULE

| Activity | 2015 |  |  |  | 2016 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | S | O | N | D | J | F | M | A | M | J | J | A | S |
| Proposal development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Establish village-level pilot processing &community training centers for processing, storage and preservation of grains, legumes and horticulture crops and livestock products(IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of improved postharvest technologies with men, women and youth farmers for enhanced adoption of technologies(IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimate and validate the economic profitability of improved postharvest technologies(IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify maize varieties with long storability period and consumer preferred traits (IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect samples from farmer’s fields and stores in the project villages for analyses of mycotoxins and other grain -quality parameters (IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train farmers/households in novel processing, products development (high nutrient diet formulation) and preservation of locally produced grains, legumes ,horticulture crops(IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze samples collected from crop management experiments for mycotoxins content; to validate GAP measures (IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify and audit best bet postharvest management measures that reduce postharvet losses and increase quality of maize (IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze mycotoxin in samples collected from experiments to identify maize varieties tolerant/susceptible to lethal necrosis disease - (IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze mycotoxin in poultry feed rations(IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct experiments to identify and validate biological control of aflatoxins (IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepareanddisseminaterelevanttrainingandinformationusingrelevantavenues(TFNC) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support research and development platforms in Babati (IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Follow up survey of knowledge, attitude and perception in response to mycotoxin media campaign(TFNC) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Data analysis and report as indicated for each activity above, plans for subsequent year(IITA) |  |  |  |  |  |  |  |  |  |  |  |  |  |

4.10 BUDGET

| Target Outputs (ESA Logframe) | Activity (Technology, tool…) | Activity description | Deliverables (end product/innovation/technology) | Responsible Person and Institution | TOTAL BUDGET | Budget split |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Myco-toxin | Post harvest |
| Output 3: Potential impact of various SI technologies in different development stages assessed | 3.1. Best variety (out of 10 - six of which are hybreeds) with long storability period and consumer preferred traits identified | Sample collection; set-up storage experiment; sampling for losses; lab analysis; consumer preference test in all the villages; extraction rate assessment. | Best variety with long storability period and consumer preferred traits identified | IITA - Abass/ Nutritionists-consultant/Postdoc | 25000 |  | 25000 |
|  | 3.2. Best bet good agricultural practices (GAP) measures that reduces mycotoxin contamination identified | Sample collection from different management systems (fertilizer types and regimes, weed management, intercropping, etc); processing and analysis of mycotoxins (fumonisin & aflatoxin) | Best best GAP measures that reduces mycotoxin contamination identified | IITA - Mahuku/Postdoc | 10000 | 10000 |  |
|  | 3.3.Best bet postharvest management measures that reduce postharvet losses and increase quality of maize | Audit of postharvest handling methods from farm to storage; sample collection and analysis for losses from farm to storage; laboratory analysis (mycotoxins; nutrient quality; pasting properties) | Best bet postharvest management measures identified | IITA -Abass/Mahuku/Postdoc | 15500 | 8000 | 7500 |
|  | 3.4. Establish SI indicator attributes that define reduced food waste |  | Threshold SI values identified | IITA | 10000 | 5000 | 5000 |
| Ouput 7: Innovations that increase availability and consumption of safe and nutritious food products deployed | 7.1. Hermetic storage technology (hermetic bags) | Registration of farmers and farmers' cooperatives for storage of maize with hermetic storage bags; distribution of bags & storage of maize in ware houses; monitoring of losses, safety/quality of maize; mycotoxins analysis | Safe food with zero-loss | IITA - Abass/Mahuku/Postdoc | 25000 | 5000 | 20000 |
|  | 7.2. Shelling machine; dryer cases | Farmers' profiling; Capacity building; shelling machines; knowledge evaluation(old villages) & potential adoption assessment. | Knowledge, machinery for processing and tools for drying & handling of maize | IITA - Abass/Mahuku/Postdoc | 15000 |  | 15000 |
|  | 7.3. Nutritious foods to increase farmers' nutrition | Development of complementary foods for under five; training of community level service providers in deliveriing nutrition services | Guidelines/manuals on community nutrition enhancement & recipe books | IITA - Abass/Consultant-Nutritionist | 18871 |  | 18871 |
|  | 7.4. Potential aflatoxin biocontrol agent | Testing potential aflatoxin biocontrol agent: field site selection & characterization; setting-up the experiment; production of biocontrol innoculum; field application; sample collection and analysis; awareness creation | Best bet biocontrol agent identified | IITA - Mahuku/Postdoc | 15000 | 15000 |  |
|  | 7.5. Awareness creation materials | Preparation of information dissemination materials; dissemination through different channes (media, brochures, radio, TV, etc); workshops to sensitive stakeholders (farmers, extension officers and policy markers on mycotoxins on human and animal health | Communication materials | TFNC & IITA -Mahuku/Postdoc/TFNC | 20000 | 20000 |  |
| Output 8: Innovations that address emerging agricultural production challenges deployed | 8.1. MLN tolerant varieties with reduced mycotoxin contamination | Collect samples from MLN trials (WP2): Integrated approaches to manage maize lethal necrosis (MLN) in Tanzania; mycotoxin (fumonisin and aflatoxin analysis) | Knowledge on interaction between MLN, ear rots and aflatoxin contamination. | IITA - Mahuku, Kumar / Postdoc; CIMMYT - Jumbo | 2129 | 2129 |  |
| 2015/2016 proposed budget |  |  |  |  | 156,500 | 65,129 | 91,371 |

## Theme 5. Management of maize lethal necrosis disease

5.1 RESEARCH TEAM (Theme leader: Jumbo Bright, CIMMYT; Lava Kumar, IITA)

| Name | Gender | Institution | Job title | Disciplinary expertise | Highest qualification | Project role | % time |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bright Jumbo | M | CIMMYT | Scientist | Breeding | PhD | PI | 25% |
| Dan Makumbi | M | CIMMYT | Senior Scientist | Breeding | PhD | Co-PI | 10% |
| NN | M | CIMMYT | Senior Scientist | Pathology | PhD | Staff | 10% |
| Lava Kumar | M | IITA | Scientist | Virology | PhD | PI | 5% |
| Allan Mereki | M | IITA/UM/MAFSC | Student | Virology | MSc (in progress) | Student | 80% |
| Susan Njeri | F | CIMMYT | Research Assistant | Breeding | MSc | Field Operations | 10% |
| George Ochieng | M | CIMMYT | Research Assistant | Breeding | Diploma | Field Operations | 10% |
| Kheri Kitenge | M | SARI | Scientist | Breeder | MSc | Research operations | 10% |

5.2 SUMMARY

The outbreak and rapid spread of MLN in Tanzania, especially in Arusha, Babati, Mara and Mwanza, has emerged as a big threat to maize production and currently most of the commercially available varieties are susceptible to the disease. With the support of AfricaRISING, efforts are in progress since 2012-13 to develop varieties resistant to MLN and understand MLN epidemiology to develop suitable integrated solutions to manage MLN threat. Some promising hybrids identified during these efforts which include J4-134, J4-238, J4-188, J4-172, J4-241, J4-179,  J4-20, J4-1, J4-34, J4-25, J4-56, J4-3, J4-103, J4-14, J4-106, J4-51, J4-87, J4-81, J4-84, J4-26, J4-117, J4-21, J4-120, J4-50, J4-109, J4-44, J4-22, J4-115, J4-123, J4-125, J4-42, J4-23, J4-83, J4-31, J5-106, J5-6, J5-41, J5-79, J5-73, J5-27, J5-90, J5-107, J5-75, J5-102, J5-65, J5-78, J5-112, J5-32, J5-111, J5-105, J5-4, J5-108, J5-38,  J5-12,  J5-34, J5-68,  J5-28, J5-9, J5-37, J5-100, J5-5, J5-48, J5-3, J5-98, J5-18, J5-55, J5-59, J5-29, J5-46, J5-22, J5-13, J5-117,  J5-64, J5-104, J5-39, J5-17, J5-7,  J5-76, J5-2, J5-67, J5-116, J5-63, J5-1, J5-91,  J5-53,  J5-40, J5-89, J5-115, J5-15, J5-25, J5-47 and J5-36 need to be tested to validate their response to MLN in the disease hotspot areas under different agronomic and cultural practices. Epidemiological surveys are required to assess the disease incidence during the off-season and its impact on new season crop. Studies are also required to understand the key biophysical characters influencing MLN epidemics in the region. Low-cost MLN diagnostic tools developed in the previous efforts need to be extended to the stakeholders, which requires investing in building local laboratory capacity and training personnel in diagnostics and analysis.

5.3 RESEARCH JUSTIFICATION

During execution of Africa RISING activities in Babati in 2013, we identified symptoms of MLN disease in the trials and noted that many of the recently released hybrids and the commercial checks were seriously affected by the disease. Although the varieties preferred by farmers expressed moderate symptoms earlier on, their response has not been consistent in the subsequent season under uniform disease pressure. Pest and disease surveys organized by IITA and partners revealed severe MLN incidence in low and mid-altitudes compared to high altitudes. Plants affected at early stage of the plant growth died prematurely resulting in 100% yield losses. Studies also revealed relatively high incidence of single infection of MCMV compared to mixed infection of MCMV+SCMV suggesting that MCMV alone is threat to maize.

The most sustainable control option for MLN is host plant resistance combined with other management options such as good cultural practices. CIMMYT together with its partners from both private and public research organizations have teamed up to work on finding solutions to control MLN. Initial evaluations of several maize inbred lines and hybrids for resistance/tolerance in Kenya have led to the identification of some hybrids and inbred lines with moderate resistance and tolerance to the disease under natural and artificial inoculation (CIMMYT, 2012). Several of these hybrids including farmer preferred hybrids selected during agronomic evaluations in Babati in year 2 (2012) have been tested in 2013/14 crop growing season for their reaction to MLN under natural infestation in hotspot areas. Best performing hybrids included the following experimental hybrids: J4-134, J4-238, J4-188, J4-172, J4-241, J4-179, J4-20, J4-1, J4-34, J4-25, J4-56, J4-3, J4-103, J4-14, J4-106, J4-51, J4-87, J4-81, J4-84, J4-26, J4-117, J4-21, J4-120, J4-50, J4-109, J4-44, J4-22, J4-115, J4-123, J4-125, J4-42, J4-23, J4-83, J4-31, J5-106, J5-6, J5-41, J5-79, J5-73, J5-27, J5-90, J5-107, J5-75, J5-102, J5-65, J5-78, J5-112, J5-32, J5-111, J5-105, J5-4, J5-108, J5-38,  J5-12, J5-34, J5-68,  J5-28, J5-9, J5-37, J5-100, J5-5, J5-48, J5-3, J5-98, J5-18, J5-55, J5-59, J5-29, J5-46, J5-22, J5-13, J5-117,  J5-64, J5-104, J5-39, J5-17, J5-7,  J5-76, J5-2, J5-67, J5-116, J5-63, J5-1, J5-91,  J5-53, J5-40, J5-89, J5-115, J5-15, J5-25, J5-47 and J5-36. Considering high variability of disease pressure under natural infestation, it is important that top performing hybrids selected from the 2013/2014 growing season are validated to confirm results.

Variations in planting time observed in farmers’ fields in Kenya as well as in Babati have shown that maize crop under delayed planting has often been severely affected by MLN. In view of this, we believe good cultural practices including timely planting would significantly support other control measures to manage this disease and, therefore, needs to be investigated. Experiments will be organized to understand the key biophysical factors influencing the MLN incidence, especially in the late sown crops.

Accurate diagnosis of MLN viruses is essential to understand the host response, surveys and epidemiological studies. In 2012-13, IITA developed low-cost diagnostic tools for the detection of MCMV and MLN casual viruses. Efforts are being made to establish MLN diagnostic lab in Selian Agriculture Research Institute (SARI), Arusha, Tanzania, to backstop regional activities. Sustainability of project outputs on MLN is very desirable and requires core activities including strengthening stakeholder capacity through training on detection and identification of MLN causing viruses, upgrading available laboratory with suitable equipment for analysis of samples. It is therefore imperative that national laboratory is equipped with necessary facilities for analysis and personnel trained on analysis and diagnostic skills.

5.4 RESEARCH OBJECTIVES

- To identify MLN resistant varieties from available commercial, farmers and experimental maize varieties grown under high disease pressure.

- Assess the effectiveness of different disease management options (cultural practices) in reducing the incidence of MLN for recommendation in target maize growing areas

- Establish the prevalence of MLN and identify causative virus strains sampled from diseased maize plants in Africa RISING research sites in Babati.

- Determine key biophysical factors of MLN epidemiology

- Develop capacity for diagnosis of MLN viruses (equipping diagnostic lab and training course for relevant staff) and community empowerment on MLN monitoring and management

5.5 METHODOLOGY

- For objective 1, we plan to set up a trial composed of 150 top performing selected from the 2013/2014 evaluation. The entries in this trial will be the top performing hybrids selected from the 2013/2014 evaluations in Babati. The trials will be planted at 4-5 hotspot locations (Manyara Farm, Seloto and Sabilo) in Babati district under natural infestation. The hot spot areas in Babati have high disease pressure as three of our 2012/13 season trials planted at three of these areas were completely lost to MLN. These hotspot locations were identified during our regular visits in Babati district and during a survey on MLN conducted in 2012 in Tanzania. The experimental design to be used will be the alpha lattice design. Data will be collected on plant stand count, grain yield, days to 50% anthesis and silking, MLN disease severity (scale 1-5, with 1=no disease and 5=100% death due to disease) and MLN disease incidence based on symptoms and diagnostic tests. Data on disease incidence and severity will be recorded at three-week intervals after planting until the end of the grain filling period.

- Addressing objective 2, we plan to stagger planting, with the first planting done timely with the onset of rains and second planting two weeks after the recommended planting time. Similarly, data will be collected as described in objective 1. This is a follow up of the previous growing season.

- For objective 3, we plan to conduct surveys in farmers’ fields around Babati to establish the prevalence of the disease aiming at developing high density MLN distribution, incidence and severity map. Survey protocol established previously will be utilized for this purpose. This will be done two weeks from the time of planting with subsequent monitoring periodically during the crop development till flowering stage. Samples will be taken from diseased plants for laboratory analysis to identify virus strains prevalent in these areas. This activity was not done last season.

- For objective 4, we plan to determine the role of contiguous farming, off-season crops (maize grown using residual moisture), alternative hosts, vectors, and seed in the primary and secondary spread of MLN viruses. Relationship between the MLN incidence and weather parameters collected from the 3 AfricaRISING action sites in Babati will be investigated.

- Objective 5:

- Will involve streamlining the diagnostics operations in SARI, with necessary facilities for analysis which is currently in progress. This will be supported with training of 10 personnel on diagnostics skills. A student has already been engaged for this work.

- Further strengthening and fostering MLN diagnostic facility established at SARI through provision of supplies and retraining of staff on the job to serve MLN R&D programs in northern Tanzania.

- Organizing hands-on- training to research and extension staff from Babati, Kongwa and Kiteto in MLN diagnosis and control.

- Preparing awareness material (print; radio jingles; and video) on MLN recognition, avoidance of risk factors and implementation of IDM.

5.6 EXPECTED RESULTS/DELIVERABLES

- Hybrids with resistance/tolerance to MLN are identified and recommendations made for their utilization: a) for inclusion in national performance trials for fast track release (experimental hybrids), and, b) for upscaling in MLN-affected areas (commercial hybrids).

- Knowledge and information on the prevalence of MLN in target maize based systems is established for utilization in formulating appropriate recommendations on management strategies, determining training needs and designing information packages for public awareness.

- Effective management options recommended for up scaling in target maize growing areas.

- High density map of MLN distribution, incidence and severity in Babati, in addition to the identification of virus strains associated with MLN in designing appropriate protocols for managing the disease in the target maize growing areas.

- Preliminary knowledge on critical factors influencing the MLN outbreaks in Babati, vital for establishing integrated measures for MLN control

- Enhanced capacity for MLN diagnostics in the Manyara region in Tanzania, and availability of MLN diagnostics services for backstopping the MLN diagnostic activities in the region  At least 10 partners from relevant NARS trained in MLN diagnostics and surveillance skills

- Capacity development

  - At least one student (supported by iAgri) trained to MSc.

  - Farmers trained on identification of MLN disease symptoms and management strategies.

  - Collaboration with other projects, especially with environmental modeling for weather data from different agro-ecological zones in Babati.

  - Collaboration will be established with SARI for execution of the trials and farmer preference studies, and DALDOs for farmer selection and training;

  - MLN diagnostics support lab at SARI

  - Collaboration with ICIPE for identification of insect vectors

  - Collaboration with FAO on information exchange and engagement with broader regional coordination efforts on MLN management

  - Collaboration with ILRI on food-feed maize variety identification

  - Collaboration with CIAT on identification of best performing maize hybrids under varying agronomic management options

- Academic, including publications, conference papers

- Scientific publication(s) in refereed journal(s) and reference bulletins for extension agents and farmers

5.8 EXPECTED OUTCOMES

Short-term

- Information on awareness and management of MLN packaged, available and training delivered to stakeholders and farmers on, diagnostics, analysis, control and management of the disease

- MLN stress tolerant hybrids validated and included in national performance trials for variety release consideration.

- Information on MLN distribution for targeted control efforts

- Epidemiology knowledge leading to integrated control strategies

- MLN diagnostic support available in the region to all stakeholders, especially for testing germplasm and disease surveillance

Long-term

- Seed of MLN disease tolerant improved maize variety is available to farmers in the Babati action areas.

- Threat to food security due to MLN in maize growing areas in Tanzania arrested.

5.9 COMMUNICATION AND DISSEMINATION STRATEGIES

The project will engage the communications units at CIMMYT and IITA to publicize key project activities through print and electronic media.

5.10 LITERATURE REFERENCES

Brandes, E.W. 1920. Artificial and insect transmission of sugarcane mosaic.Journal of Agricultural Research 19: 131-138.

CIMMYT, 2012. Maize lethal necrosis (MLN) disease in Kenya and Tanzania: Facts and actions.

Nault, L. R., W. E. Styer, M. E. Coffey, D. T. Gordon, L. S. Negi, and C. L. Niblett. 1978. Transmission of maize chlorotic mottle virus by Chrysomelid beetles. Phytopathology 68: 1071–1074.

Pemberton, C.E., L.J. Charpentier. 1969. Insect vectors of sugarcane virus diseases. In: Pests of Sugarcane. (Eds. Williams JR, Metcalfe JR, Mungomery RW, Mathers R), pp. 411-425.

Wangai A., M. G. Redinbaugh, Z. M. Kinyua, D. W. Miano, P. K. Leley, and M. Kasina, G. Mahuku, D. Jeffers. 2012. First Report of Maize chlorotic mottle virus and Maize Lethal Necrosis in Kenya. Plant Disease 96: 1582.

5.11 PROJECT ACTIVITY SCHEDULE

| Activity | Oct 2015 | Nov 2015 | Dec 2015 | Jan 2016 | Feb 2016 | Mar 2016 | Apr 2016 | May 2016 | Jun 2016 | Jul 2016 | Aug 2016 | Sep 2016 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Pre-trial site stakeholder and inception meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Seed multiplication for trials (done in advance using other resources, preparation & Shipment |  |  |  |  |  |  |  |  |  |  |  |  |
| Land preparation and 1st planting |  |  |  |  |  |  |  |  |  |  |  |  |
| 1st monitoring visit and initial disease scoring, MLN surveys & trainings |  |  |  |  |  |  |  |  |  |  |  |  |
| Topdressing of trials, MLN surveys |  |  |  |  |  |  |  |  |  |  |  |  |
| 2nd monitoring visit and disease scoring, MLN survey |  |  |  |  |  |  |  |  |  |  |  |  |
| Land preparation and Second Planting (MLN) |  |  |  |  |  |  |  |  |  |  |  |  |
| Data collection (flowering, disease scoring feed quality), MLN survey |  |  |  |  |  |  |  |  |  |  |  |  |
| 3rd monitoring visit |  |  |  |  |  |  |  |  |  |  |  |  |
| Harvest maize |  |  |  |  |  |  |  |  |  |  |  |  |
| Data analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Report write-up and submission |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity building activities on MLN monitoring and control |  |  |  |  |  |  |  |  |  |  |  |  |

* The 2016 activity schedule involves two time planting (early planting in mid Dec-early Jan and late planting in late March or early April)

5.12 BUDGET

| Line item | IITA Budget | CIMMYT Budget |
| --- | --- | --- |
| Personnel |  |  |
| Staff time | 9000 | 10000 |
| Consultant/Research technician | 13000 | 5000 |
| Research consultants/Partners | 5000 | 2000 |
| Research Costs |  |  |
| Seed production costs (hybrid seed-pollination costs-pollination bags, labor, irrigation costs, fertilizers) , Field trial set up, management (planting, weeding, fertilizers, harvesting, labor), data collection and field days | 3000 | 20000 |
| Initiate release of promising MLN tolerant hybrids in National performance trials | 0 | 10990 |
| Field surveys and virus diversity and mapping (objective 3) | 9000 | 0 |
| Epidemiological studies – MLN mapping and analysis | 7000 | 6000 |
| Strengthening of MLN diagnostics lab at SARI (objective 5) | 0 | 0 |
| Training in MLN diagnostics and surveillance (objective 5) | 9300 | 0 |
| Piloting community phytosanitation and Integrated Disease Management | 10000 | 8000 |
| SI indicator measurements | 4500 | 5500 |
| Local and International travel | 9000 | 8000 |
| Vehicle costs | 600 | 5000 |
| Office equipment and supplies | 1500 | 2012 |
| Sub-total (Direct costs) | 80900 | 82502 |
| Indirect costs , 15% CIMMYT |  | 12375 |
| Institutional totals | 80900 | 94877 |
| Theme Total | 175,777 |  |

5.13 LOGICAL FRAMEWORK FOR 2014/2016

| ESA Master logframe component | Management of Maize Lethal Necrosis disease, logframe |  |  |  |
| --- | --- | --- | --- | --- |
| ESA Logframe Output (Reference) | Theme Outputs: | Objectively verifiable indicators | Means/Source of Verification | Important assumptions |
| Research Output 8: Innovations that address emerging agricultural production challenges deployed | Output 8.1: Integrated Maize Lethal Necrosis (MLN) management options validated and recommended for use: - Top performing maize varieties validated for MLN resistance - Best bet agronomic and cultural practices validated and recommended for use - High density map for MLN distribution in Babati - Information on key epidemiological factors of MLN outbreak established - Information on virus strains associated with MLN in the target maize growing areas established & measures taken for designing appropriate protocols for managing the disease - A full functional ELISA-based lab established at SARI personnel from NARS trained in MLN diagnostics and surveillance | 8.1.1. Number of maize varieties validated for resistance to MLN resistance and entered in national Performance Trials (NPT) 8.1.2. Number of best bet agronomic and cultural practices validated and recommended for use. 8.1.3. Available information on virus strains associated with MLN in the target maize growing areas. 8.1.4.Available high density map for MLN distribution in Babati 8.1.5. Available information on virus strains associated with MLN and measure taken for designing appropriate protocols for MLN management 8.1.6. Available and functional ELISA based lab established and number of personnel from NARs trained in MLN diagnostics and surveillance | 8.1.1. Field reports, government annual reports 8.1.2. Project reports, government reports 8.1.3. Project reports 8.1.4. Project reports 8.1.5 Project reports 8.1.6. Project reports, lab reports, training reports | 8.1.1. Availability of fields for testing, good rain season, good disease pressure, stable political environment 8.1.2. Availability of fields for testing, good rain season, good disease pressure, stable political environment 8.1.3. disease occurrence 8.1.4. disease prevalence, conducive environment for disease outbreak 8.1.5. disease occurrence 8.1.6. Support from SELIAN |
| Activities |  | Milestones | Timeline | Lead Responsibilities |
| 8.1.1.Validate performance of selected maize varieties for resistance to MLN 8.1.2. Validate agronomic and cultural practices as options for MLN management |  | Data on key traits collected and analyzed, and resistant/tolerant varieties validated by September, 2016 Data on key traits collected and analyzed, and effective MLN management options validated and recommendations made by September, 2016 | October 2015 to September 2016 October 2015 to September 2016 | CIMMYT |
| 8.1.3. Establish high density map of MLN distribution in Babati 8.1.4. Determine the key epidemiological factors of MLN outbreak 8.1.5. Identify virus strains associated with MLN, formulate measures and design appropriate protocols for managing the disease in the target maize growing areas. 8.1.6. Develop capacity for monitoring and diagnosis of maize viruses, including MLN 8.1.7. Piloting community phytosanitation and integrated disease management (IDM) for MLN control 8.1.7.1. Select two communities in MLN hotspot areas in Babati ; obtain community buy-in for implementation of in community action against MLN. 8.1.7.2. Develop appropriate phytosanitation and IDM methods based on current knowledge (from AfricaRISING activities and other projects) against MLN and pilot in selected communities. 8.1.7.3. Organize farmer field schools, training-of-trainers in out-scaling phytosanitation and IDM. 8.1.7.4. Monitor MLN incidence and severity during cropping season. 8.1.7.5. Apply in selected fields to assess AflaSafe to assess its effectiveness in reducing ear rots and aflatoxin contamination (Note: collaborative activity with mycotoxin component of AfricaRISING). |  | 8.1.3. Surveys during crop season [pre- (Nov-Dec) and post (May-Jun) main (Jan-April) crop season) completed by June 2016; analysis of survey samples for MLN viruses completed by July 2016; MLN distribution map developed by Aug 2016 8.1.4. By Dec 2015, organize trials in three agro-ecologies; monthly monitoring reports till harvest. 8.1.5. By Dec 2016, information on virus strains associated with MLN in the target maize growing areas established & measures taken for designing appropriate protocols for managing the disease 8.1.6. A full functional ELISA-based lab established at SARI by Jan 2016; 10 personnel from NARS trained in MLN diagnostics and surveillance 8.1.7.1. Farmers adopting new IDM approach to MLN leading to reduced incidence and severity 8.1.7.3. Knowledge on new IDM model for effective control of MLN for further improvisation and out-scaling. 8.1.7.5.1. Integration of AflaSafe (aflatoxin control) into MLN management by Sept 2016. 8.1.7.5.2. Knowledge on interaction between MLN, ear rots and aflatoxin contamination by Sep 2016. | October 2015 to December 2016 | IITA |

5.14 FtF INDICATORS 2015/16

| Indicator / Disaggregation | 2016 |
| --- | --- |
|  | Target |
| 4.5.2(2): Number of hectares under improved technologies or management practices as a result of USG assistance (RIA) (WOG) | 4 |
| Technology type |  |
| crop genetics | 2 |
| pest management |  |
| disease management | 2 |
| 4.5.2(5): Number of farmers and others who have applied new technologies or management practices as a result of USG assistance (RIA) (WOG) | 10 |
| New/Continuing |  |
| New |  |
| Continuing | 10 |
| Disaggregates Not Available |  |
| Sex |  |
| Male | 6 |
| Female | 4 |
| Disaggregates Not Available |  |
| 4.5.2(7): Number of individuals who have received USG supported short-term agricultural sector productivity or food security training (RIA) (WOG) | 40 |
| Type of individual |  |
| Producers |  |
| People in government |  |
| People in private sector firms |  |
| People in civil society |  |
| Disaggregates Not Available |  |
| Sex |  |
| Male | 25 |
| Female | 15 |
| Disaggregates Not Available |  |
| 4.5.2(12): Number of public-private partnerships formed as a result of FTF assistance (S) | 5 |
| Agricultural production |  |
| Agricultural post harvest transformation |  |
| Nutrition |  |
| Multi-focus |  |
| Other | 5 |
| Disaggregates Not Available |  |
| 4.5.2(39): Number of new technologies or management practices in one of the following phases of development: (Phase I/II/III) (S) |  |
| Phase 1 Number of new technologies or management practices under research as a result of USG assistance | 5 |

Theme 6: Institutional cooperation and co-learning

6.1 RESEARCH TEAM (Team leader: Per Hillbur)

| Name | Gender | Institution | Job title | Disciplinary expertise | Qualification | Project role/responsibility | % time commitment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Per Hillbur | M | Malmö University | Research Consultant | Human Geography | Phd | Principal Investigator | 50 days |
| Festo Ngulu | M | IITA-Arusha | Research Consultant | Crop Science | MSc | Research team coordinator | 20 % |
| Haroon Sseguya | M | IITA | Scaling Expert |  |  | Scaling Expert, platform team | 3 % |
| Gundula Fischer | F | IITA- Arusha | Gender expert | Anthropology, Sociology | PhD | Gender Expert, platform team | 3 % |
| N N | To be recruited |  | Facilitator | Community development |  | Facilitator, strategic level |  |
| N N x 3 | To be recruited |  | Facilitators | Community development |  | Facilitators, Operational level |  |

6.2 SUMMARY AND JUSTIFICATION OF ACTIVITIES/OUTPUTS

The idea of bringing different stakeholders together to address a particular problem or a range of challenges is not new. In Africa RISING, the prime vehicle chosen for multi-stakeholder interaction is called research-for-development (R4D) platforms and innovation platforms (IPs).

In this overview on existing and planned platforms in Babati District, Tanzania, I will use R4D platform for the district level platform, also identified as a “strategic level platform”, while we talk about “grassroot level platforms”, operating at ward and village level. The latter may also be called “operational level platforms”.

The first R4D platform in this context, called JUMBA (Jukwaa la Utafiti kwa Maendeleo Wilaya ya Babati – Babati District R4D platform), was inaugurated in April 2014, and has eighteen months of operation up to now. The next step is to initiate operational level platforms in a number of wards in Babati District in order to respond to demands of scaling of technologies, but also to initiate a demand-driven process based on local communities’ decision-making.

The rationale for employing R4D platforms is to link a range of organizational actors that can promote the simultaneous technological, social and institutional change needed for sustainable intensification (Hillbur 2013b). This may include a range of activities, but from a research point of view, the R4D platform responds to the establishment of three different communicative strategies: network building, social learning and conflict management (Leeuwis and Aarts 2011:31).

We need better understanding of the added value of R4D platforms under different conditions. As with many open-ended processes, we lack insights in what exactly makes R4D platforms effective in changing mainstream practices depending on policy environment, the range of issues involved or the scale(s) at which the platform operates. There is also an urge to know more about how these platforms function when organized around other constructs than just value chains.

The primary beneficiaries are the small-scale farmers and other stakeholders in rural areas who, through the platforms, will have better access to information, technologies, skills, credits, markets, etc., supporting agricultural intensification for improved and sustainable livelihoods. Depending on the methodology used for involving farmers and other stakeholders in research, they will increase their understanding of the dynamics of these networks and the conditions/requirements of their success. An important goal for the platform is that results (in the form of interventions, lessons learned and mediated change) will inform decision makers, public and private players in agricultural development and educators about how R4D platforms can work to promote technological, social and institutional change, in order to put sustainable intensification to scale (Hillbur 2013b)

Setup of the platform teams

An important lesson learned from the first year of operation at the strategic level is that the platforms need an experienced support team to initiate and guide activities as well as to provide training in platform management, communication of research-for-development and visionary work with local communities.

For 2015/16, we have designed a support structure that is based on our experiences so far combined with a dialogue with colleagues in Humidtropics/East African Highlands and ILRI/Ethiopia. For 2014, the budget for platforms has basically covered a part-time (non-local) consultant and expenses for a number of platform meetings at the strategic level. The emphasis so far has been on achieving sustainability and self-reliance of JUMBA within the first phase of Africa RISING. This has included a focus on formalization and documentation of a new local organization (JUMBA), although less has been devoted to establish a wide understanding and recognition of the platform idea itself. This has resulted in few operational activities on the ground, and an even stronger dependence on donor/project activity rather than the contrary.

Strategic level (district)

Facilitator, stakeholders

Operational level (ward)

Facilitators, stakeholders

Platform team

PI WT6, Research Coordinator,

Gender, Scaling, Communication

We therefore suggest that a strategically oriented platform team is set up at the project level. This will include the PI (consultant) and the local research coordinator, with support of the AR gender specialist and the AR-NAFAKA scaling specialist. In addition, the team should be complemented by a communication specialist to advise the team on training and documentation matters. The platform team resumes monthly to follow up on the progress of the platforms.

According to experiences elsewhere, the role of facilitation and training cannot be underestimated in platform management. We therefore suggest resources for a facilitator at the strategic level (high proficiency in English and Swahili and excellent communication skills) and 2-3 local facilitators at the operational level (with strong communication skills at the local level). The facilitators should be politically unbound and able to work independently with development of local organization of the platforms. Experiences from elsewhere may suggest that the local facilitators are nominated by the local communities.

The integration of platform activities in AR regular research

Until now, the R4D platform activities have been largely research-driven, as the incentive has been strongest for Africa RISING to make things happen. Still, parts of the research team have conducted other activities separately which may as well be coordinated as platform activities. These activities include feedback meetings with farmers and local communities, training sessions with stakeholders on particular technologies, etc. This suggest a role of the district level R4D platform as a hub for research coordination and capacity building, which would be helpful both for research and for the local community, including government interventions. There seems to be limited incentive for the local community to initiate activities. An option would be to further involve private sector representatives and NGOs to stimulate the incentives for the local community.

Furthermore, although Africa RISING is primarily a research program, we are interested in the impact and potential scaling of introduced technologies as well as the well-being of different groups of beneficiaries. This calls for a forum where research can be initiated based on collective learning, social interaction or straightforward needs of the local communities. The platform structure above should be able to address this.

After fifteen months with JUMBA, the lesson learned is that we should revisit some local networks, institutions and stakeholders to strengthen JUMBA, particularly to discuss collaboration and incentives for private actors and NGOs operating locally. This should be a priority in the communication strategy for Africa RISING and JUMBA in Babati for next year.

Performance indicators of platforms

Last, but not least, we must learn more about how to follow up and measure the progress and impact of platforms. As we are still in a start-up phase for platform activities, it is time to set up a structure for monitoring and evaluation of platforms. Below are some aspects that should be addressed the following year:

- Platforms and their contributions to development outcomes. Should we identify success criteria? Which are the most important development outcomes to be addressed by platforms?

- Efficiency and effectiveness of platforms. Can platforms save time and resources spent on other activities? For which kind of interventions are platforms suitable – or necessary?

- Sustainability in the local community. Is it reasonable to talk about initiating something that goes beyond the project term? How can we measure sustainability in platforms? What is a reasonable exit strategy?

6.3 ACTIVITY SCHEDULE (R=reports on activity, DR= Draft/midterm report)

6.4 ACTIVITY DESCRIPTION

| year | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| month | O | N | D | J | F | M | A | M | J | J | A | S |
| Activity/output 1: Consolidation of R4D platform at district level (strategic platform) |  |  |  |  |  | DR |  |  |  |  |  | R |
| Activity/output 2: Establishment of 6 grassroot level platforms at ward level (operational platforms) |  |  |  |  |  | DR |  |  |  |  |  | R |

| Target Outputs (ESA Logframe) | Activity | Activity description | Deliverables | Responsible P Institution |
| --- | --- | --- | --- | --- |
| Output 4: R4D and Innovation platforms influencing stakeholder practices established | 4.1 Consolidation of R4D platform at district level (strategic platform) | 1) Revisiting stakeholders - evaluation 2) Training/capacity building of JUMBA stakeholders aiming at independent leadership and ownership of JUMBA. 2) Promotion of JUMBA within and outside Babati District by help of communication strategy and material. 3) Technical support from AR platform team on organizational, process and gender matters (monthly update). 4) 2 stakeholder meetings | Functional R4D platform at district level | PI, IITA |
|  | 4.2 Establishment of 6 grassroot level platforms at ward level (operational platforms) | 1) Selection of wards, sensitization meetings at ward level. 2) Preparations for demand-driven activities at ward level based on available documents on land use, agriculture, etc. 3) Training of facilitators. 4)Facilitation of meetings and activities at ward level | Six grassroot level platforms identified and initiated by May 2016 | PI, IITA |

6.5 FtF TARGETS FOR 2015-16

| Indicator / Disaggregation | 2016 |
| --- | --- |
|  | Target |
| 4.5.2(11): Number of food security private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) receiving USG assistance (RIA) (WOG) | 7 |
| Type of organization |  |
| Private enterprises (for profit) |  |
| Producers organizations |  |
| Water users associations |  |
| Women's groups |  |
| Trade and business associations |  |
| Community-based organizations (CBOs) | 7 |
| Disaggregates Not Available |  |
| New/Continuing |  |
| New | 6 |
| Continuing | 1 |
| Disaggregates Not Available |  |
| 4.5.2(27): Number of members of producer organizations and community based organizations receiving USG assistance (S) | 20 |
| Type of organization |  |
| Producer organization | 5 |
| Non-producer-organization CBO | 15 |
| Disaggregates Not Available |  |
| Sex |  |
| Male | 10 |
| Female | 10 |
| Disaggregates Not Available |  |
| 4.5.2(42): (4.5.2-28) Number of private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) that applied new technologies or management practicies as a result of USG assistance (RIA) (WOG) | 7 |
| Type of organization |  |
| Private enterprises (for profit) |  |
| Producers organizations |  |
| Water users associations |  |
| Women's groups |  |
| Trade and business associations |  |
| Community-based organizations (CBOs) | 7 |
| Disaggregates Not Available |  |
| New/Continuing |  |
| New | 6 |
| Continuing | 1 |
| Disaggregates Not Available |  |

6.6 BUDGET

| Activity/line item | Number | Cost per item | Total |
| --- | --- | --- | --- |
| Principal investigator | 50 days | 400 | 20,000 |
| International travel | 4 trips | 1500 | 6000 |
| Perdiem | 30 days | 180 | 5400 |
| Perdiems | 20 days | 40 | 800 |
| Vehicle/driver: Babati/Arusha | 30 days | 150 | 4500 |
| Communication support |  |  | 5000 |
| Facilitator, grassroots level | 60 days | 40 | 2400 |
| Stakeholder training JUMBA 20-25 people | 1 session | 2,000 | 2,000 |
| Facilitator training-6 people | 10 days | 250 | 2500 |
| Platform meetings | 2 district level | 2,000 | 4000 |
|  | 6 grassroots level | 1500 | 9000 |
| Total 2015/16 |  |  | 61,600 |