BABATI R4D PLATFORM (JUKWAA LA UTAFITI KWA MAENDELEO BABATI-JUMBA)

PROPOSED ACTIVITIES DEVELOPED FOLLOWING JANUARY 2015 JUMBA RETREAT AT SARI-ARUSHA

OBEJCTIVE 1: CREATE RELIABLE MARKET FOR AGRICULTURAL PRODUCTS FROM BABATI

| Activity | Rationale | Inputs and Costs | Expected Outputs | Indicator | Time frame | Responsible person/institution | Potential funding |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1.Conduct 5 days training to 50 extension workers from the 25 wards of Babati to become trainers on Farming as Business to farmers | Farmers in Babati district do not take farming as business. The ward purpose of the training is to impart entrepreneurial skills | Resource persons M&E personnel Conference facilities Training materials Breakfast | Each ward have a trainer for Agriculture as business | Number of trainees | May to June 2015 | District Council MVIWATA World Vision SARI AVRDC REPOA EU/Farm Africa ILRI IITA | Africa Rising Babati District Council |
| 1.2.Conduct training on Post Handling Management (PHM ) for maize and maize stovers to 50 ward ext Workers and 190 farmers from 19 wards | a).The needs to minimize crop losses and mitigation of health risks to consumers. b).Increase feed availability and animal productivity | - Human resource - Training material - Facilitation - Transport | a) Extension workers in Babati are aware and able to institute PHM to 190 maize farmers. b) Farmers practice PHM of maize crop c) Maize Products at the market free from health hazard materials d) Post harvest losses reduced by 50% In the trained wards e) Feed availability ensured throughout the year f) Expanded zero grazing in the district | a)Number of farmers practicing PHM b)Incidences of food poisoning c) Number of farmers practicing zero grazing | June – Sept 2015 | IITA Babati District Council Ext Workers bag suppliers choppers/balers suppliers FIDE TAP | Africa RISING SNV TAP |
| 1.3.Enhancing the acquisition and use of appropriate processing and storage facilities | Minimize post harvest losses and reduce health risks to consumer Increase feed availability to livestock. Decrease labour costs. | - Human resource - Suppliers - Seed money | a) Storage and processing equipment available to farmers b) Products at the market free from health hazard materials c) Post harvest losses reduced in the targeted wards | Farmers purchase and use the storage and processing facilities | June – sept 2015 | IITA DC Ext Workers bag suppliers choppers/bailers suppliers FIDE TAP | Africa Rising SNV |
| 1.4.Training existing farmer groups on group dynamics and facilitate formation of new groups | Support economic groups for investment in agriculture | - Transport - Resource person facilitation (cooperatives) - Conference facility - Training material | Existence of registered creditable Farmers groups | Number of creditable farmer groups | 2016 | Babati District Council Financial Institutions SIDO SACCOS/VICOBA | ORGUT/ALAT SNV, Barclays Bank |

OBJECTIVE 2: CREATE ENABLING ENVIRONMENT FOR EFFICIENT PRODUCTION OF AGRICULTURAL PRODUCTS (LIVESTOCK AND CROPS)

| Activity | Rationale | Inputs and budget | Expected Output | Indicator | Time frame | Responsible person/institution | Potential funding |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 2.1.Facilitate processing industries to add values to products through proper packaging, labeling and promotional services | a) Value addition increase price and earnings from sale of products b) Assists in promotion of products | Promotional materials Information transfer facilities | Obligation of processing industries to pack and label their products | Produced and marketed products well packed and labeled | continuous | TFDA, JUMBA, Babati District Council DAICO, DLFO, Workers, Trade Officer Health Officer | JUMBA initiatives |
| 2.2.Develop market strategies for crop and livestock for price stabilization | - Crop and livestock products are seasonal and rather perishable goods that need proper storage and their price fluctuates considerably with time and season - Price fluctuation is stabilized between seasons where there is a control/speculative price baseline | JUMBA initiatives | Existence of pricing system where indicative prices are set by a pricing authority | All products have indicative price irrespective of season but with quality consideration | Continuous | JUMBA, Trade Officer, Planning Officer, DAICO, DLFO | Babati District Council, JUMBA initiatives |
| 2.3.Facilitate proper land use planning with emphasis on land ownership and title deeds | - Land conflicts are minimal where proper land use plan exist and people are well informed of the partitions (participatory done) | - Promotional materials - Human resource - Facilitations | There are areas set aside for different human activities and environment conservation | Areas for crops, livestock, settlements and other human activities is well set in the district | June 2017 | District Council, Land Officers, Land Ministry, PMO-RALG, IITA | AfricaRISING BABATI District Council JUMBA |
| 2.4.Contribute to development and enforcement of by-laws | - Land conflicts are minimal where proper land use plan and by laws are developed and enforced | - Facilitation to the JUMBA advocacy team | Policy and by laws, regulations enforced and areas where new initiative is required identified | Policy and by laws, regulations implemented, Contemporary by laws and regulations in place | continuous | JUMBA, Bunge, PMORALG, Babati District Council | Babati District Council PMORALG |

OBJECTIVE  3: CAPACITY BUILDING OF JUMBA

| Activity | Rationale | Inputs and budget | Expected Output | Indicator | Time frame | Responsible person/institution | Potential funding |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1. Training of 30 extension officers on GAP: -Soil conservation, Fertility management, Optimum spacing & fertilizer application -Forage production and utilizations -Pests and disease management | Stimulate adoption of improved crops and livestock management practices. | Stationery Transport Perdiem /allowance Communication M&E personnel Land survey facilities | Knowledgeable extension staff, Adoption of soil and water conservation. Higher crop yield | Number of trainees Number of topics covered | August-September 2015. | Extension officers, Researchers, CSOs, land use experts,VEO and WEO IITA ILRI MLFD | Babati DC |
| 3.2.Capacity building on maize QDS production in 3 wards | QDS production will minimize the issue of inaccessibility/high price of certified seeds at the village level | Allowance/ perdiem Fertilizer Seeds Pesticides | Assured availability of improved seeds at village level Reduced adulteration of seeds Higher yields Higher adoption rates of improved varieties | Number of QDS producers Quantity of QDS produced and marketed | October-November 2015 | TOSCI Extension workers Input suppliers. SARI IITA CIMMYT CIAT | Seed Companies |
| 3.3.Sensitization on Artificial insemination in six wards | Promotes improvement of local breeds | Facilitations Improved semen Preservation facilities | Increased number of improved breeds Increased livestock productivity | Number of cows/bulls of specific improved breeds No. of farmers keeping improved breeds | Feb -March 2016 | NAIC DED Babati TALIRI IITA, ILRI | NAIC-USA RIVER. BABATI DC |

OBJECTIVE  4: STRENGTHENING  PLATFORM  CAPACITY

| Activity | Rationale | Inputs and budget | Expected Output | Indicator | Time frame | Responsible person/institution | Potential funding |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1.Establishment of JUMBA at ward level through sensitization meetings in 6 wards. | Active platforms at ward level enhance JUMBA's performance at higher level. | Stationery Perdiem /allowance Transport Communication | Existence of JUMBA in 6 wards. | No. of meetings conducted Farmers’ perception | June -July 2015 | Extension officers, Community D officers, VEOs and WEOs, Ward councilors, Farmers, Livestock keepers and Religious leaders | Africa RISING Babati DC |
| 4.2. Publicizing JUMBA activities and success stories through media such as local Website, Radios, TV, Newspapers, and Fliers. | Community awareness on the vision, mission sand activities of JUMBA opens up scope for attracting potential partners/collaborators. | Stationery & relevant logistics | JUMBA widely publicized to farming community and other strategic stakeholders | Number of articles developed and disseminated, number of programmes broadcasted | Continuous | Media stations JUMBA management team. | JUMBA members |
| 4.3.Conduct constitutional meetings Annually | Conducive forum for self evaluation, sharing experiences, lessons and plan for coming activities. | Stationery Transport Communication Allowance/Perdiem Conference hall | JUMBA activities evaluated and way forward plans developed. | Number of constitutional meetings conducted. Number of participants to the meetings Beneficiaries remarks | April and October (Annually) | All JUMBA stakeholders | AfricaRISING BABATI District Council JUMBA |

OBJECTIVE 5: ATTRACT   YOUTH TO FARMING AS A BUSINESS THROUGH PROVISION OF FEASIBLE INCENTIVES

| Activity | Rationale | Inputs and budget | Expected Output | Indicator | Time frame | Responsible person/institution | Potential funding |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5.1.Conduct special training for 20 youth to become entrepreneurial poultry and vegetable producers | To entice youth to engage in vegetable and poultry production as economic activity | Seed money Trainable youths Fees Facilitation | Youths becoming entrepreneurs in farming | Number of youths doing farming as business | July 2015 – June 2016 | Training institutions Babati District DAICO/DLFO Ext Workers Ward Executive Officers | Vijana SACCOS Babati District Council |
| 5.2.Link youth to credit facilities(FIs) | Youth have limited capital for investment; hence the need to source back up funds from credit institutions | JUMBA human resource | Vijana Groups are connected to financial institutions for credit aquisition | Volume of credit from CIs to Vijana groups | May to June 2016 | JUMBA Management team Vijana Group Leaders | Self financing |