Sustainable Intensification of Maize-Legume Systems for the Eastern Province of Zambia (SIMLEZA)

Project Summary

Summary:

Social wellbeing and economic development in Zambia is strongly linked with productivity growth in agriculture and sustainable management of farming systems. Maize is the main staple food crop grown widely in the country and critical for ensuing food security for the poor. Low income smallholder farmers also produce some grain legumes (e.g. soybean, beans and groundnuts) within the maize-based systems, which provide a cheap source of proteins. Legumes provide cash and also fix nitrogen and contribute to enhancing soil fertility in maize based systems. The cash earned from selling legumes represents valuable income for women to educate their children and invest in healthcare and other necessities. This project focuses on eastern Zambia where small-scale farmers depend for their livelihoods on maize-legume mixed systems characterized by low productivity, extreme poverty, poor soil fertility and environmental degradation. The project aims at leveraging science for sustainable productivity growth, intensification and diversification of maize based systems in the region through new varieties, improved agronomic practices, legumes integration, and improved access to markets and services. It addresses Pillar 1 of the Food Security Initiative of CCADP. The program will be jointly managed and implemented by IITA and CIMMYT in collaboration with the national partners (ZARI, GART, University of Zambia, extension agencies, NGOs and seed companies and input suppliers).

The SIMLEZA project will adopt participatory and value chain approaches and aims at increasing food security and productivity, in the context of climate risk and change, through the development of more resilient, profitable and sustainable maize-legume farming systems and institutional innovations that improve farmers’ access to technologies, inputs and markets. The five main objectives are: (a) to enhance technology targeting and delivery for the poor (and women) by identifying systemic constraints and options for improving input and output value chains and impact pathways; (b) to identify productive and resilient agronomic practices for intensification and income growth in maize-legume cropping systems; (c) to enhance the diversification of maize, soybean and cowpea use at household level through processing, product diversification and marketing; d) to increase the range of maize and legume varieties through  participatory screening, testing and release, and enhanced delivery of seeds of  adapted varieties; (e) to enhance the capacity of national partners in technology generation, deployment and service delivery for the poor. Gender mainstreaming, monitoring and evaluation will be cross-cutting activities. . Improved maize and legume varieties and value chains innovations will be tested through on-farm research, demonstrations and pilot interventions in input and produce marketing chains.

Our vision is to achieve R4D gains that contribute postiviely to reducing poverty, hunger, malnutrition, and environmental degradation for poor smallholder famers particularly women in eastern province. An indicator of success wil be increase in maize and legume yield by 25% in project communities over four years. The yield increase will be achieved through yield stability and yield level grain through use of better adapated varieties, improved crop management, responsiveness to modern inputs, conservation agriculture and biological nitrogen fixation. We expect benefits from grain value and fertilizer subsititive value, improved food security and nutritional security.  SIMLEZA will directly benefit at least 30,000 farm households in four years. Participatory research and development with farmers, extension agents, NGOs, and agribusiness along the value chains will be coordinated through institutional innovations that strengthen access to information, technologies and services for the poor. The work will be linked regionally with the ACIAR supported project (SIMLESA) on maize-legume systems; BMGF supported Drought Tolerant Maize Project, Tropical legumes II and other initiatives. The project will be coordinated by a lead scientist with regular oversight provided by a project management committee composed of program directors from CIMMYT & IITA and representatives of national partners.

I. Problem Analysis (2-3 pages)

Agriculture is vital for attaining broad-based economic growth for meeting the global development objectives of alleviating poverty and hunger and improving nutrition, health, and social wellbeing in Zambia.  The majority of the poor live in rural areas where, over 75% of the population depend on smallholder farming for subsistence and livelihoods. About 85% of the smallholder farmers cultivate maize as a primary staple crop under rain-fed systems.  It is estimated that over 55% of the daily calorie intake in Zambia is derived from maize with the average consumption of about 85-140 kg per year.  Eighty percent of maize in Zambia is produced by smallholder farmers under low soil fertility, frequent drought, and limited use of high yielding varieties and inorganic fertilizer. The smallholder production systems are also characterized by undeveloped markets for agricultural products and weak extension services and technology delivery systems. As a result maize yields in Zambia (1.5 t/ha) are amongst the lowest in the world. While the national maize area has increased from 0.5 million in the 1980s ha to about 1 million ha, maize production has not shown appreciable growth except during the last 2-3 years when domestic maize production exceeded the national food requirements of 1.2 million ton per annum. Improved access to maize hybrids and fertilizers through government subsidies, along with good rains, has contributed to increased production of maize in the country. Despite the national surplus, several smallholder farmers across the country and especially the resource poor farmers and women who lack capital and assets to invest in improved production methods are deficit producers and net buyers of maize. This is particularly true for the drought-prone areas and areas with limited market access for value chain development and delivery of inputs and services to growers.  Average yields still remain low for many smallholder farmers, which vary between 1 and 2 tons/ha, depending on weather conditions, notably rainfall, and access to fertilizers and improved seed.

Legumes are key components of maize based systems in Zambia. Legumes provide dietary protein especially to the poor who cannot afford animal protein. Legumes often attract high prices and are widely used in intercrops/rotations in maize systems.  Legumes reverse soil degradation through nutrient supply. For example, the net soil nitrogen accrual from the incorporation of grain legume residue in the soil can be as much as 140 kg N/ha. Thus, using legumes in the farming system will help reduce dependence on fertilizers for cereals, which reduces the cost of production for resource poor farmers and minimizes environmental pollution. Dual purpose soybean and cowpea varieties are particularly well suited for the poor, especially women, as they provide highly nutritious fodder for livestock. Cowpeas are also well suited in drought prone areas since they are drought tolerant and mature within 2 months and provide food during the ‘hunger period’. Cowpea leaves are used as a high protein vegetable and therefore contribute to resolving malnutrition. Soybean is an important legume in Zambia and is typically grown in rotation with maize or wheat. Area planted to soybean and production increased from less than 5,000 ha and 7 000 tons in the 1980s to over 62,000 ha and 110, 000 tons in 2010. Much of the increase in soybean production is driven by area expansion, while yields/ha have largely stagnated. The increase in soybean production is mainly driven by the demand from the poultry sector, which has been growing at around 20% per year. Around 90% of domestic soybean cake goes to the poultry sector.

Stabilizing and increasing productivity of maize and legumes in the face of recurring droughts and poor soils is a major priority for improving food security. The use of drought tolerant maize varieties and soil enhancing legumes that also provide nutritional and income benefits for the poor in the maize-based systems provide considerable promise in boosting productivity. Integrated Crop and Soil Fertility Management (ICSFM) technologies are additional options for resource-poor smallholder farmers to achieve food security.

Enhancing the impact of maize and legume technologies in Zambia however requires addressing key socioeconomic and policy constraints that limit farmer (especially women’s) access to new technologies, including access to markets for seeds, fertilizer as well as credit to finance these investments. As a landlocked country, fertiliser prices in Zambia are one of the highest in the world (currently close to US$800/ton for urea in urban centres). Farmers also need access to output markets and effective grain storage and processing methods. To resolve these challenges, CIMMYT and IITA along with national partners have been developing high yielding and risk reducing maize and legume varieties. CIMMYT and IITA have also been developing and testing productivity-enhancing and climate change mitigation technologies in rainfed maize-legume systems such as drought tolerant and high yield varieties and crop management options based on principles of conservation agriculture. The Drought Tolerant Maize for Africa (DTMA) project has for example developed several stress tolerant maize OPVs and hybrids in Zambia that need participatory evaluation and promotion in maize-legume systems. The SIMLEZA project is a multi-institutional and multi-disciplinary effort to improve the productivity of maize-legume systems in Eastern Province to enhance food security, nutrition and incomes for smallholder farmers, especially women who play a key role in agriculture and family well-being in Zambia.

II.Goal,  objectivies and main activities (1-2 pages)

The goal of SIMLEZA is to increase food security and incomes for the resource poor and women farmers by increasing the productivity, market access and resilience of selected maize-legume systems in eastern province of Zambia. The objectives and main activities for each objective are listed below.

- Objective 1: To enhance technology targeting and delivery for the poor (and women) by identifying systemic constraints and options for improving input and output value chains and impact pathways

  - Socioeconomic and GIS characterization of targeted maize-legume farming communities and households  and selection of research sites/communities

  - Conduct a baseline study of maize and legume production constraints and opportunities, technology choices, resource use patterns, profitability, and market access

  - Desk study of maize-legume value chains to identify constraints, investment opportunities, and institutional innovations for increased adoption of improved technologies (seed, ISFM including conservation tillage, etc.)

  - Conduct early adoption and impact studies of improved maize and legumes varieties and ISFM technologies and define strategies for scaling up/out pro-poor innovations for greater impact on food security.

- Objective 2: To enhance adoption and adaptation of  productive and resilient agronomic practices and local innovation systems for intensification and income growth in maize-legume cropping systems

  - Conduct discussions with innovation platform partners to identify agronomic and seed technologies to be tested on-farm in each of the targeted communities

  - Evaluate crop production technologies (hybrids/varieties, agronomic practices) for adaptation and adoption in the targeted agro-ecologies

  - Establish on-farm demonstration/ participatory variety selection (PVS) trials of maize-legume rotations and integrated innovations to identify single and dual-purpose germplasms and ICSFM combinations that increase productivity and incomes from maize-legume systems

  - Facilitate improved linkages between farmers and input suppliers for timely access to seeds, fertilizers and agrochemicals.

  - Mobilization of farmers using the channels of mass communication (radio, video, TV etc.) and field days to create public awareness of available technologies and help farmers adopt them successfully

- Objective 3: Enhance the diversification of maize, soybean and cowpea use at household level through processing, product diversification and marketing

  - Assess the nutritional status and diet quality of women of child bearing age and their under 5 children in target communities

  - Adapt and promote household level technologies for the production, processing, and storage of nutritionally improved traditional maize food products and soybean and cowpea based novel foods

  - Expand agro-processing and markets for maize, soybean, and cowpea products

  - Marketing outlets for maize, soybean, and cowpea products developed and expanded to increase incomes and improve nutrition

- Objective 4: To increase the range of maize and legume varieties through  participatory testing and release, and enhanced delivery of seeds of locally adapted varieties

  - Conduct on farm trials to identify stress tolerant and higher yielding maize and legume varieties through farmer- and seed company-participatory evaluation and G X E analysis

  - Provide varietal performance data to accelerate variety release and registration

  - Develop maize and legumes seed road maps to enhance the availability of maize and legume seeds and integrate into the work plans of public and private sector partners

  - Increase production and availability of breeder and pre-basic seed of farmer and market preferred maize and legume varieties to stimulate the market and community based seed production and supply

  - Facilitate the establishment of functional community based seed production (especially by women’s groups) and develop collaborative partnerships with seed companies to increase the supply and diffusion of certified hybrid maize, soybean and cowpea varieties to resource poor farmers and women

- Objective 5 :To enhance the capacity of national partners on targeting, technology adaptation, trial management, seed and input supply and value chain development

  - Assess the training needs of women and men farmers, researchers, extension agents and private sector, and develop appropriate training programs

  - Train women and men farmers, farmers’ associations, women groups and extension personnel in community-based seed scheme in the production and marketing of quality assured seeds

  - Train smallholder farmers, technicians and extension agents on appropriate crop management practices and participatory variety selection (PVS)

  - Train small and medium scale processors and entrepreneurs on  storage/processing systems for maize and legumes

  - Develop platforms including databases  for  effective exchange of  information

  - Train M.Sc. and non-degree students in technology targeting, analysis of value chains, breeding/seed technology, agronomy and cropping systems.

III. Description and sequencing of activities (1-2 pages)

Objective 1

The socioeconomic and agro-ecological characteristics of farming systems will be established  through secondary data and participatory methods. Rapid appraisals, baseline studies and consultations with key partners will be undertaken to identify research sites/communities. GIS maps with socioeconomic and biophysical characteristics will be developed for selected farming systems. Project sites will be selected in consultation with farmers.  Outputs will include a better understanding of production constraints, the role and constraints to adoption of improved technologies, marketing challenges, the preferences and livelihood status, and strategies used by farmers to sustain productivity of maize-legume systems as well as the prospects of alternative investments and technological solutions. Early adoption and impact studies will be conducted to assess the extent, path ways, and determinants of technology adoption as well as the farm level or primary impacts of technologies among adopters in the target sites where there is significant early adoption. Research hypotheses will be formulated to test and explain gender differentials in adoption and impacts with a view to enhancing the intrahousehold distribution of the benefits from the project. Technology adoption may also have differential effects within and across households due to the influence of social structures as well as gender imbalances in access to productive assets and support services.  A value chains approach will be adopted to promote and sustain the adoption of improved technologies through increased output marketing and demand creation for maize and legumes. After a market survey of processors, traders, and other actors along the maize-legume value chains in eastern province, strategic alliances that will  link producers to traders and processors will be established. Value chains development will involve activities that lead to increased farm gate prices for producers as well as lower prices and diversify uses maize and legumes for consumers. These include better farmer organization and empowerment, horizontal integration among producers, and vertical integration of producer groups with processors and traders as well as an integrated input supply system. The project will adopt a participatory market chain development approach to foster greater interaction and co-ordination among the various market actors. A key objective is to create the awareness, capacity, and opportunities for farmers to become more positive and informed actors in the market chain. The outcome will be a more organised and structured value chain that allows farmers and traders to work together in a more informed market process and address issues of product differentiation, quality and standards, volume and frequency of supply, and to create a platform for new market-oriented technology implementation. Participatory approaches will enable the project address gender-related issues to ensure empowerment and equity through increased market participation among women farmers. Gender issues will NOT stand alone, but will be integrated into all project activities. Gender disaggregated sampling approaches and data collection methods will be applied to explore gender roles and gender relations in project target communities. This will enable us to document for planning purposes the differences between men and women in the activities they perform, how they perform them, and access to resources by gender, knowledge base of men and women farmers.

Objective 2

In order to improve productivity of maize-legume production systems, this project will test various technologies together with farmers. These will include improved varieties, crop protection products, fertilizers, improved intercropping systems and better agronomic practices. Using the participatory approaches, researchers and development partners will facilitate the processes of experimentation, technology dissemination, and monitoring and evaluation.  A number of researcher-managed “mother trials” on farmers’ fields will be established to demonstrate best-bets improved technologies. Lead farmers will also be invited to test selected technologies under their management practices. The project will provide all the necessary inputs to the farmers, on loan basis, to allow the establishment of “daughter trials”. These trials will serve the purpose of further evaluating the technology under farmer conditions and demonstration plots where other farmers see and evaluate the performance of improved technologies. Selected best-bets technologies from the mother trials will be extensively tested and promoted in lead farmer managed on-farm demonstration plots. Each lead farmer representing a community-based organization in his community will have two plots each measuring 400m2. The first plot will consist of the improved maize or legume varieties grown using improved technologies. The second plot will serve as control where the farmer will use his own crop varieties and crop management practices. Mid and end of season evaluations and field days will be organized periodically during the cropping season to popularize improved technologies. Community-based feedback mechanisms will be encouraged to allow researchers to refine the research agenda in a bottom-up manner to respond to emerging issues from the farmers’ field experiences, and strengthen institutional collaboration. Major input dealers and credit providers will be identified. Through annual needs assessment, farmers’ requirements for inputs and credit will be collated. This information will be used by the project to link service providers with farmers groups for bulk delivery of inputs.

Objective 3

Diagnostic studies undertaken in objective 1 will also provide an understanding of the processing, value addition and diversification needs in project communities.  Surveys supplemented by biochemical analyses will be used to assess the nutritional value of existing maize based foods. Anthropometrical, clinical and biochemical analyses will be used to assess the nutritional status of women and children in project communities.  Processing using low-cost machinery and processes for producing high quality nutritious food products under rural conditions will be tested using participatory approaches. Storage and packaging technologies to extend product shelf life will also be tested.  Pilot processing centers at the community level will be established and linked to the commercial sector. Smallholder farmers and/or farmer co-operatives at project locations will be given assistance through training in testing and adopting recommended technologies for primary processing.  Major maize and legume brokers and their requirements, delivery schedules, and prices will be identified. This information will be made available to farmers groups to negotiate prices and contract conditions with brokers. To address gender issues, women farmers or traders will be organized into  associations to ensure collective negotiation and marketing of their products. Nutrition awareness campaigns will be carried out in partnership with all stakeholders involved in the process of technology transfer in objective 2. This will involve demonstrations of food products during farmer field days, community level, and trade fairs.  The mass media will be used to transfer simplified information on the nutritional benefits of legume based diets. Primary and secondary school teachers will be sensitized to disseminate the message in schools.  Women groups and women opinion leaders will be involved in the overall process. We propose to work closely with growers/processors associations, brokers, and the industrial processors in targeting women traders so that they are not disadvantaged in the process. The project will also liaise with NGOs and other groups promoting the interest of women traders or associations to explore synergies for the benefit of women farmers and traders in the target countries.

Objective 4

Promising and newly released maize hybrids and OPVs and legume varieties with potential suitability for the targeted farming system will be selected based on past regional and national trial data. Varieties that meet the requirement of the agroecologies of the targeted farming systems and farmer preferences will be fast-tracked for release and scaling up of seed production. Best-bet varieties will be assessed for performance, farmer preference and marketability in collaboration with farmers and seed companies in the selected communities. Ease of production will assessed with seed companies supplying those communities. A minimum of three producible maize hybrids and OPVs and at least two legume varieties suitable for the targeted farming system will be identified and variety release supported. Based on GxE analyses and socio-economic characterizations, recommendation domains for varieties and hybrids will be developed both within each district and across the province to support rapid scaling out and dissemination. Released varieties will be licensed to seed companies and x ton of breeder seed per variety produced in support of rapid scaling-up. (more information needed )

Objective 5

Simleza's implementation plan will include very concrete efforts towards its sustainability, which will be  fulfilled  by involving and engaging local partners.  Any gaps in skills of local partners will be addressed through appropriate training. A skills gap analysis will be conducted to determine the skills required by the main actors along the maize-legume value chains (e.g. researchers, extension agents, farmers, processors, and marketers). Appropriate training, information and communication materials serving the needs of key partners will be developed. These will be made available in media and language that is most acceptable and will have the greatest impact on the clientele.  Farmers and extension agents will be trained in productivity-enhancing activities such as choice of varieties to grow,  land preparation, planting, fertilizer application, harvesting, safe use of agrochemicals and seed production as well as integrated pest management. Training will be provided using different training  methods such as field days, radio programs, extension materials, and demonstrations.  Pilot processing sites established under objective 3 will be used for training of community based processors. Promising postharvest technologies that are acceptable to communities will be promoted and communities linked up with appropriate institutions to acquire the technologies. As demand for these improved technologies increase, local artisans and manufacturers will be trained to fabricate the low cost machines and provide after-sales service to users. Extension workers will also be trained on operation and management of these technologies. This project will work closely with the partners who have expertise in storage systems to promote the use of improved storage technologies. Farmers will be trained to ensure quality and bulk marketing arrangements. Producers, processors and traders will be trained in group dynamics, business management, book-keeping, and credit management.

After a human skills and equipment needs assessment, support will be provided to ZARI and other national entities to strengthen their capacities and prepare them for taking more responsibilities in implementing the proposed activities.  In addition to technical skills, the project will also work with the coordination office to enhance the skills of local partners in financial management, reporting, and proposal development. Capacity building will include both non-degree practical training (e.g. sabbatical leave or short-term visits to CG centers by scientist from ZARI, UNZA etc) and post-graduate degree training. Practical training will include enhancing skills in technology targeting, risk analysis, value chain diagnosis, cropping systems management and conservation agriculture, integrated maize-legume modeling, and methods for participatory breeding and quality seed production.

IV. Collaborating partners  and roles (1-2 pages)

| Objectives | Backstopping | Local implementation | Analysis of data & best-bet options | Advocacy and scaling up/out |
| --- | --- | --- | --- | --- |
| 1. Targeting and value chains | Methodology: CIMMYT and IITA | Field Surveys: UNZA, ZARI | CIMMYT, IITA, UNZA | Policy advocacy: ZARI, GART,, MACO |
| 2. Improved agronomy and innovation systems | Approach and methods: CIMMYT and IITA | On-farm trails and innovation platforms: ZARI, GART, NGOs | CA & storage options : CIMMYT, IITA, GART | Scaling up/out: ZARI, GART, World Vision |
| 3.Diversification of maize, soybean and cowpea use | Technology introduction: IITA, ZARI and UNZA | Awareness campaigns, processing: ZARI; NGOs and UNZA | Test processing options: IITA, UNZA, GART | Scaling out promising and gender sensitive processing methods: ZARI, NGOs and CBOs |
| 4. Improved maize and legume varieties | Germplam identification: CIMMYT and IITA | On farm trials and PVS: GART, ZARI Breeder and pre-basic seed: ZARI-GART Seed certification: SCCI | GXE analysis: CIMMYT, IITA, ZARI | Prod and marketing of certified maize hybrids seed: Seed companies Maize OPVs and Legume seed: NGOs and farmer groups |
| 5. Capacity building | Training in Breeding, agronomy, value chains, targeting: CIMMYT, IITA, UNZA | Training of farmers, extension and seed companies: GART, ZARI, UNZA | Supervision of MSc students: UNZA, CIMMYT, IITA | Extended training (degree and non-degree): UNZA |

V. Monitoring & Evaluation (1-2 pages)

Performance monitoring

Monitoring and evaluation of the SIMLEZA project will involve performance monitoring as well as outcome and impact evaluation for learning lessons and providing feedback to the research and development process. Performance monitoring is a project management function involving monitoring of project inputs, activities, outputs, and milestones through a process monitoring and evaluation system which will also provide a database for internal and external evaluations as well as for regular progress reports to stakeholders. Specifically, performance assessment will review the quality and quantity of outputs based on the evolution of key performance indicators. Milestone tracking will involve monitoring of the achievement of pre-determined (planned) milestones laid out in the project logframe as well as identification of achievements not originally envisaged (unexpected discoveries/opportunities). Lower level results indicators outlined in the FTF Results Framework, such as farmers receiving productivity training, relate largely to project outputs and will thus be monitored through the performance monitoring system in the same way as the other project milestones. All partner involvement will be defined by sub-contracts, linking deliverables to financial support. Annual review and planning meetings and Steering Committee meetings will review project progress, establish annual work plans and the roles of project scientists and partners, and discuss and apply new insights for the most effective use of project funds within the objectives and activities of this project. The project will prepare regular reports to both inform the donor and to exchange results among project partners and key stakeholders. It is expected that the project will also benefit from external evaluations commissioned by the donor during and/or at the end of the project period.

Outcome and impact evaluation

Outcome and impact evaluation will provide a comprehensive assessment of the extent and determinants of uptake and impacts of research outputs and the effectiveness of the overall technology development and delivery efforts. First, a strong knowledge base will be established through baseline studies and situation analyses to contribute to an increased understanding of the constraints to increased productivity and competitiveness of smallholder agriculture; the role and constraints to adoption of technologies; and the preferences and livelihood status and strategies of smallholder producers. An important output will be a description of the maize-legume production system constraints and opportunities and analyses of the livelihood status and strategies of producers as well as the prospects of alternative investments and technological solutions. This will guide investments in maize-legume research, institutional innovations, and complementary public goods for income gains and poverty reduction. The productivity and incomes of smallholder producers will be enhanced through greater adoption of technologies that address key production constraints and have the traits that are highly preferred by them.

The results of the baseline studies will form the basis for assessing progress and primary or adopter-level impacts of the project. Household and community surveys will be conducted using validated instruments to assess production constraints, costs and returns, end-user preferences, and the roles of maize and legumes in general and existing varieties in particular on farmers’ livelihoods with a view to drawing lessons for the deployment of new varieties. Gender-differentiated focus groups will be used to better understand farmer perspectives, motivations, and constraints. Female enumerators will be used to gather gender-sensitive data from women respondents. The baseline study will form the basis for measuring the indicators of household level project impacts among adopters in the target areas. A review of the literature will be undertaken to identify already existing information. Baseline study instruments (e.g., community-level questionnaires, household-level questionnaires, key informant checklists) will be developed and enumerators trained on sampling design and data collection. Baseline surveys will be conducted, data entered, and analyzed. A baseline report will be published and results shared with all stakeholders.

Second, early adoption and impact studies will be conducted to assess the extent, path ways, and determinants of technology adoption as well as the farm level or primary impacts of maize-legume technologies among adopters in the target areas where there is significant early adoption at the end of the project. Using standardized protocols, early adoption and impact studies will be conducted across the target/pilot sites to identify the extent, determinants, and pathways of adoption of improved varieties and management practices. The timing of these surveys will be towards the end of the project when significant adoption of improved varieties and practices will likely have taken place in the pilot sites and communities. Research hypotheses will be formulated to test and explain gender differentials in adoption and impacts of improved technologies with a view to enhancing the intrahousehold distribution of the benefits from maize-legume research and extension. Indeed, not only are there gender differentials in technology adoption, but technology adoption may also have differential effects within and across households due to the influence of social structures as well as gender imbalances in access to productive assets and support services.

The first order or primary outcome and impact indicators for the project will include: changes in technology adoption in terms of the number of farmers applying, and land area under, improved varieties and management practices; changes in crop yields, area, and production; and changes in production costs and profitability (i.e. gross margin per hectare of land). The second order impacts that may result in the long term will include: changes in welfare of producers and consumers due to permanent income, asset accumulation, and price effects; changes in consumption, food and nutritional security; and changes in distributional impacts (e.g. different wealth groups, marginal farmers and women). In the short term, emphasis will be given to measuring the first order outcomes and impacts of the project. With improved targeting of technology development and delivery, the benefits of outcome and impact assessment research will be realized through increased adoption and impacts on household incomes and food security.

Impacts and adoption pathways

It is estimated that close to 30,000 farm households will be impacted within four years. The direct economic benefits will include productivity gains and production risk reduction, which will raise farm household incomes. The intervention will increase land/labour productivity and incomes for the poor and women farmers, which will reduce poverty and alleviate malnutrition, increase food security and improve health and education outcomes. Productivity increase can also stimulate demand for labour and thus expected to reduce unemployment. The integration of legumes and CA into maize-based production systems will improve soil quality and reduce soil erosion. There will be increased capacity of R&D partners to foster agricultural innovations systems and of farmers and agro-enterprises to utilize maize-legume innovations through enhanced arrangements for networking, exchange of knowledge, training and partnerships; enhanced capacity (with an emphasis on female participation) of agro-enterprises (farmer organizations, agro-dealers, seed companies) and private/public sector service providers in input supply and output marketing and service delivery to farmers; and increased capacity of policy makers and government agencies to make informed policy decisions related to technology targeting and promotion of maize and legume innovations.

VIII. Summary Budget (This has to follow the USAID format)

| Personnel |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Equipment and supplies |  |  |  |  |  |
| Travel |  |  |  |  |  |
| Workshops and conferences |  |  |  |  |  |
| Training and technology dissemination |  |  |  |  |  |
| Field costs and research |  |  |  |  |  |
| Publications |  |  |  |  |  |
| Communications |  |  |  |  |  |
| Contractual |  |  |  |  |  |
| Coordination |  |  |  |  |  |
| Grant admin fee |  |  |  |  |  |
| Overhead (19.3%) |  |  |  |  |  |
| Overall total |  |  |  |  |  |

|  | CIMMYT | IITA | Total | % share | Objective share (%) |
| --- | --- | --- | --- | --- | --- |
| Obj 1: Improved targeting and value chains for impact | 0.21 | 0.18 | 0.39 | 26 | 26 |
| Obj 2: Improved agronomy and innovation systems | 0.23 | 0.13 | 0.36 | 24 | 24 |
| Obj 3: Diversification, processing and nutrition | 0 | 0.13 | 0.13 | 8.7 | 8.7 |
| Obj 4a: Improved maize varieties | 0.23 | 0 | 0.23 | 15.3 | 15.3 |
| Obj 4b: Improved legume varieties | 0 | 0.15 | 0.15 | 10 | 10 |
| Obj 5: Capacity building | 0.07 | 0.06 | 0.13 | 8.7 | 8.7 |
| Project management/coordination | 0.06 | 0.05 | 0.11 | 7.3 | 7.3 |
| Total | 0.8 | 0.7 | 1.5 | 100 | 100 |

Please see attached Excel spreadsheets for detailed budgets.

ANNEX 1: Logframes

| Objective 1 | To enhance technology targeting and delivery for the poor (and women) by identifying systemic constraints and options for improving input and output value chains and impact pathways |  |  |  |
| --- | --- | --- | --- | --- |
| Activities | Outputs/Milestones | Outcomes | Means of Verification | Risks / assumptions |
| 1.1 Socio-economic and geospatial characterization of selected maize-legume farming communities and selection of research sites/communities |  |  |  |  |
| 1.1.1: Assemble/analyse secondary data and characterize/map target farming systems | Socioeconomic and biophysical profiles developed for target farming systems | Researchers/extensionists identify priority pilot areas and recommendation domains for maize-legume research and extension | Project Reports; NARS Reports | Relevant data on production conditions, constraints and socioeconomic factors (population, roads, markets, poverty profiles, etc) is accessible from secondary sources |
| 1.2 Farmers’ maize-legume production constraints and opportunities, resource use, technology preferences, profitability, and market access |  |  |  |  |
| 1.2.1: Develop standardized baseline survey instruments through consultation with partners | Survey instruments and protocols for survey data collection developed | Scientists and research managers take into account maize-legume production and technology adoption constraints and end-user preferences in setting maize-legume research and development priorities Research managers and development partners use baseline information for establishing benchmarks for monitoring progress towards project goals | Donor Reports; Project Reports; and Government/NARS Reports | Proactive participation of partners in developing a tool for collecting relevant information; and participating farmers will cooperate in providing the necessary information through in-person surveys |
| 1.2.2: Identification and training of enumerators, and implementation of farm household surveys | Household survey data collected and documented |  |  |  |
| 1.2.3: Analysis of existing farmers’ resource use patterns, production practices, technology choices and preferences, constraints to market participation, and maize-legume systems improvements in the target communities to appraise technology options | Survey report completed and shared with partners |  |  | Availability of good data will allow quick analysis of major socioeconomic conditions, constraints and opportunities in the target farming systems |
| 1.3 Maize and legume input and output markets and value chains including market constraints and opportunities |  |  |  |  |
| 1.3.1: Review of market and value chain studies and secondary data on selected service delivery systems (seed, fertilizer, credit, CA equipment,) and product markets | Review report prepared on maize-legume value chains with emphasis on key service delivery systems (seed, fertilizer, credit, etc.) and product markets | Scientists, donors, and private sector identify technology options and investment opportunities for linking maize and legume producers to input as well as output markets | Donor Reports; Project Reports; and Government/NARS Reports | Institutions are willing to share documents and data |
| 1.4 Early adoption and impacts of the project in the target communities |  |  |  |  |
| 1.4.1: Develop adoption and impact survey design, tools, and methodology for use by project partners for implementing the adoption and impact surveys | Standardized adoption and impact survey design, tools, and methodology developed and adopted by project partners for implementing the adoption and impact surveys | Scientists, research managers, and policy makers take into account constraints to adoption of maize-legume technologies in refining and addressing research and development priorities and constraints Research managers and development partners use early adoption and impacts information for monitoring progress towards project goals Capacity of UNZA/ZARI and other national programs strengthened through hands-on training of socio-economists in early adoption and impact survey designs, tools, and methodologies | Donor Reports; Project Reports; and Government/NARS Reports | Political and security conditions will remain stable in the country to allow continuous monitoring of changes attributable to the interventions. |
| 1.4.2: Conduct household, community, and market surveys of uptake and impact pathways of maize-legume technologies and institutional innovations | Database established on the uptake and impact pathways of maize-legume technologies and institutional innovations |  |  |  |
| 1.4.3: Assess adoption constraints and project impacts through farm household surveys as well as use of on-farm experimental data to identify impact pathways and facilitate learning, change and priority setting processes | Report prepared documenting early adoption and impacts of maize-legume technologies and shared with researchers and other stakeholders |  |  |  |

| Objective 2 | To enhance adoption and adaptation of productive and resilient agronomic practices and local innovation systems for intensification and income growth in maize-legume cropping systems |  |  |  |
| --- | --- | --- | --- | --- |
| Activities | Outputs | Outcomes | Means of verification | Risks/assumption |
| 2.1 Conduct discussions with innovation platform partners to identify agronomic and seed technologies to be tested | Databases of available agronomic and seed technologies | Researchers and development partners use information to design or adapt yield –enhancing technologies | Project reports; IITA , CIMMYT annual reports | Farmers and other partners willing to share information |
| 2.2 Evaluate crop production technologies (hybrids/varieties, agronomic practices) for adaptation and adoption | More productive maize and legume varieties Appropriate technologies identified and ready for introduction into targeted communities Information on farmer preferred maize, cowpea and soybean varieties for targeted communities available Data compiled to facilitate varietal registration and release | At least 40% of farmers are aware of the availability of improved maize, soybean and cowpea varieties and crop management technologies in pilot sites Adoption of improved varieties and crop and soil management technologies increased by 30% Improved soil health and increased maize/legume productivity | Project reports; IITA , CIMMYT annual reports | Environmental conditions Sustained commitment from partners to evaluate improved technologies |
| 2.3 Establish on-farm demonstration of improved technologies including maize-legume rotations that increase productivity and incomes | At least 10 on-farm demonstrations on improved crop management practices established per year | Extension systems demonstrate recommended practices for adoption by farmers | Project reports; IITA , CIMMYT annual reports | Sustained commitment from farmers to participate in the project activities |
| 2.4 Mobilization of farmers using mass communication (fact sheets, radio, TV etc.) and field days to create public awareness of available technologies | At least 2 factsheets or bulletins produced and at least 2 radio/TV programs aired per year At least 2 field days held each year with the participation of at least 100 people | Producer adopt the use of improve production practices | Project reports; IITA , CIMMYT annual reports |  |
| 2.5 Introduce and test appropriate post-harvest storage interventions for maize and legumes | Reduced storage losses of maize and cowpea using triple bag | Producers adopt better storage practices A range of efficient storage technologies evaluated and adapted by NARS, NGOs, and private sector partners | Project reports; IITA , CIMMYT annual reports | Producers willing to test improved technologies |

| Objective 3: Enhance the diversification of maize, soybean and cowpea use at household level through processing, product diversification and marketing |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activities | Outputs/Milestones | Outcomes | Mean of Verification | Risks/Assumptions |
| 3.1 Assess the nutritional status and diet quality of women of child bearing age and their under 5 children in target communities |  |  |  |  |
| 3.1.1 Determine the nutritional status of women of childbearing age and their children under 5 in target communities | Levels of wasting, stunting, and underweight established in at least 3 project communities | Appropriate strategies and interventions for improving nutritional status developed | Project reports NARS reports | Willingness of participants to participate. Procurement of Ethical Clearance |
| 3.1.2 Evaluate the nutrient composition of existing maize-, soybean-, and cowpea-based food products as consumed by target communities | Nutrient content of at least 15 maize-, soybean-, and cowpea-based food products determined | Information on nutrient content of maize-, soybean-, and cowpea-based products | Project reports NARS reports | Active participation of partners |
| 3.1.3 Conduct focus group discussions on maize, soybean, and cowpea processing and storage practices including their products | At least 3 focus group discussions conducted At least 3 processing and storage methods improved | Knowledge on processing and storage practices | Project reports NARS reports | Active participation of partners and selected communities |
| 3.1.4 Estimate the consumption and contribution of maize, soybean and cowpea to energy and protein intake | At least 1 food consumption survey undertaken in 2 target communities | Information on the contribution of maize, soybean and cowpea to energy and protein intake | Project reports NARS reports | Active participation of partners and selected communities |
| 3.2 Adapt and promote household level technologies for the production, processing, and storage of nutritionally improved traditional maize food products and soybean and cowpea based novel foods |  |  |  |  |
| 3.2.1 Adapt, and introduce maize, soybean, and cowpea products | At least 10 food products adapted, tested, and introduced in target communities | At least 20% of households consume soybean and cowpea products | Project reports NARS reports | Introduced products are acceptable |
| 3.2.2 Characterize soybeans and cowpea for protein content and use for food to food fortification | At least 20 varieties each of soybean and cowpea characterized for nutrients | Information on protein, antinutritional factors, and content a | Project reports NARS reports | Active participation of partners |
| 3.2.3 Conduct training of trainers workshops on improved soybean and cowpea processing, product development and food hygiene/safety | At least 6 Training of Trainers workshops conducted | Researchers, extensionist, NGOs, and CBOs aware of alternative uses of maize, soybean, and cowpeas | Project reports NARS reports | Active participation of partners and selected communities |
| 3.2.4 Promote consumption of safe nutritionally improved traditional and novel food products | At least 30 one day training and demonstrations conducted | Awareness on alternative uses of maize, soybean, and cowpea | Project reports NARS reports | Active participation of partners and selected communities |
| 3.3 Expand agro-processing and markets for maize, soybean, and cowpea products |  |  |  |  |
| 3.3.1 Conduct needs assessment of small and medium scale processors | Needs assessment of at least 10 small and medium scale processors conducted | Information on needs of small and medium scale processors | Project reports NARS reports | Active participation of partners and processors |
| 3.3.2 Establish/upgrade small and medium scale processing and product development facilities | At least 5 small and medium scale processing facilities upgraded | Improved quality of processed products | Project reports NARS reports | Active participation of partners and processors |
| 3.3.3 Conduct training on business enterprise development | At least 10 small and medium scale processors trained | Enhanced business skills of processors | Project reports NARS reports | Active participation of partners and processors |
| 3.3. 4 Promote small and medium scale industrial processing technologies | Production of 2 novel/improved maize, soybean, or cowpea products promoted | More products of either maize, soybean, or cowpea available in the market | Project reports NARS reports | Active participation of processors Market opportunities available |
| 3.4 Marketing outlets for maize, soybean, and cowpea products developed and expanded to increase incomes and improve nutrition |  |  |  |  |
| 3.4.1 Strengthen local innovation platforms to enhance farmer learning and awareness of promising processing options | At least 1 partnership created among producers, processors, marketers, consumers | Enhanced income generation , improved nutrition, and increased commercial activities | Project reports NARS reports | Enabling environment and active participation of partners |
| 3.4.2 Develop capacity of entrepreneurs in market identification, product development, packaging, storage and enterprise development, | At 1 training workshop conducted for small and medium scale processors | Increased production of safe and nutritionally improved food products | Project reports NARS reports | Active participation of partners and processors |
| 3.4.3 Facilitate small and medium scale agro-processor’s groups and enterprises’ access to inputs, credit, information, and improved technologies | At least 4 linkages facilitated and access to inputs improved | Increased production of safe and nutritionally improved food products | Project reports NARS reports | Active participation of processors and inputs providers Enabling policy environment |
| 3.4.4 Identify opportunity for and facilitate linkages between farmer associations and industrial processors, private and public sector grain markets. | At least 2 opportunities identified and facilitated | Signed contracts or agreements between farmer associations and private sector especially processors | Project reports NARS reports | Active participation of processors Market opportunities available |

| Objective 4 | To increase the range of maize and legume varieties through participatory testing and release, and enhanced delivery of seeds of locally adapted varieties |  |  |  |
| --- | --- | --- | --- | --- |
| Activities | Outputs | Outcomes | Means of Verification | Important Assumptions |
| 4.1 Conduct on farm trials to identify stress tolerant and higher yielding maize and legume varieties through farmer- and seed company-participatory evaluation and GXE analysis |  |  |  |  |
| 4.1.1 Stress tolerant and high yielding maize, soybean and cowpea varieties ( | At least 4 high yielding stress tolerant and locally adapted maize varieties , and 6 legume varieties for different districts of eastern Zambia released | Increased maize and legume production in eastern province | Reports prepared, field visit during the trial period | Small-scale farmers in the different districts are willing to participate in PVS trials and willing to buy seeds of improved varieties. |
| 4.1.2Data from on-farm trials analysed and made available to stakeholders | Potential maize and legume varieties for the target environment in the program countries analyzed with partners. | Stakeholders have access to information on the performance of maize and legume varieties from on-farm | Reports by ZARI, IITA and CIMMYT | Availability of farmer-preferred varieties of maize, soybean and cowpea in the existing breeding programs |
| 4.2 Provide varietal performance data to accelerate variety release and registration |  |  |  |  |
| 4.2.1 Promising varieties from on-station and on-farm identified and submitted to national performance trials | Four maize and 6 legume varieties submitted for release | Superior and farmer-preferred varieties released and made available to farmers | Reports; list of genotypes in NPT | Superior genotypes available in the gene pool for testing and selection |
| 4.3 Develop maize and legumes seed road maps to enhance the availability of maize and legume seeds and integrate into the work plans of public and private seed sector partners |  |  |  |  |
| 4.3.1 Identify a number of public and private seed companies to develop seed road maps | At least 4 seed companies identified for the development of seed road maps for the production of maize and legume varieties | Farmers have access to certified seed of maize and legume varieties | Seed company reports and national statistics | Seed companies are will to participate |
| 4.3.2 Set up demonstration and promotional materials in line with seed road map | A number of demonstrations and promotional materials developed | Farmers become more knowledge about maize and legume varieties from various seed companies | CIMMYT and IITA reports. | Active participation of seed companies |
| 4.4 Increase production and availability of breeder and pre-basic seed of farmer and market preferred maize and legume varieties to stimulate the market and community based seed production and supply |  |  |  |  |
| 4.4.1Seed increase of pre-release and newly released maize hybrids and OPVs and legume species and varieties with potential suitability for the targeted farming system | At least one ton of pre-basic and basic seed produced and distributed to seed companies for scaling-up | Pre-basic and basic of newly released variety become more available to seed companies | CIMMYT and IITA reports | Number of new maize and legume varieties are released |
| 4.4.2Provide back-stopping of NARS and seed companies in the production quality seed. | A number of seed companies and NARS are backstopped in the production of seed | Seed companies and NARS produce quality seed | CIMMYT and IITA reports | Seed companies are willing to take newly released varieties |
| 4.5 Facilitate the establishment of functional community based seed production (especially by women’s groups) and develop collaborative partnerships with seed companies to increase the supply and diffusion of certified hybrid maize, soybean and cowpea varieties to resource poor farmers and women |  |  |  |  |
| 4.5.1 Identify varieties for community based seed production with farmers | Number of maize, soybean and cowpea varieties for seed production | Farmers are knowledgeable about variety choices | Records of ZARI, CIMMYT, IITA and other partners | Farmer and end-user preferred varieties of maize, soybean and cowpea are available. |
| 4.5.2 Identify suitable production model that suit the community | Models of seed production preferred by the CBOs |  | Records of district agricultural offices, ZARI, IITA and CIMMYT | Seed production and delivery strategies suitable for the farming community available. |
| 4.5.3 Train farmers on seed production and business skills | Increase capacity of farmers in seed production and business skills |  | Records of district agricultural offices, ZARI, IITA and CIMMYT | Women farmers interested in seed production and business skills. |
| Objective 5 :To enhance the capacity of national partners on targeting, technology adaptation, trial management, seed and input supply and value chain development |  |  |  |  |
| Project activities | Output | Outcomes | Means of Verification | Important Assumptions |
| Assess the training needs of women and men farmers, researchers, extension agents and private sector, and develop appropriate training programs | Training needs assessment report | Researchers and development plan use the information to develop appropriate training programs for stakeholders | Project reports/IITA/CIMMYT reports | Partners are willing to share information |
| Train women and men farmers, farmers’ associations, women groups and extension personnel in community- based seed scheme in the production and marketing of quality assured seeds | Enhanced capacities of women and men producers of maize and legumes | Producers using improved production practices in maize/legume systems | Number of participants, project reports, CIMMYT/IITA reports | Training will improve skills and use of improved technologies by producers |
| Train smallholder farmers, technicians and extension agents on appropriate crop management practices and participatory variety selection (PVS) | Enhanced capacity of producers, extension agents and technicians | Producers using improved knowledge in maize/legume production systems Extension agents using new tools and knowledge to deploy improved technologies | Number of participants, project reports, CIMMYT/IITA reports | Active participation of partners in training programs Training will result in increased adoption of improved technologies |
| Train small and medium scale processors and entrepreneurs on storage/processing systems for maize and legumes | Enhanced capacity of processors and entreprenueners | Processors using improved technologies in processing maize and legume products | Number of participants, project reports, CIMMYT/IITA reports | Active participation of partners in training programs Training will result in increased use of processing and storage technologies |
| Develop platforms including databases for effective exchange of information | Knowledge sharing platforms and databases for information exchange | Stakeholders using new knowledge to improve productivity and profitability of maize/legume systems | Number of participants, project reports, CIMMYT/IITA reports | Partners are willing to share information |
| Train M.Sc. and non-degree students in technology targeting, analysis of value chains, breeding/seed technology, agronomy and cropping systems. | At least one PhD, two Msc and 10 technicians trained | Researchers using now skills, tools and knowledge to generate and promote improved production practices for maize/legume production systems | Number of participants, project reports, CIMMYT/IITA reports | ZARI and other national entities will identify qualified students for training |

ANNEX II: First Year Implementation Plans

| Objectives/Activities | Month of First Project Year |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | S | O | N | D | J | F | M | A | M | J | J | A |
| Objective 1. To enhance technology targeting and delivery for the poor (and women) by identifying systemic constraints and options for improving input and output value chains and impact pathways |  |  |  |  |  |  |  |  |  |  |  |  |
| - Socioeconomic and GIS characterization of targeted maize-legume farming communities and households and selection of research sites/communities |  |  |  |  |  |  |  |  |  |  |  |  |
| - Conduct a baseline study of maize and legume production constraints and opportunities, technology choices, resource use patterns, profitability, and market access |  |  |  |  |  |  |  |  |  |  |  |  |
| - Desk study of maize-legume value chains to identify constraints, investment opportunities, and institutional innovations for increased adoption of improved technologies (seed, ISFM including conservation tillage, etc.) |  |  |  |  |  |  |  |  |  |  |  |  |
| - Conduct early adoption and impact studies of improved maize and legumes varieties and ISFM technologies and define strategies for scaling up/out pro-poor innovations for greater impact on food security. |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 2. Enhance adoption and adaptation of productive and resilient agronomic practices and local innovation systems for intensification and income growth in maize-legume cropping systems |  |  |  |  |  |  |  |  |  |  |  |  |
| - Conduct discussions with innovation platform partners to identify agronomic and seed technologies to be tested. |  |  |  |  |  |  |  |  |  |  |  |  |
| - Evaluate crop production technologies (hybrids/varieties, agronomic practices) for adaptation and adoption |  |  |  |  |  |  |  |  |  |  |  |  |
| - Establish on-farm demonstration of improved technologies including maize-legume rotations that increase productivity and incomes |  |  |  |  |  |  |  |  |  |  |  |  |
| - Introduce and test appropriate interventions for small-scale post-harvest storage of maize and cowpea |  |  |  |  |  |  |  |  |  |  |  |  |
| - Mobilization of farmers using mass communication (Fact sheets, radio, TV etc.) and field days to create public awareness of available technologies |  |  |  |  |  |  |  |  |  |  |  |  |

| Objective 3: Enhance the diversification of maize, soybean and cowpea use at household level through processing, product diversification and marketing |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 Assess the nutritional status and diet quality of women of child bearing age and their under 5 children in target communities |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 Adapt and promote household level technologies for the production, processing, and storage of nutritionally improved traditional maize food products and soybean and cowpea based novel foods |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Expand agro-processing and markets for maize, soybean, and cowpea products |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 Marketing outlets for maize, soybean, and cowpea products developed and expanded to increase incomes and improve nutrition |  |  |  |  |  |  |  |  |  |  |  |  |

| Activities | Month of First Project Year (2011/2012) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | J | J | A | S | O | N | D | J | F | M | A |
| Objective 4: To increase the range of maize and legume varieties through participatory testing and release, and enhanced delivery of seeds of locally adapted varieties |  |  |  |  |  |  |  |  |  |  |  |  |
| Output.1. Increased capacity by stakeholders in producing and delivering seed of new stress tolerant, well-accepted maize, soybean and cowpea varieties |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Stress tolerant and high yielding maize, soybean and cowpea varieties (6 trials per crop per district) selected, evaluated, and disseminated. |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2.Data from on-farm trials analysed and made available to stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |
| Output.2. Much reduced time-span between the development of new maize, cowpeas and soybean varieties and their availability to small-holder farmers in eastern province. |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Promising varieties from on-station and on-farm identified and submitted to national performance trials |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 3. Basic Seed Production of farmer-approved varieties |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 4. Improved knowledge of NARS, and seed company technicians on their level of knowledge of the seed production, processing and marketing of new seed varieties |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 Identify training needs for seed companies, NARS and other partners |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 conduct training on seed production and processing |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 5. Established and functional community based seed production schemes (especially by women’s groups.) |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 Identify varieties for community based seed production with farmers 5.2 Identify suitable production model that suit the community 5.3 Train farmers on seed production and business skills |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 6 .Increased promotion by, seed companies, NGO and extension staff of new stress tolerant maize, soybean and cowpeas that perform well under farmers’ conditions and are accepted by farmer |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 Conduct demonstrations and field days for the most promising varieties 6.2 Design and distribute poster, brochures and pamphlets of most promising varieties |  |  |  |  |  |  |  |  |  |  |  |  |
| Output 7. Annual evaluation and planning meetings will be held to monitor progress and orient future directions of the project to maintain dynamism and efficiency. |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1 Select the location for the annual planning meeting and prepare the agenda |  |  |  |  |  |  |  |  |  |  |  |  |

| Objectives/Activities | Month of First Project Year |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | S | O | N | D | J | F | M | A | M | J | J | A |
| Objective 5. To enhance the capacity of national partners on targeting, technology adaptation, trial management, seed and input supply and value chain development |  |  |  |  |  |  |  |  |  |  |  |  |
| Assess the training needs of women and men farmers, researchers, extension agents and private sector, and develop appropriate training programs |  |  |  |  |  |  |  |  |  |  |  |  |
| Train women and men farmers, farmers’ associations, women groups and extension personnel in community-based seed scheme in the production and marketing of quality assured seeds |  |  |  |  |  |  |  |  |  |  |  |  |
| Train smallholder farmers, technicians and extension agents on appropriate crop management practices and participatory variety selection (PVS) |  |  |  |  |  |  |  |  |  |  |  |  |
| Train small and medium scale processors and entrepreneurs on storage/processing systems for maize and legumes |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop platforms including databases for effective exchange of information |  |  |  |  |  |  |  |  |  |  |  |  |
| Train M.Sc. and non-degree students in technology targeting, analysis of value chains, breeding/seed technology, agronomy and cropping systems. |  |  |  |  |  |  |  |  |  |  |  |  |

‘Mother’ trial consists of a basket of improved options e.g., high yielding varieties, crop protection products, planting dates, different fertilizing regimes, where farmers observe and compare different management options.

On farm farmer- managed trials with backstopping from extension agents