M&E Plan and Implementation Roadmap for Africa RISING

Annotated outline/section drafts (with responsibilities)

# Introduction

  - M&E plan and implementation roadmap development process, finalization – GE

This document is a Monitoring and Evaluation (M&E) Plan for Africa RISING (Africa Research in Sustainable Intensification for the Next Generation), a USAID-funded research for development (R4D) project.  The document describes Africa RISING’s strategy for M&E, the methods to be used in M&E, the responsibilities for M&E activities, and the indicators and impacts to be measured.  Monitoring and evaluation are separate, related activities, each with its own methods that can and should be complementary.  However, by referring to “M&E,” this plan is not referring to a single combined activity, but rather to each of them separately.

This plan was developed as a part of an iterative process that involved finalizing the scope of work—for Africa RISING this is referred to as a Research Framework—somewhat simultaneously with developing this plan.  This was a useful process, in that clarification of the activities and expected results of Africa RISING is essential before an M&E plan could be drafted.

USAID’s process for arriving at an agreed set of monitoring indicators and targets is also iterative.  Because of USAID’s internal requirements, an initial set of indicators was selected by USAID for Africa RISING “Quick Win” activities undertaken during 2012.  During the development of the set of indicators to be used for longer-term AR activities, these initial indicators were considered and some additions and subtractions are proposed herein.  These will be reviewed during September 2012, and an agreed set determined.  Setting targets for indicators involves the implementing partner’s proposing realistic targets after the baseline values of the indicators are known.  In some cases baseline values are zero, so targets can be proposed once indicators are agreed upon.  Because baseline data will need to be collected for some monitoring indicators and then targets proposed and agreed, this plan is necessarily a “living document” that will be updated periodically.

Beyond the necessary requirements of satisfying standard/conventional M&E needs, this plan also describes activities designed under an expanded AR M&E scope that involves a stratification schema (by geography and household categories), predictive modeling of key input, output and outcome variables, and a comprehensive M&E data management platform having open access to project teams and partners.

# Plan proposed after a careful review of the intended results – GE

[TBC]

# M&E Objectives

Monitoring and evaluation of project activities are critical for several reasons.  They support effective project management, provide the data for reporting to USAID, and help all stakeholders to learn about the project’s successes and failures.  As the Administrator of USAID has pointed out, it is important to learn from both what did work and what did not (citation?).

# Critical aid in effective management-  GE

Monitoring can be a critical aid in effective management when it provides the project managers with timely information on the status of activities and the ongoing results they are achieving.  This allows managers to assess the need for changes in strategy or implementation.

# Reporting requirements – GE

All clients require ongoing reporting of results (monitoring) so that they can report back to their funding sources to both justify the expenditures underway and to maintain a flow of resources as the project continues.  In this regard it is important to be clear on what is important to the proximate and ultimate clients with regard both to direct results, like an increase in productivity, and to associated and/or cross-cutting factors, like gender equity.  All factors important to the client and stakeholders need to be considered when selecting and/or designing indicators and when considering how to report on the indicators (e.g., frequency of reporting, types of disaggregation).

AR M&E data is of interest both to USAID and to  implementation partners (e.g. CGIAR CRPs and scientists) in tracking their own effectiveness, so this plan will strive to meet the legitimately distinct goals and priorities of both USAID and the CGIAR system.

# Learning

Development projects provide great opportunities to learn what works and what does not.  This can be done through rigorous independent impact assessment and/or through evaluation(s) carried out by project staff.  For large and highly visible projects the impact of which will be reported at high levels, USAID’s evaluation policy specifies an independent (and rigorous) evaluation.  However, much valuable learning can also be achieved through evaluations carried out by the project itself, and USAID certainly recognizes this.  Africa RISING is likely to collect or make use of large amounts of detailed information, which can support various types of evaluation, especially if the evaluation design is carefully considered at the outset of the project.  After its plan of work, the set of questions that Africa RISING sets out to answer in relation to its work and the design of the consequent evaluation(s) are probably the most important decisions that the project faces at its outset.

# A mix of M&E approaches in Africa RISING and their different contributions to Africa RISING’s work

The activities of Africa RISING are designed to rely on data collection and analysis, both for reporting and for management.  A lot of “evaluation” will also be conducted.  At the outset, a detailed situation analysis will gather and analyze many types of data related to agricultural productivity, e.g., to structure development domains and create farm household typologies.  Then recommendations will be produced for new combinations of existing crop and livestock technologies on the basis of careful evaluation of their potential.  These new farming systems will be tested and evaluated under on-farm and on-station conditions.  Finally recommendations for scaling up successful combinations of technologies will be made after evaluative modeling.

Along the way Africa RISING will be interested in the rate of adoption of its recommended systems through diffusion, and how this can sustainably increase agricultural productivity.  Like many other such types of data, those on adoption will help to fulfill both the reporting requirement and the learning objective.

[TBC with Outcome mapping]

# Africa RISING M&E commitments – IFPRI

# FTF Compliance – [IFPRI]

As a project funded by Feed the Future, Africa RISING must and will report regularly on its progress using FTF indicators.  The FTF Indicator Handbook specifies these indicators in detail, including required disaggregations.  Africa RISING may decide on additional disaggregation of data by development domain, farm household typology, etc. to ensure the granularity of data required by its analytical and programmatic objectives.  Africa RISING may also develop a small number of custom indicators to fill gaps in progress reporting, knowing that these indicators could not be aggregated across FTF projects but would still be useful to Africa RISING and to those in USAID monitoring Africa RISING’s progress.

# Open-access platform - IFPRI

# Backward & forward assessment - IFPRI

# Multi-scale reporting - IFPRI

# SSA-wide - IFPRI

# Site-wide report - IFPRI

# Country report - IFPRI

# Sub-system reports - IFPRI

# Scaling-up and out assessments - IFPRI

# Roadmap of this document - GE

The next section of this document contains a brief description of Africa Rising and a definition of sustainable intensification.  This provides the programmatic context for the various components of this detailed M&E Plan that follow.

The next four sections detail 1) the causal logic of Africa RISING, 2) the proposed Results Framework and results indicators that will be used to monitor progress, 3) the output and any process indicators proposed, and 4) how targets will be set against baseline data.

Following these sections there is a discussion of the risks and assumptions about collecting indicator and other required data.  There is a clear and detailed plan for performance monitoring, including the overall strategy, responsibilities, data sources, and deliverables. The plan also describes the proposed M&E Alliance, an open-access M&E website, and an annual M&E technical meeting.

The next two sections specify: 1) data planned for collection and tools for their organization and display, and 2) modeling activities, including linkages between M&E and other data.

The final section of this Plan covers evaluation, both quantitative and qualitative approaches. The analytical approaches and tools detailed in this section include:

- Delineation and characterization of target farming systems;

- Technology/intervention inventory;

- Change estimation/projection models for selected indicator; and

- Attribution assessment, including site selection and stratification, potential comparison group(s), and impact assessment design.

# Brief Description of Africa RISING and Its Goal of Sustainable Intensification - GE

2.1	Objectives and Justification

As part of the U.S. Government’s Feed the Future (FTF) initiative to address global hunger and food security issues in Sub-Saharan Africa, the U.S. Agency for International Development (USAID) is supporting three multi-stakeholder agricultural research activities to sustainably intensify key African farming systems.

The overall aim is to transform agricultural systems through sustainable intensification activities in three regions of Africa:

- Sustainable Intensification of Cereal-based Farming Systems in the Sudano-Sahelian Zone of West Africa – led by IITA

- Sustainable intensification of crop-livestock systems to improve food security and farm income diversification in the Ethiopian highlands – led by ILRI

- Sustainable intensification of maize-legume-livestock integrated farming systems in East and Southern Africa – led by IITA

A similar activity, CSISA (Cereals Systems Initiative for South Asia), is being implemented in the Indo-Gangetic Plains of India and Bangladesh.

Sustainable (agricultural) intensification is defined as producing more output from the same area of land while reducing the negative environmental impacts, and at the same time increasing contributions to the natural capital and the flow of environmental services.

These regions were chosen based on analysis of cropping systems, poverty, population, country development priorities, and the potential for successfully improving agricultural productivity.

These activities will also contribute to the CGIAR’s Research Programs (CRPs) on integrated systems: CRP 1.1 on drylands and CRP 1.2 on the humid tropics.

2.2 	Development of Africa RISING

Africa RISING emerged from a process of discussion and consultation – adapting design and thinking along the way – and engaging a wide range of stakeholders.

These stakeholders progressively refined:

- The three concept notes for the three regions;

- The project goals, outcomes, targets and assumptions or hypotheses;

- The notion of an ‘intensification gradient’ across sites and how this could be put into practice;

- Criteria to select research sites, and in some cases to zoom in on specific places;

- Some ‘early wins’ where the activities could demonstrate results in their first year of operation;

- The overall research framework, and hypotheses to be tested;

- Coordination and management mechanisms – at activity and project levels;

- Monitoring and evaluation and associated data collection and management systems and tools;

- Approaches to communication, learning and knowledge management.

Each region’s concept note was reviewed. In particular the major assumptions or hypotheses guiding each of the regional concept notes, as well as the intended high level outcomes informing the vision were debated and refined. Issues getting greater attention included nutrition, gender and the importance of quantitative targets; great emphasis was given to better alignment with sectoral goals of governments, as well as the priorities of funders.

Discussions in the Tamale workshop made it clear that the various activities need to commit themselves to achieve ambitious goals, targets and outcomes. Further, that these need to be developmental, not limited to what research alone could produce.

Site selection was a challenging issue in all the workshops. With data and support from the International Food Policy Research Institute (IFPRI), participants in each workshop identified a few promising sites in each country.

The initial concept was for three separate research activities. It quickly emerged in the first workshop that a coherent research design approach or framework across the three would be very useful. The initial basic idea was extended in the Addis Ababa workshop and brought together in Dar es Salaam with a team identified to work on a very initial Program-wide research framework within which the regional activities would operate.

Alongside the three research activities, USAID commissioned a team from IFPRI to work with each activity – and now the project as a whole – on monitoring and evaluation. The team played a large role in site selection, mapping various ongoing initiatives, and working with the activities on intended research and development outcomes and indicators.

Finally, as a result of various interactions, communication, learning and knowledge management also came to the fore as a crucial “glue” to ensure strong cooperation and coordination across all institutes, partners and countries involved.  Each of the regional activities is expected to work on these issues in its specific situation, ILRI will take the lead in facilitating project-wide activities of this kind.

#### Development Hypothesis/casual pathway/results chain – GE

#### DH Graphic - GE

[The following graphic is an early attempt to capture what might become the agreed objectives, activities, expected results, and M&E activities of AR.  It relies partly on concept note material, but also attempts to fill gaps with suggestions.  As such it is an attempt to provoke discussion and arrive at a clearer picture of AR and how to go about its monitoring and evaluation.  All elements of the diagram should be seen as open to discussion, including the format and complexity of the graphic.]

Pilot-Scale

Impacts

Participant

Behavior Change

Outcomes

Participant

Behavior Change

Testing

Activities

AR

Outputs

Develop

Recommendations

Participatory

Diagnosis

Sustainable On-Farm

Intensification

Institutional/ Value Chain Improvements

(Markets, Extension, Input Supply Systems)

Breeder & foundation seed produced

New technology systems adopted

Increased income

Increased on-farm investment

Increased value chain investment

Value chains on sustainable growth path

Baseline surveys on constraints,

interactions, resource use, tech. preferences, land use, market access & gender in target farming systems

Bio-economic & simulation modeling for selected farm household typologies to define system options

Monitoring and Evaluation

Monitor and evaluate promising production system technologies under on-station & on-farm conditions

Sustainable livelihoods

Adoption surveys of integrated production technologies during initial diffusion period

Develop simulation models and assess scalability

Synthesize findings on options & develop recommendations for different agro-ecological zones & socioeconomic groups

Promote options for improving input delivery systems, output markets & value chains

Value chain conduct and performance improved

Improved management practices adopted

Identify viable options for postharvest management & improving food safety

Identify institutional innovations to support sustainable intensification of farming systems & development of value chains

Participatory mapping of impact & intensification pathways

Increased sales

Socioeconomic & biophysical characterization & mapping of target farming systems

Participatory evaluation of promising system technologies

New integrated technology systems made available

Synthesize recommendations for input use & improved crop & livestock technologies for nutrient use efficiency, labor savings, & yield

Develop dissemination tools & extension approaches

Develop options for improving input delivery systems, output markets & value chains

Implement institutional innovations to support sustainable intensification of farming systems & development of value chains

Design institutional innovations to support sustainable intensification of farming systems & development of value chains

Ex-post impact assessment

Develop methodological templates for scaling up and scaling out interventions and/or results

Short-term training provided

Producer organizations and members assisted

PPPs formed

Baseline surveys covering monitoring and evaluation indicators

Outcome-related surveys & other data collection

Investment surveys

Improved market efficiency

Improved extension effectiveness

Scaling Up

& Out

Stakeholders implementing risk-reducing practices/actions to improve resilience to climate change

Increased whole-farm productivity

Farmers producing for the market

Sustainable higher productivity

On-farm and on-station trials

Catalog recommended systems by development domain & farm household type

- FTF Results Framework and Results Indicators - GE

  - Results indicators

FTF Indicators Originally Designated for Africa Rising by USAID*

| FTF IR/FTF Sub IR/Indicator |  | Output/Outcome Indicator |
| --- | --- | --- |
| IR 1: Improved Agricultural Productivity |  |  |
| Sub-IR 1.1: Enhanced Human and Institutional Capacity Development for Increased Sustainable Agriculture Sector Productivity |  |  |
| Number of individuals who have received USG supported long-term agricultural sector productivity or food security training |  | Output |
| Number of individuals who have received USG supported short-term agricultural sector productivity or food security training |  | Output |
| Number of food security private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) receiving USG assistance |  | Output |
| Number of members of producer organizations and community based organizations receiving USG assistance |  | Output |
| Number of farmers and others who have applied new technologies or management practices as a result of USG assistance |  | Outcome |
| Number of private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) that applied new technologies or management practices as a result of USG assistance |  | Outcome |
| Sub-IR 1.2: Enhanced Technology Development, Dissemination, Management, and Innovation |  |  |
| Number of new technologies or management practices in one of the following phases of development: …in Phase I: under research as a result of USG assistance …in Phase II: under field testing as a result of USG assistance …in Phase III: made available for transfer as a result of USG assistance |  | Output |
| Sub-IR 1.3: Improved Agriculture Policy Environment |  |  |
|  | Indicator deleted per team discussion. |  |
| IR 3: Increased Investments in Agriculture and Nutrition-Related Activities |  |  |
| Number of public-private partnerships formed as a result of FTF assistance |  | Output |

*During the Quick-Win phase.

Additional Indicators Proposed for discussion by IFPRI

| Indicator | IR/Sub-IR | Output/Outcome Indicator |
| --- | --- | --- |
| Gross margin per unit of land, kilogram, or animal of selected product | IR 1 | Outcome |
| Number of hectares under improved technologies or management practices as a result of USG assistance | IR 1 | Outcome |
| Number of stakeholders implementing risk-reducing practices/actions to improve resilience to climate change as a result of USG assistance | Sub-IR 1.1 | Outcome |
| Number of rural households benefiting directly from USG interventions | Sub-IR 1.2 | Output |
| Value of incremental sales (collected at farm-level) attributed to FTF implementation | IR 2 (Expanding Markets and Trade) | Outcome |
| Farmer satisfaction with quantity, quality and timeliness of extension and input supply services | Custom (Sub-IR 2.3: Improved Market Efficiency) | Outcome |
| Value of new private sector investment in the agriculture sector or food chain leveraged by FTF implementation | IR 3 | Outcome |
| Number of vulnerable households benefiting directly from USG interventions | IR 5 (Increased Resilience of Vulnerable Communities & Households) | Output |

  - FTF Results Framework graphic - GE

Africa Rising FTF Results Framework

FTF Goal: Sustainably Reduce Global Poverty and Hunger

IR 1: Improved Agricultural Productivity

Outcome Indicators:

Gross margin per hectare (whole farm and by crop)

Number of hectares under improved technologies or management practices

IR 3: Increased Investments in Agriculture and Nutrition-Related Activities

Output Indicator:

Number of public-private partnerships formed

Outcome Indicator:

Value of new private sector investment in the agriculture sector or food chain

FTF First Level Objective 1: Inclusive Agricultural Sector Growth

Sub-IR 1.1: Enhanced Human and Institutional Capacity Development for Increased Sustainable Agriculture Sector Productivity

Outcome Indicators:

- Farmers who applied new technologies or management practices…

- Private enterprises/organizations that applied new management practices…

- Stakeholders implementing risk-reducing practices/actions to improve resilience to climate change

Output Indicators:

- Individuals who received long-term training

- Individuals who received short-term training

- Private enterprises/ organizations receiving assistance

- Producer/community based organizations receiving assistance

Sub-IR 1.2: Enhanced Technology Development, Dissemination, Management, and Innovation

Output Indicators:

- Number of new technologies or management practices: 1) Under research, 2) Under field testing, or 3) Made available for transfer

- Number of rural households benefiting directly from USG interventions

IR 2: Expanding Markets and Trade

Outcome Indicator:

Value of incremental sales

Custom Outcome Indicator:

Farmer satisfaction with quantity, quality and timeliness of extension and input supply services (Sub-IR 2.3: Improved Market Efficiency)

USAID-provided IRs and indicators

Additional suggested IRs and indicators

IR 5: Increased Resilience of Vulnerable Communities and Households

Output Indicator:

Number of vulnerable households benefiting directly from USG interventions

- Baselines and Targets

  - Baselines

# FTF indicators – GE

As was mentioned in the Introduction, setting targets for indicators involves the implementing partner’s proposing realistic targets after the baseline values of the indicators are known (although internal requirements often lead to USAID’s setting preliminary targets much earlier).  In some cases baseline values are zero, so targets can be proposed once indicators are agreed upon.  Because baseline data will need to be collected for some monitoring indicators and then targets proposed and agreed, this plan is necessarily a “living document” that will be updated periodically.

Africa RISING will conduct a survey (or set of surveys) to jointly determine any non-zero baselines once all indicators are agreed and other initial survey needs are considered.

# Other data – IFPRI

  - Targets for FTF indicators- GE

Due to their nature, the following indicators do not require that a baseline be measured before setting the annual target, as the baseline is implicitly zero.  For example, when a project conducts training, it is not relevant whether the persons trained had training by another project in the past, so the target number of individuals is set in the absence of any baseline information. The following table shows the targets proposed for FY 2013.

For some indicators previous levels are quite relevant.  For example if a farmer were already applying a method that a new project intends to disseminate, then the new project should not count that farmer towards its target.  If a firm were already exporting a product, then a project to promote exports should not count the full level of exports of that firm towards its target, but rather only the difference between the current total and the baseline level.

| Indicator | FY 2013 Target(s) |  |  |
| --- | --- | --- | --- |
|  | Sudano-Sahelian Zone of West Africa | Ethiopian highlands | East and Southern Africa |
| Number of individuals who have received USG supported long-term agricultural sector productivity or food security training |  |  |  |
| Number of individuals who have received USG supported short-term agricultural sector productivity or food security training |  |  |  |
| Number of food security private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) receiving USG assistance |  |  |  |
| Number of members of producer organizations and community based organizations receiving USG assistance |  |  |  |
| Number of new technologies or management practices in one of the following phases of development: …in Phase I: under research as a result of USG assistance |  |  |  |
| …in Phase II: under field testing as a result of USG assistance |  |  |  |
| …in Phase III: made available for transfer as a result of USG assistance |  |  |  |
| Number of public-private partnerships formed as a result of FTF assistance |  |  |  |
| Number of rural households benefiting directly from USG interventions |  |  |  |
| Number of vulnerable households benefiting directly from USG interventions |  |  |  |

The following are indicators for which the non-zero baseline would have to be determined before the target was set:

- Number of farmers and others who have applied new technologies or management practices as a result of USG assistance

- Number of private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) that applied new technologies or management practices as a result of  USG assistance

- Gross margin per unit of land, kilogram, or animal of selected product

- Number of hectares under improved technologies or management practices as a result of USG assistance

- Number of stakeholders implementing risk-reducing practices/actions to improve resilience to climate change as a result of USG assistance

- Value of incremental sales (collected at farm-level) attributed to FTF implementation

- Farmer satisfaction with quantity, quality and timeliness of extension and input supply services

- Value of new private sector investment in the agriculture sector or food chain leveraged by FTF implementation

- Risks and Assumptions about Measurement - IFPRI

[TBC with:

- Risk: the complexity of the intervention design will make the evaluation design extremely difficult, slowing implementation and/or resulting in few defensible findings

- Assume that participants are willing to share all required data

- Assume that the costs of gathering the generally desired breadth and depth of data are within project resources

- Assume that the needed accuracy of data can be attained within project resources and that the required technology is available and feasible in these locations; power calculations for the evaluation(s) add a dimension to this assumption]

# Plan for Performance Monitoring

  - Strategy for collecting, managing and reporting FTF indicator data – GE

    - Split of resources between M and E

The split of Africa RISING resources between monitoring and evaluation depends on the final level of evaluation proposed. In general there will be much more effort required to conduct evaluation than monitoring.  These efforts should be complementary, in that monitoring data should help to tell the story that evaluation needs to tell, and in some cases, monitoring data might be collected through surveys that are primarily conducted for evaluation.

    - Project management vs. strategic M&E needs

Project monitoring serves both day-to-day project management (by providing accurate and timely data on progress) and strategic M&E needs (by providing a comprehensive set of data that address all of the project’s expected results, thereby permitting occasional “portfolio reviews”).  Africa RISING sees both these purposes as important, and it sees little tradeoff between them in implementing the monitoring program.  Data collection and basic analysis will be a regular feature of the monitoring program, to support management and regular reporting.  Analysis for strategic purposes would be additional, but might be carried out by management staff, rather than regular M&E staff.

    - Roles of “M&E team”  vs. implementing partners in collecting & analyzing data

# Data sources, collection methods and timing

# FTF indicators – GE

| Indicator | Frequency of Data Collection | Source/Method of Data Collection |
| --- | --- | --- |
| Number of individuals who have received USG supported long-term agricultural sector productivity or food security training | Continuous | Project records |
| Number of individuals who have received USG supported short-term agricultural sector productivity or food security training | Continuous | Project records |
| Number of food security private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) receiving USG assistance | Continuous | Project records |
| Number of members of producer organizations and community based organizations receiving USG assistance | Continuous | Project records |
| Number of farmers and others who have applied new technologies or management practices as a result of USG assistance | Annual | Survey of farmers |
| Number of private enterprises (for profit), producers organizations, water users associations, women's groups, trade and business associations, and community-based organizations (CBOs) that applied new technologies or management practices as a result of USG assistance | Annual | Survey of organizations |
| Number of new technologies or management practices in one of the following phases of development: …in Phase I: under research as a result of USG assistance …in Phase II: under field testing as a result of USG assistance …in Phase III: made available for transfer as a result of USG assistance | Annual | Project records |
| Number of public-private partnerships formed as a result of FTF assistance | Annual | Project records |
| Gross margin per unit of land, kilogram, or animal of selected product | Per growing seasons | Survey of farmers |
| Number of hectares under improved technologies or management practices as a result of USG assistance | Per growing seasons | Survey of farmers |
| Number of stakeholders implementing risk-reducing practices/actions to improve resilience to climate change as a result of USG assistance | Per growing seasons | Survey of stakeholders |
| Number of rural households benefiting directly from USG interventions | Per growing seasons | Project records |
| Value of incremental sales (collected at farm-level) attributed to FTF implementation | Per growing seasons | Survey of farmers |
| Farmer satisfaction with quantity, quality and timeliness of extension and input supply services | Per growing seasons | Survey of farmers |
| Value of new private sector investment in the agriculture sector or food chain leveraged by FTF implementation | Per growing seasons | Survey of farmers and firms |
| Number of vulnerable households benefiting directly from USG interventions | Per growing seasons | Project records |

# Other data – IFPRI

# Responsibilities (sites and levels)

# FTF indicators – GE

# Other data – IFPRI

# Deliverables

# FTF-related – GE

# Other deliverables – IFPRI

# M&E Alliance – IFPRI

# M&E Open-Access Web-Site – IFPRI

# Annual M&E Technical Meeting - IFPRI

# Data Planned for Collection and Tools for Organization and Display - IFPRI

# Modeling Activities, Including Linkage of M&E and Other Data - IFPRI

# Evaluation

# Qualitative – GE

# Quantitative – GE

[Following are some dimensions of evaluation that we need to discuss in formulating a plan for evaluation.  The outcome of the discussion will affect both quantitative and qualitative evaluation. The M&E plan will report the status of evaluation planning when the plan is “finalized” in September.]

Africa RISING Evaluation Dimensions and Questions

| Aspect of project or analysis | Implications or questions for evaluation |
| --- | --- |
| Priorities | Which are the most important questions to answer? In general a reasonable answer to this question should come first; then we can see if the resources available allow us to answer the high-priority questions. |
| Sites | - Will Africa RISING collaborate with a value chain or similar project? How would this affect site selection? - Will there be sites to constitute a counterfactual? - Does site selection serve an implementation purpose, an evaluation purpose, or both? |
| Household types | Do these present a dimension that should be evaluated? |
| Development domains | How many domains are there per activity? Are results to be evaluated in all of them? |
| Technology components in packages | Evaluate as a package or try to determine which component(s) are effective? |
| “Participatoriness”: Sequence of recommendation, testing, and adoption vis-à-vis role of farmers and scientists | - Will “science huddle” create a small number of technology packages that farmers will test? (SI has core principles that should guide package composition.) - Or will farmers try one or two technologies that seem attractive first, as one of the concept papers states? - Or both? - Or science huddle creates a menu from which farmers choose? |
| RCT and counterfactual, level at which randomizing (household, village, district), power and sample size | - If evaluation is to be rigorous and attribute impact, these aspects must be dealt with. - Rigorous evaluation design will “interfere” with implementation, in that treatment and control groups need to be selected and informed, and data need to be collected from both. - RCT could be done ex post, but collecting baseline data will provide information on variances, which is likely to reduce required sample sizes to show desired effects. |
| Starting from the Malawi-Tanzania M&E plan by Regis Chikowo | - Outcome Mapping is the main framework used. OM specifically avoids measuring impact rigorously. This poses a major question for the project, especially the donor. - M&E Plan is all about monitoring, not about evaluation - Joseph Rusike is on the same team but is supposedly in favor of RCTs - Joseph’s multi-level design: the design is not clear, nor the implications for evaluation |

Analytical Approaches and Tools - IFPRI

# Delineation and characterization of target farming systems - IFPRI

# Technology/intervention inventory - IFPRI

# Change estimation/projection models for selected indicators - IFPRI

# Attribution assessment, including site selection and stratification, potential comparison group(s), and impact assessment design – IFPRI-GE

Annex

Indicator reference sheets

[For standard FTF indicators, see reference sheets in the FTF indicator handbook]

Custom indicators - GE

| SPS LOCATION: N/A INITIATIVE AFFILIATION: FTF – Sub-IR 2.3: Improved Market Efficiency |  |
| --- | --- |
| INDICATOR TITLE: Farmer satisfaction with quantity, quality and timeliness of extension and input supply services |  |
| DEFINITION: |  |
| RATIONALE: |  |
| UNIT: | DISAGGREGATE BY: Sex (male, female) |
| TYPE: Outcome | DIRECTION OF CHANGE: Higher is better |
| DATA SOURCE: |  |
| MEASUREMENT NOTES: - LEVEL of COLLECTION: Project-level - WHO COLLECTS DATA FOR THIS INDICATOR: Implementing partners - HOW SHOULD IT BE COLLECTED: - FREQUENCY of COLLECTION: Collected per growing seasons; reported annually |  |