| FOURTH MEETING (SKYPE) MINUTES OF THE BABATI RESEARCH TEAM Friday July 4, 2014: 11.05 – 11.35HRS |  |
| --- | --- |
| PARTICIPANTS B. Simon Collaborator – WP4 G. Sikumba Co PI – WP3 T. Stoilova CoPI - WP 6 F.S. Ngulu Consultant –Agronomist / Secretary ABSENT WITH APOLOGIES J.Kihara PI –WP1 S.Lyimo CoPI- WP1 |  |
| Agenda - Matters arising - Emerging issues from MAI meeting |  |
| Agenda Item | Follow-up Responsibility |
| 4.1.1: Integration of multidisciplinary activities 4.1.1.1: WP1 & WP4 - Managed to collect 186 maize seed samples from WP1sites for mycotoxin contamination assay. Samples derived from 4 different varieties and three fertilizer treatments( MRP, Manure and untreated) - WP4 planning to evaluate storage structures in relation to mycotoxin contamination; three storage structures, 10 farmers per village - Integration with WP8 not yet effected. Awaiting Leonard to specify the formulations | Simon making follow up with the extension agents on appropriate date to start |
| 4.1.1.2: WP6 & WP8 & WP1 Vegetables (WP6) are fast growing and short term crops which can integrate readily with WP1 & WP8. There is need for PIs to see how to effect integration.- optimal fertilizer packages, vegetables in chicken feed formulation, and intercropping options with maize | Victor, Stoilova, Kihara, Kizito, Ben, Leonard |
| 4.1.2: Progress of WP activities WP1: PIs were not present but indicated harvesting is in progress. Have also harvested 10 plots under “coupon” maize and fertilizer under IFPRI . The PIs is urged to circulate the field day report; for Hallu and Sabilo WP3: - Organized “farmer variety selection” and a field day at Sabilo (Israel Petro). - 93 farmers attended the field day: Sabilo(42), Bashnet-Long (15), Matufa (5), Hallu (5), Seloto (21), Haysam (10) - KK2, ILRI16837 and ILRI16835 both pure stand & intercropped with Desmodium ranked highest. - Major selection criteria: number of tillers per stool, length of stems, stem thickness and tolerance to drought - The event stimulated farmers interest and high demand for planting material next season - The CoPI made follow up with CARMATEC on the progress of “pulverizers” and hay-baler. There are three types of pulverizers: hand operated, diesel operated and a third one that runs on electricity. The hay-baler is mounted on wheels. The machines will be ready by end of July. - Leonard is out in Babati conducting base line survey. - This work package is planning training on seed multiplication in July/August. The training will cover demonstrations on the use of pulverizers and hay-baler - The CoPI is compiling a report on the “farmers variety selection” and field day at Sabilo WP6: Planning a field day in Babati next week. Write –shop: - This is just a reminder to all. The write-shop will be held in SG lodge along Nairobi road close to BP petrol station. The hotel charges are reasonable. WP PIs advised to meet own travel and accommodation expenses. Other write-shop expenses covered by A-R secretariat - Confirmed participation: Ben, Gregory, Kihara, Lyimo, Victor, Ainsley Log frame template – Circulated by Dr. Irmgard Again this is a reminder to all to complete and submit it | Kihara & Lyimo Gregory Gregory & Ngulu Stoilova |
| 4.2 MAI Meeting – Mbulu district 26-27th June 2014 - MAI stands for Manyara Agricultural Initiative. - Africa Rising was invited to highlight its activities in Manyara region and contribute to MAI vision - A-R presentation on mycotoxin studies and improved storage facilities captured interest of an NGO working with farmer groups (MVIWATA) - The NGO wants to include super bags/hermetic bags in its programme –an opportunity for scaling up the technology beyond A-R action sites. | The NGO has been linked with Simon |
| - AOB - The chair could not participate due to connectivity problems - Need to sort out technical hitches on “Skype group discussions” - Next meeting due first Friday August 2014 | Ngulu |