Africa RISING East and Southern Africa

2016 - 2021 project log frame

- Typlogies???

| INTERVENTION LOGIC | OBJECTIVELY VERIFIABLE INDICATORS | MEANS/SOURCE OF VERIFICATION | IMPORTANT ASSUMPTIONS |
| --- | --- | --- | --- |
| Purpose Provide pathways out of hunger and poverty for small holder families through sustainably intensified farming systems that sufficiently improve food, nutrition, and income security, particularly for women and children, and conserve or enhance the natural resource base. | - Per capita food consumption and availability at household level increases - Household income generated through agricultural activities increases - The proportion of children below 5 years having adequate nutrition and normal growth indicators increases - Acreage under sustainable land use practices increases | - Program ex-post evaluation report by IFPRI - Poverty monitoring surveys by local governments - Household expenditure surveys in project action sites by local governments | - Partner countries continue to invest in agriculture in a way that compliments program activities - Feed the Future priority countries and investments remain consistent with project - Political stability in countries with intervention sites |
| Project Outcome 1: Productivity, diversity, and income of crop-livestock systems in selected agro-ecologies enhanced under climate variability |  |  |  |
| OUTPUT | OBJECTIVELY VERIFIABLE INDICATORS | MEANS/SOURCE OF VERIFICATION | IMPORTANT ASSUMPTIONS |
| Output 1.1: Demand-driven, climate-smart, integrated crop-livestock research products (contextualized technologies) for improved productivity, diversified diets, and higher income piloted for specific typologies in target agro-ecologies [and scaled in Outcomes 4 and 5]. | - Numbers of research products* identified and suitability for target groups and areas, (*farmer approved varieties, technologies and their associated recommendations) - Numbers of research products assessed for performance across SI domains (environment, production, economic, social, and human) - Numbers of beneficiaries trained (at multiple scales, farmer, extension, researchers, students, other stakeholders, policy makers) - Numbers of partnerships and innovation platforms developed to support dissemination - Numbers of novel ICT dissemination approaches developed; Extent of adoption of technologies and associated research products - Numbers of recommendations developed based on impact in multiple SI domains of research products for different scenarios | - Research products data bases (CKAN) - Research products* described in published reports and journal papers (AR reports) - Partnership agreements and function (wiki and AR reports) - Reports on ICT delivery modes developed - Training reports and student thesis (AR reports) - Country level release of recommendations, technologies and research products (AR program reports and gazette) | - Demand for technologies and research products developed - Resource (human and financial) flow is maintained - Government support - political will and policy |
| Output 1.2: Climate smart crop and crop-livestock technologies and research products in targeted landscapes and semi-arid areas delivered. | - Number of research products that are identified as best bets for adaptation and mitigation purposes; Identification of areas and groups who can benefit through targeting of research products - Numbers of innovation platforms operating and related partnerships; Numbers of novel ICT modes of delivery - Numbers of beneficiaries trained in this area (at multiple scales) - Extent of adoption of climate smart research products - Number of government policy recommendations developed based on potential for impact on climate change adaptation and mitigation | - Research products including extension recommendations data bases (CKAN) - Partnership agreements and function (AR program reports) - Report on ICT delivery modes developed (wiki, AR program report) - Research products and adoption potential and actual, described in journal papers (AR reports, wiki) - Training reports and student thesis (AR reports) - Publication of policy briefs and changes in government policies (AR program reports and gazette) | - Demand for technologies and research products developed - Resource (human and financial) flow is maintained - Government support - political will and policy |
| Output 1.4: The impact of crop residues, forages, and other locally available organic resources on productivity quantified and disseminated, this is potentially part of ISFM within 1.1 [this is a sub-activity of output 1.1] | - Number of recommendations developed based on understanding of organic resources and interactions, and assessment of impact - Numbers of recommendations based on documentation of the findings regarding SI impact in multiple domains - Number of demonstrations and improved use of locally available organic resources - Number of partnerships, extension services and business models that support above. | - Research products and recommendations data bases (CKAN) - Extension briefs (AR report, wiki) - Research articles (AR reports) - Partnership agreements (AR program reports) | - Demand for recommendations and research products developed - Resource (human and financial) flow is maintained - Government support - political will and policy |
| Output 1.2: Required agro-inputs identified to increase productivity, diversity, and income for crop-livestock systems, including fodder, organic resources, fertilizer, and improved seeds [and scaled in Outcomes 4 and 5] |  |  |  |
| Output 1.3: Demand-driven, labor-saving and gender-sensitive research products to reduce drudgery while increasing labor efficiency in the production cycle piloted for relevant typologies in target areas [and scaled in Outcomes 4 and 5] | - Numbers of research products and recommendations that are gender sensitive and labor saving identified and suitability assessed for target groups and areas - Evaluating from a gender-lens the research products and technologies; Numbers of beneficiaries trained in this area (at multiple scales) - Number of partnerships, extension services that support above; Assess adoption of gender-sensitive technologies and associated research products, and document for policy recommendations | - Research products and recommendations data bases (CKAN) - Extension briefs (AR report, wiki) - Research articles (AR reports) - Training reports - Policy briefs (AR reports) - Partnership agreements (AR program reports) | - Demand for technologies, recommendations and research products developed - Resource (human and financial) flow is maintained - Government support - political will and policy |
| Output 1.4: Tools (included ICT-based)_for disseminating recommendations in relation to above research products, integrated in capacity development [and used in Outcomes 4 and 5] |  |  |  |
| Project Outcome 2: improve Natural resource integrity and resilience to climate change enhanced for the target communities and agro-ecologies | - Households income and food security from agricultural activities improved by? %. | - AR Program level Report (CG Space) - USAID Country level Quarterly Reports | - Political stability in target countries |
| OUTPUT | OBJECTIVELY VERIFIABLE INDICATORS | MEANS/SOURCE OF VERIFICATION | IMPORTANT ASSUMPTIONS |
| Output 2.1: Demand-driven research products for enhancing soil, land and water resources management to reduce household/community vulnerability and land degradation piloted in priority agro-ecologies and . [and scaled in Outcome 5] | - Number of households with increased resilience and adaptation to water stress and land degradation increased - Acreage of land under improved NRM | - Project Reports (field visits, surveys, RRA, PRA, Participatory evaluations) - NARS Bi-annual Reports - Newsletters, Wiki, websites - Videos, podcasts, blogs, publications, case studies and photo-films | - Donor support remains sustained - Target areas remain conflict free - Extreme events do not impact target areas (e.g. fires, floods, droughts) |
| Output 2.2: Innovative options for land and water management in selected farming systems demonstrated at strategically located learning sites [and scaled in Outcome 5] | - Number of demonstration and training sites - Diversity of innovative options demonstrated - Functional innovation platforms established/strengthened | - Project Reports - NARS Annual Reports | - Donor support remains sustained - Target areas remain conflict free - Extreme events do not impact target areas (e.g. fires, floods, droughts) |
| Output 2.3: Inclusive approaches and methods for collective action to deliver innovative water, soil and land resources management piloted in target communities [and scaled in Outcome 5] | - Diversity of approaches and methods - Number of stakeholders reached with innovative approaches/methods | - Project Reports (field visits, surveys, RRA, PRA, Participatory evaluations) - NARS Reports - Videos, podcasts, blogs, publications, case studies and photo-films | - Donor support remains sustained - Target areas remain conflict free - Extreme events do not impact target areas (e.g. fires, floods, droughts) |
| Project Outcome 3: EFood and feed safety, nutritional quality, and income security of target smallholder families improved equitably (within household) | - At least 95% of the food /feed produced/marketed and consumed have contaminant levels below the safety limits - Percentage increase in proportion of households diversifying their diets - Percentage increase in the proportion of children under 2/5 able to meet the minimum acceptable diet - Proportion of households with reduced expenditure on food | - Publications on food/feed safety interventions - Food/feed analysis analysis reports - Household/nutrition survey reports - Household expenditure/economic survey reports | - Stable political situation allowing research - Funding is available on time - Farmers and partners willing to participate |
| OUTPUT | OBJECTIVELY VERIFIABLE INDICATORS | MEANS/SOURCE OF VERIFICATION | IMPORTANT ASSUMPTIONS |
| Output 3.1: Demand-driven research products to reduce postharvest losses and improved food quality and safety piloted in target areas [and scaled in Outcome 5] | - Postharvest losses reduced to below 5% among target households - At least 95% of the food /feed produced/marketed and consumed have contaminant levels below the safety limits | - Postharvest loss assessment report/publications - Adoption studies - Qualitative studies on barriers/enablers to post harvest technologies - BTTT???? - Research publications | - Funding is available on time - Farmers are able to invest in technologies for postharvest reduction |
| Output 3.2: Nutritional quality improved through increased accessibility and use of nutrient-dense crops and livestock products | - Increase in the proportion of households with access to nutrient-dense crops, livestock and livestock products through production or purchase - Increase in the proportion of households incorporating nutrient dense crops, livestock and livestock products into their diets - Increase in the proportion of households/children diversifying their diets | - Food and nutrient analysis - Household nutrition survey reports - Acceptability studies report - BTTT???? - Research publications | - Funding is available on time - Farmers and partners willing to participate - Farmers willing to adopt nutrient dense foods - Markets are available for access to nutrient dense foods |
| Output 3.3: Capacity of farming communities and partners to use nutrient-dense crops and livestock product enhanced [including the use of decision support tools]. | - Percentage increase in the proportion of farm families producing diverse crop/fodder species - Percentage increase in number of local partners promoting diverse crop/fodder species | - Adoption study reports - Qualitative studies on barriers/enablers for diverse crop/fodder production and utilization - Food and feed safety assessments - BTTT???? - Research publications | - Funding is available on time - Farmers and partners willing to participate |
| Project Outcome 4: Functionality of input and output markets and other institutions to deliver demand-driven sustainable intensification research products improved | - Increased share of crop and livestock products marketed - Percentage increase in household income - Percent of households (including all gender groups and the youth) accessing market information - Percentage increase in productivity - [add indicator on agro-input markets, including seed, fertilizer, organic inputs, pesticides] | - Household and market survey reports (on CKAN) - Project monitoring reports | - Willingness of market actors to share data - Conducive political environment prevails |
| OUTPUT | OBJECTIVELY VERIFIABLE INDICATORS | MEANS/SOURCE OF VERIFICATION | IMPORTANT ASSUMPTIONS |
| Output 4.1: Access to profitable markets for smallholder farming communities and priority value chains facilitated | - Number of inclusive value chain analyzed - Number of market linkages developed | - Monitoring report | - Willingness of market actors to share data - Stakeholders are willing to cooperate - Enough market demand |
| Output 4.2: Collective and inclusive (gender- and typology-related) action models linking farmers to markets developed and piloted | - Number of communication channels used to provide market information - Number of farmers and traders (including all gender groups and the youth) accessing functional market information systems - Number of field days/ trade fair/open days where market | - Monitoring report - Documentaries of open days | - Market information adequately available |
| Project Outcome 5: Partnerships for the scaling of sustainable intensification research products and innovations operationalized |  |  |  |
| OUTPUT | OBJECTIVELY VERIFIABLE INDICATORS | MEANS/SOURCE OF VERIFICATION | IMPORTANT ASSUMPTIONS |
| Output 5.1: Opportunities for the use and adoption of sustainable intensification technologies identified for relevant farm typologies. | - Number of innovations redesigned to improve adoption guided by socio-economic context. - Number of policy recommendations made to support adaption and scaling. | - Project monitoring and review reports - Policy briefs developed by the research teams | - Agriculture focal area of investments by the target countries. - Partners remain committed to engage in project implementation. |
| Output 5.2: Strategic partnerships with public and private, initiatives for the diffusion , and adoption of research products established. | - Number of new partnership formed annually for technology, knowledge and dissemination. - Number of actors involved in each partnerships. - Number of IP and other partnership events conducted involving different stakeholder and actors. - Learning alliances, Innovation Platforms, etc | - Project monitoring and review reports - Partner reports - New MOUs farmed with partners - IP Meeting and partnership event reports | - Stakeholders have incentive to share knowledge and technology along the value chain. - Other complementary development agencies and partners continue to invest and support agriculture led growth |
| Output 5.3: Gender-sensitive decision support tools for farmers to assess technology-associated risk and opportunities used by partners and development partners | - Number of farmers using the decision support tools to guide adaption. - Number of scientists deploying decision support tools at on farm research. | - Project monitoring and review reports - Partner reports | - Gender inclusiveness remains focus area for investments by governments and partners |
| Output 5.4: Knowledge sharing centers and learning alliances within existent local and regional institutions including development actors developed. | - Number of IPs /partnerships established across the development landscape annually. - Number of new partnership farmed annually. - Number of old partnership expanded with new actors annually. | - New MOUs farmed with partners - IP Meetings and events | - Partners remain committed to invest and sustain R&D in agriculture. |
| Output 5.5: A technology adoption, monitoring, evaluation, and learning framework for use by the project team and scaling partners released [led by IFPRI and used by project partners] | - Number of scientist using M & E tools to track adoption. - Number of scientist using this information to modify technology delivery/pathways. | - Project monitoring and review reports - Partner reports | - Partners remain committed to invest and sustain R&D in agriculture. |